Prince George’s County Public Schools

Title I 1003(g) School Improvement Grant (SIG II)

First & Second Quarterly Report

Date Submitted March 7, 2012

Part I:  Executive Summary

A lesson learned in the SIG I process was the importance of partners.  In addition, it is important to provide an infrastructure of support within the district.  With that in mind, the district decided to use the restart model with a partner which would provide support around leadership support, academic supports, protocols for planning and teaching and family engagement.  In addition, the district expanded the role of the Turnaround Office with more subject content support and family engagement support.

Mosaica was selected as the partner.  The first six months of the partnership was a process of aligning expectations and deliverables.  The relationship was not in the tradition vein of an Educational Management Organization takeover, to more of a partnership.  The leadership support started slowly as it took time to build trust.  Eventually, the Mosaica staff was changed to create a stronger relationship with the principals.  The academic support came in the form of a computerized program called Mercury on-line.  This process required an alignment of the technology and an upload of student information.  While currently in place, there that been some issues in the full implementation of the program.  The district and Mosaica continue to work through the challenges.  The protocols for collaborative planning, student support planning and teacher planning were implemented early in the process and continue.  Family engagement continues to evolve.

The Turnaround Office has been able to provide subject content support and family engagement support.  In addition, the Turnaround Office has maintained critical and continued communication with Mosaica.  This has served to clarify expectations and deliverables.  The relationship continues to evolve in a positive direction.

Challenges to the turnaround effort continue to be staffing with highly effective teachers.   The district continues to examine hiring and placement practices to find the most highly effective teachers for the turnaround effort.  Additional challenges include the release of SIG funds to hire additional positions.  The turnaround content specialists were not in place until the end of the first marking period due to the grant loading and approval process.  The district continues to work through procedural challenges.

The leadership in the SIG II schools is well positioned to oversee instructional improvement and academic performance.  Gains in performance are noted in the appropriate section.

IA.  Strengths:

First Quarter

SIG II provided a unique opportunity for Prince George’s County Public Schools to reflect upon lessons learned in “Turnaround” to add two additional schools using the restart model.  Many question why the district selected this model over turnaround.  First, with the decrease in school funding and reduction in force, the turnaround model as written is counterproductive to our efforts to accelerating school achievement.  Replacing fifty (50) percent of staff would not have been an effective strategy in light of the difficulty of securing highly effective staff for the original SIG I schools, and the pool of candidates was not as vast as we would have preferred.

SIG II was different form SIG I in that it allowed the district to work closely with the restart partner to conduct funded pre-implementation activities to support the work.  Prince George’s County was successful at developing an RFP, hosting a meeting for potential partners, reviewing proposals, and collaborating to select the best company to partner with our two new SIG II schools: Oxon Hill Middle and Thomas Johnson Middle.

Needs Assessments were conducted at each school during the month of June.  Within two weeks of the needs assessment, Mosaica, our restart partner provided a narrative of their findings to support their work.  The needs assessment for each school is attached.

Staff meetings were held in June for two purposes. First, the Turnaround Director provided the vision of PGCPS Turnaround while discussing the unique aspects of the SIG II application to include the purpose for funding, staffing allocations, and an introduction to Mosaica.  Secondly, the president of Mosaica Education Turnarounds provided an overview of the company and a summary of the work that would be conducted in each of the schools to include intense professional development, professional development plans for each staff member, individual plans for students, role of additional staff, etc… Parent meetings followed reiterating the same message.

First Quarter

The needs assessment conducted in June of 2011 was helpful in planning an initial course of action for both schools and the list of deliverables was clear in its terms and derived directly from the grant application.

School staff was well informed as to the restart efforts and the anticipated changes that would occur.  Processes and procedures existed in each school and in the county itself to support restart efforts.  Collaborative planning meetings occurred regularly as did school-wide meetings around school culture and student achievement.

MTP offered 2 full-time staff members to work with both schools.

Second Quarter

The on boarding of experienced coaches and specialists accelerated the speed of implementation which has resulted in observable growth and proficiency in each school as was evidenced in the January 2012 SIG II Year 1 Monitoring Team’s Second Onsite Visit.  While schools are showing some documented growth in school culture and academic achievement, the beginning phases of implementation are now becoming habit and a way of life at both schools.

Mosaica gained better access to PGCPS data systems.

A change in Mosaica personnel has led to more effective communication between MTP and PGCPS.

IB.  Areas for Improvement:

First Quarter

As with any newly formed partnership, the collaboration between PGCPS and Mosaica has been slow to develop. According to Mosaica, the transition to a new school system and individual personnel in each school lasted longer than expected and access to school-wide data systems was difficult to initiate.

Selection of the additional positions was delayed due to the Notice of Grant Award.  As a result, the work of the school level coaches, math, reading, and data, did not begin until the end of October.  The same holds true for behavior specialist and parent intervention specialist.

Second Quarter

PGCPS and Mosaica worked collaboratively to restructure the implementation of deliverables.  Furthermore, vice president Dr. John Q. Porter, Chief Academic Officer, Dr. Duane Arbogast, and the Turnaround Director met November 22, 2012 to discuss PGCPS’ ongoing concerns with the implementation of deliverables as stipulated in the contract for services.  During this meeting, both parties agreed a replacement for the current leadership coach was in order.

According to Mosaica, the challenge in the second quarter mainly revolved around gaining ground on implementation and defining further the relationship between PGCPS and MTP.  Both parties have agreed to an implementation timeline and regular meetings have been scheduled to monitor activities.

Part II.  Monitoring

II A.  Turnaround Director’s Monitoring of SIG Restart Partner

The Turnaround Director meets, at a minimum, once a month with the restart partner to be provided status updates on the deliverables provided in the agreement.  Most meetings have been held in person.  There have been a few occasions in which conference calls were conducted in lieu of face-to-face meetings.

Listed below is a brief synopsis of each meeting:

August 31, 2011

Collaborative meeting between MOSAICA, principals, and TA Director to chart the course of the year based on the school’s vision and performance data (professional development plan for leadership and professional staff, goal setting, PBIS, etc.

September 14, 2011

This was a collaborative meeting between MOSAICA, principals, and TA Director to finalize the applicant screening and selection process.  Team reviewed resumes (behavior specialist and parent engagement specialist), made recommendations for interviews, developed interview questions and scoring rubric, and scheduled interviews.

September 27, 2011

Collaborative meeting between MOSAICA, both principals, and TA Director to discuss ELO and Mercury Online implementation:  technical requirements for and management of Mercury Online.

October 10, 2011

Collaborative meeting between MOSAICA, both principals, and TA Director to share ELO updates for each school.  Implementation status of Mercury Online (a major of component of the ELO) was also discussed and MOSAICA was asked to submit a Mercury Online Implementation Plan by Monday, October 17.

November 22, 2011

Collaborative meeting between MOSAICA and PGCPS to discuss the status of deliverables as stipulated in the agreement.  During this meeting, both parties agreed to replace the existing leadership coach for the remainder of the school year.

December 5, 2011

Collaborative meeting between MOSAICA, both principals, and TA Director to discuss the following:  Mercury Online implementation status; MOSAICA’s PD Plan for each school; upcoming 0.5 PD days (1/18; 2/13, 4/18); school-based workshops for teachers (money is available); MOSAICA-Principal partnership meeting schedule; parent-community meetings.  A discussion was also held concerning the need to realign some funds for classroom libraries across content areas and for RELA and math supplies.

January 9, 2012

Collaborative meeting between MOSAICA, both principals, and TA Director to discuss the MSDE SIG feedback from the first onsite visit, expectations around documentation for the second MSDE visits scheduled for February, and the monitoring tool developed by PGCPS to monitor MOSAICA.  The new MOSAICA Executive Coach (Dr. Robinson who replaced Mr. Gibson) attended this meeting.

II B.  Chief Academic Officer Monitoring of SIG Restart Partner

This table shows the dates and number of occurrences for each monitoring activity by the Chief Academic Officer of the Turnaround Director. Additionally, the Chief Academic Officer and Turnaround Director frequently discuss the status of the schools and implementation of deliverables.

First Quarter

| Schools | Quarterly Evaluation of test data by school | Quarterly Evaluation of Participation Data (Attendance, suspension, etc.) | Quarterly Meetings with Restart Partner Executive Leadership to discuss progress. |
| --- | --- | --- | --- |
| Oxon Hill Middle | November 9, 2011 | November 9, 2011 | November 9, 2011 |
| Thomas Johnson | November 9, 2011 | November 9, 2011 | November 9, 2011 |

Second Quarter

| Schools | Quarterly Evaluation of test data by school | Quarterly Evaluation of Participation Data (Attendance, suspension, etc.) | Quarterly Meetings with Restart Partner Executive Leadership to discuss progress. |
| --- | --- | --- | --- |
| Oxon Hill Middle | January 26, 2012 | January 26, 2012 | January 26, 2012 |
| Thomas Johnson | January 26, 2012 | January 26, 2012 | January 26, 2012 |

II C.  SIG Restart Partner Implementation of Deliverables

First Quarter

During the Pre-Implementation phase, MTP conducted observations of the teaching staff at both schools in June 2011 and made recommendations as to teacher and leadership staffing.  MTP President and other staff participated in 2 parent meetings and 2 staff meetings (one at each school) to provide an overview of the work that would occur at each school.  MTP staff also participated in Back-To-School Night at OHMS on September 6, 2011.  Position descriptions were provided for two content specialists, a data coach, Behavior Intervention Specialist and Parent Engagement Specialist.  MTP also conducted 4 days of professional development on Culture & Climate (Positive Behavioral Interventions and Support or PBIS) and Building Cultural Capital, the data cycle (Classroom-Focused Improvement Process) or CFIP) and Effective Teaching Strategies.  MTP staff did a preliminary analysis of school-wide MSA data.

MTP exceeded the expectation of access to a leadership coach on a bi-monthly basis by providing a Leadership Coach/Project Manager and Curriculum/Staff Development Coach in schools approximately 4 days a week.

Due to the late start of the content specialists and other required personnel, PGCPS and MTP revised the deliverables on September 12, 2011.  MTP participated in Collaborative Planning Meetings, when possible, to assist content area teachers in implementing the CFIP protocol.  MTP also participated in the interview process for content specialists and other personnel.  MTP conducted professional development on the Framework for Teaching and Data Analysis for School Leaders (OHMS).  MYP also re-delivered a professional development session on CFIP, upon the request of PGCPS.

In general, MTP staff offered support and technical assistance to school principals on each school’s particular area of focus.  Because Thomas Johnson Middle School retained its principal from the 2010-2011 school year many reform programs were already in existence.  PBIS had been formally introduced as well as significant work on planning within collaborative planning meetings.  TJMS choose to deepen its work on the data cycle and planning for instruction while Oxon Hill Middle School choose to focus its initial efforts on Culture and Climate and student engagement.  Both schools worked to refine the PBIS programs implemented in previous years and spent a significant amount of time deciding upon what incentives would work best with their respective populations.

Second Quarter

The speed of implementation was accelerated with the arrival of two content specialists, a Data Coach, a Behavior Intervention Specialist and Parent Engagement Specialist.  During the week of November 15, 2011, MTP conducted a 3-day Orientation for Coaches and Specialists with sessions on making staff familiar with the SIG grants and the relationship between PGCPS and MTP, the coaching relationship and adult learners, and leading the CFIP protocol.  The Orientation also included significant time for action planning with each school team.

Leadership Staff at both schools began to implement new programs and revise existing protocols for higher efficiency in supporting student achievement.  Content specialists delivered professional development sessions of various lengths on observed areas of need.  These sessions continue to give teachers explicit instruction in writing SMART objectives and planning for instruction.  Each school also instituted ½-day data analysis and planning sessions after FAS testing for content area teachers.

As previously stated, each school has a different area of focus.TJMS is offering additional professional development in Classroom Management and Differentiated Instruction while OHMS is developing its PEACE Initiative (Positive Energy Activates Constant Elevation), a comprehensive program aimed at school culture, climate and empowerment.  Both schools continue to review processes and procedures for operations and documentation.

MTP and PGCPS staffs began the implementation of Mercury Online in both schools and continue to work on procedures to ensure that this program will be successful for all students who participate.

In January of 2012 upon an agreement between MTP and PGCPS, MTP brought in a new Leadership Coach/Project manager who has formalized and refined the Executive Coaching sessions and increased the amount of communication between MTP and the PGCPS Turnaround Director.

Part III. Progress

III A.  Benchmark Data

IIIA1:  Reading Benchmark Data

This chart shows the Quarter 1 Reading Benchmark Results By School and Grade Level.

County FAST IReading Average

6th Grade – 71				7th Grade – 75				8th Grade – 79

Both Thomas Johnson and Oxon Hill Middle began the school year with solid RELA teams and student achievement data is reflective of the teams’ efforts.  Students in the 6th and 7th grade were a percentage point under the County average; however, students enrolled in the 8th grade exceeded the County average.

Students at Oxon Hill Middle exceeded the County average at both grade levels.

This chart shows the Quarter 2 Reading Benchmark Results by School and Grade Level.

County FAST II Reading Average

6th Grade – 72.9			7th Grade – 73.2			8th Grade – 77.9

Reading data at Thomas Johnson suggests students are increasingly working towards and/or meeting the standard.  Although there was a decline in student performance from 1st quarter in the 6th grade, the team has worked closely with the reading coach and instructional specialist to adjust instruction to meet the needs of students.  7th grade students exceeded the County average in achievement.  8th grade students were slightly under the County average.

Students at Oxon Hill Middle exceeded the County average for grade 7 and were slightly under the County average for grade 8.

This chart shows the FAST I and FAST II Reading Benchmark Results by School and Grade Level.

IIIA2. Math Benchmark Data

This chart shows the Quarter 1 Math Benchmark Results by School and Grade Level.

County FAST IMathematics Average

6th Grade – 59			7th Grade – 44			8th Grade – 52

The County average for achievement in 6thGrade was 59 percent.  According to the chart, Thomas Johnson was 13 percent below the County average.  7th grade students achieved at a rate of 53 percent which is 11 percent abovethe County average.  On the other hand, 8th grade students achieved at a rate of 43 percent which is 9 percent below the County Average.

Oxon Hill Middle School was significantly lower than the County average for 7th grade.  Student achievement for 7thgrade was 29 percent.  Students in the 8th grade met the County average.  To assist with improving student achievement in Mathematics, the newly selected coaches and the instructional specialist will provide intensive support to teachers and students.

This chart shows the Quarter 2 Math Benchmark Results by School and Grade Level.

County FAST II Mathematics Average

6th Grade – 61.8			7th Grade – 62			8th Grade – 56.3

The County average for achievement in 6th Grade was 61.8 percent.  According to the chart, Thomas Johnson was 26 percent below the County average.  Student achievement in the 7th and 8th grade was significantly better than students currently enrolled in the 6th grade.  7th grade students achieved at a rate of 55 percent which is 7 percent below the County average.  Furthermore, 8th grade students achieved at a rate of 50 percent which is 6 percent below the County Average.

Oxon Hill Middle School, while under the County Average, showed growth for students enrolled in Math 7.  Student achievement for 7th grade was 39.35 percent.  Students in the 8th grade met the County average of 56 percent which represents a 15 percent increase in student achievement.

This chart shows the FAST I and FAST II MathematicsBenchmark Results by School and Grade Level.

III B.  Attendance

This table shows the Overall Attendance Percentages from the 2009 School Year to Date for the 2011-2012 School Year.

Source: www.mdreportcard.org and PGCPS’ Data Warehouse

| School | 2009 | 2010 | 2011 | 2011-2012 1st Quarter | 2011-2012 2nd Quarter | 2011-2012 3rd Quarter | 2012 |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | % | % | % | % | % | % | % |
| Oxon Hill Middle | 94.5 | 94 | 93.7 | 95.68 | 94.26 |  |  |
| Thomas Johnson Middle | 95 | 95 | 95 | 96.74 | 96.07 |  |  |

III C. Suspensions

This table shows the number of Suspensions by School for the current School Year 2010-11.

Source: PGCPS’ Data Warehouse

| School | 2010-2011 1st Quarter | 2011-2012 1st Quarter |  | 2010-2011 2ndQuarter | 2011-2012 2nd Quarter |  | 2010-2011 3rd Quarter * | 2010-2011 4th Quarter |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Oxon Hill Middle | 29 | 27 |  | 41 | 40 |  |  |  |
| Thomas Johnson | 3 | 33 |  | 32 | 32 |  |  |  |