# Priority SIG II Monitoring and Fiscal Team First Onsite Visit Feedback

# Maryland State Department of Education—Title I School Improvement Grant (SIG), section 1003(g)

LEA: Prince George’s County Public Schools (PGCPS) LEA Turnaround Director: Ed Ryans LEA Turnaround Lead: Duane Arbogast, Acting Deputy Superintendent of Academics Date Shared with PGCPS: October 31, 2012 MSDE SIG II Program Team Member: Gail Clark Dickson Date of SIG Program Team Onsite Visit: October 2, 2012 MSDE SIG II Fiscal Team Member: Geri Taylor Lawrence Date of SIG Fiscal Team Onsite Visit: October 16, 2012

Title I School Improvement Grant (SIG):  The School Improvement Grant (SIG) Program, authorized under section 1003(g) of Title I of the Elementary and Secondary Act of 1965, provides funding through State educational agencies (SEAs) to local educational agencies (LEAs) with the lowest-achieving schools that have the greatest need for the funds and demonstrate the strongest commitment to use the funds to raise significantly the achievement of students.  The United States Department of Education (USDE) views the large infusion of Federal funds into the SIG program through the American Recovery and Reinvestment Act of 2009 (ARRA) as a historic opportunity to address one of the most intractable challenges for America’s education system: turning around or closing down our Nation’s persistently lowest-achieving schools.  USDE approved Maryland’s Flexibility Plan in May 2012 which included Maryland’s SIG II schools as Priority Schools.

# Purpose of the SIG II Year 2 Monitoring and Fiscal Teams’  First Onsite Visit:   As approved by USDE, MSDE, through SIG Monitoring Teams, will conduct three onsite monitoring visits annually in each LEA that receives a school improvement grant to ensure that the LEA is implementing its intervention model fully and effectively in Maryland’s Tier I and Tier II schools.  As part of the SIG II Year 2 first onsite visit for school year 2012-2013, the SIG Team will interview members of the LEA Central Support Team which is the leadership body for planning, implementing, supporting, monitoring, and evaluating the LEA’s approved SIG Plan.  In addition to the interviews, the MSDE SIG Fiscal Team will monitor SIG II Year 1 budgets that include the LEA Budget, Consolidated Budget, and the individual SIG II schools’ budgets.

| Table Organization of SIG II Year 2 Program and Fiscal Teams’ First Onsite Visit Feedback |
| --- |
| Table 1 | PGCPS Central Support Team Interview Questions and Responses |
| Table 2 | Priority SIG II Year 1 LEA Budget (Part of Consolidated Budget) |
| Table 3 | Priority SIG II Year 1 Consolidated Budget |
| Table 4 | Priority SIG II Year 1 LEA Budget |

Table 1

LEA Commitments and Capacity LEAs that accept 2009 Title I 1003(g) school improvement funds agree to establish a central support team to oversee the implementation of the selected models in Tier I and Tier II schools as well as the strategies that the LEA will implement in Tier III schools. The Title I office must be represented on the Central Support Team. The team will coordinate the support, as well as monitor, and assess the progress for each of the identified schools. Complete the Table 4.A. Add rows as needed.

Turnaround Executive Committee for 2012-2013

PGCPS shared the following changes in staff on the Turnaround Executive Committee for 2012-2013 school year: The committee meets once a month and is chaired by Dr. Duane Arbogast, who is now the Acting Deputy Superintendent of Academics for PGCPS. In addition to the main committee and subcommittees, the Turnaround Office has a staff of 6 members. At the time of MSDE’s monitoring, the student support specialist in the Turnaround Office is vacant. Mr. Douglass Anthony is the Acting Chief of Student Services on the committee. Ms. Glenda Willis is the new PBIS Coordinator on the committee. Ms. Stephanie Cochran is the new SIG Budget Liaison (Grants Management Financial Office) on the committee.

How often will the LEA 1003g central support team meet? PGCPS shared the following response to this question: The Turnaround Executive Committee meet monthly.

How often will they report on their work and the work on Tier I, II and III schools to the Superintendent? PGCPS shared the following 2012-2013 change in its response to this question: The LEA Superintendent is apprised monthly of the SIG II implementation progress by Dr. Duane Arbogast, Acting Deputy Superintendent of Academics in one-on-one meetings. The Turnaround Director met with the new Interim Superintendent in PGCPS in early September to discuss the work of the turnaround office and schools in PGCPS. He will begin attending the monthly turnaround executive committee meeting in October.

How often will they report on their work and the work on Tier I, II and III schools to the Board of Education? PGCPS shared the following 2012-2013 change in its response to this question: The Acting Deputy Superintendent of Academics, along with the Superintendent, will direct reporting information via the Turnaround Director to the PGCPS Board of Education on the progress of Tier II schools, including student academic achievement, teacher evaluations, and principals/assistant principals leadership development. Has the LEA 1003(g) central support team met prior to the submission of the grant application to review the individual school descriptions and to discuss how it will coordinate and manage the support, monitoring and assessment outlined in those plans? __X___ Yes _____ No If no, briefly describe the plans for the central support team to begin work on the Tier I, II, and III schools? Not applicable for SIG II Year 2 Monitoring by MSDE What role has or will the LEA 1003(g) central support team play in the creation of annual goals for student achievement and annual review/assessment of progress based on these goals described in sections 2 and 3 of this proposal? PGCPS shared the following 2012-2013 change in its response to this question: PGCPS will set Key Performance Indicators for 2012-2013 for each school; “smart goals” will be set with a targeted increase of 10% being a realistic achievable increase. What steps will the LEA take to ensure that the school improvement funds are utilized (1) in a timely way and (2) effectively and efficiently to support the required components of the selected intervention? Specifically, what assurances will the LEA make that schools and LEA support teams have access to these funds, even during annual rollover processes? How will the LEA support principals’ timely and effective use of these funds? PGCPS shared the following 2012-2013 changes in its response to this question: A 100-day planning process was developed to allow for timelier spend down of funds and reduce the needs of future amendments. The Turnaround Office Compliance Specialist worked closely with both schools to develop a budget. During the process, the compliance specialist collaborated with the assigned budget specialist to ensure all line items and explanations were consistent with the spirit of the grant and met appropriate guidelines. [Programmatic amendments were created, when appropriate.] The proposed SIG II, Year 2 budget was sent to MSDE for pre-approval. PGCPS developed the following actions: To monitor the spend-down of the grant, monthly SIG Budget meetings will occur, facilitated by the district’s Chief Financial Officer. Danielle Curtis, Cynthia Moore, and Myra Grzeskiewicz from the Grants Management Financial Office and the Turnaround Office will collaborate to provide monthly statements for each SIG school and the turnaround office to advise of remaining balances. The Chief Financial Officer (CFO) has reorganized his division to provide an additional layer of support for all grants within the district. The CFO has aligned budget analysts and accountants into one unit that will report to the Director of Finance and Treasury Operations. Stephanie Cochran was assigned as a budget liaison to assist with spend-down and other budget monitoring. The 1003g SIG application has been revised and updated to more accurately reflect current initiatives in the schools. Within this proposal, the LEA identified actions taken or in the planning to support individual Tier I and Tier II schools’ implementation of the selected interventions. Looking across the commitments made for the schools, and considering as well the strategies selected by the LEA for identified Tier III schools, what additional actions will the LEA take to ensure that the selected interventions are implemented as designed and to make the other changes such as: (1) realignment of other resources; (2) removal of expectations that might run counter to the approach outlined in the selected intervention; (3) timely modification of practices and policies (those anticipated ahead of time and those that will emerge during implementation); and (4) engaging in reflective and sustained, collaborative conversation and planning to ensure that improvement efforts can be sustained once this funding ends? Realignment of other resources: The grants financial office has been reinstated and reorganized, under Wayne Upshaw. Removal of expectations that might run counter to the approach outlined in the selected intervention for the 2012-2013 school year: PGCPS has provided more enhanced and targeted support between the system’s Human Resources Department and the Turnaround Office. For 2012-2013, the turnaround schools received no “forced placements” and were able to successfully complete a number of administrative transfers. Timely modification of practices and policies (those anticipated ahead of time and those that will emerge during implementation) for the 2012-2013 school year: PGCPS extended the instructional day (by 40 minutes) for all middle schools this year. Each turnaround school was allowed to adapt its master schedule to incorporate a variety of extra activities to include remediation, enrichment, advisory period, etc. Turnaround schools do not share buses with high school students (a new trend in PGCPS this year). All SIG II schools will continue to implement extended learning programs. All programs will begin by October 2012. ELO Program Descriptions will be forwarded to MSDE by October 15, 2012. Engaging in reflective and sustained, collaborative conversation and planning to ensure that improvement efforts can be sustained once this funding ends. Collaborating with Maryland Center for Inclusive Education and hosting monthly meetings with Mosaica. Mid-Atlantic Equity Center is no longer a contracted partner; Planning to renew contract with Mid-Atlantic Equity Center. PGCPS continues to partner with MSDE’s Breakthrough Center to provide services for both district and schools. The Chief Financial Officer (CFO) has reorganized his division to provide an additional layer of support for all grants within the district. A budget liaison was hired (Stephanie Cochran) to assist with spend-down and other budget monitoring. What are the major challenges to full and effective implementation of all components of the SIG grant that the LEA 1003 (g) central support team has identified and how will the team address these challenges in the early phases of the work? PGCPS shared the following 2012-2013 changes in its response to this question: PGCPS anticipates lesser challenges this year to the full and effective implementation of all components of the 1003(g) grant. With the implementation of a longer school day for students, transportation has been the major challenge.

Table  2

| Priority SIG II Year 1 LEA Budget (Part of Consolidated Budget) LEA: Prince George’s County Public Schools |
| --- |
| MSDE Fiscal Reviewer: Geri Taylor Lawrence Monitoring Date: October 16, 2012 |
| SIG II Year 1 LEA Allocation: $ 320,451 | LEA Budget Spent: Amount- $ 243,055 Percentage - 76 % | Spend Down Data as of: October 15, 2012 |
| Salaries & Wages | Fixed Charges | Other |
| Budgeted: $ 125,796 | Budgeted: $ 47,212 | Budgeted: Indirect Cost $ 147,443 |
| Encumbered: $ 0 | Encumbered: $ 0 |  |
| Spent (amount): $ 125,796 Spent (%): 100 % | Spent (amount): $ 45,607 Spent (%): 97 % | Spent (amount): $58,320 Spent (%): 40% |
| How much of the LEA SIG II 1003(g) Title I Part A, budget has been expended to date (amount and %)? PGCPS provided documentation that indicated that the LEA has spent $243,055. This amount is 76% of the LEA budget. |
| Is the LEA spending consistent with budget timeline? If not, what steps are being taken to expend the funds as planned? PGCPS indicated that spending is consistent with the timeline in all categories. |
| What action steps or planned activities have not taken place that would impact the LEA budget? PGCPS explained that all planned activities are occurring. PGCPS indicated that the remainder of the indirect cost will be posted on December 30, 2012 at the end of the grant period. |
| Has a budget amendment been submitted? If yes, what budget changes were requested for the LEA? PGCPS indicated that no amendment has been done that will impact the budget LEA portion of the grant. |
| How often are LEA expenditures monitored? Who monitors? PGCPS indicated that monitoring for the LEA budget was conducted on June 27, 2012. PGCPS explained that quarterly spend down meetings have been changed to monthly meetings and will begin on October 22, 2012. These meetings are held to discuss the activities and spending of the LEA budget. Stakeholders in attendance at these meetings are Turnaround Director, Turnaround Budget Specialist, Director of School Leadership and staff from Budget Management Services. |

Table  3

| Priority SIG II Year 1 Consolidated Budget LEA: Prince George’s Public Schools |
| --- |
| MSDE Fiscal Reviewer: Geri Taylor Lawrence Monitoring Date: October 16, 2012 |
| SIG II 1003(g) Title I, Part A |
| Total Allocation | $ 2,644,942 |
| Amount Spent | $ 1,705,133 |
| Percent Spent | 65% |
| Amount Encumbered | $ 111,843 |
| Spend Down Data as of : | October 15, 2012 |

Table  4

Priority SIG II Year 1 LEA Budget LEA: Prince George’s County Public Schools

MSDE Fiscal Reviewer: Geri Taylor Lawrence Monitoring Date: October 16, 2012

SIG II Year 1 LEA Allocation: $ 933,755

Spend down as of: October 15, 2012

* Contracted Services -Budgeted: $ 933,755

Encumbered: $ 0

Spent (amount): $ 929,061 Spent (%): 99 %

How much of the LEA SIG II budget has been expended to date (amount and %)? PGCPS provided documentation that indicated that the LEA has spent $ 929,061. This amount is 99 % of the LEA budget. No additional funds have been encumbered.

Is the LEA spending consistent with budget timeline? If not, what steps are being taken to expend the funds as planned? PGCPS indicated that the grant period has ended and final provisions for liquidation of funds are in progress.

What action steps or planned activities have not taken place that would impact the LEA budget? PGCPS explained that all planned activities have taken place.

Has a budget amendment been submitted? If yes, what budget changes were requested for the LEA? PGCPS indicated that no amendment to reallocate funds has been submitted to MSDE since November 2011.

How often are LEA expenditures monitored? Who monitors? PGCPS provided documentation that showed that monitoring for the LEA budget was conducted on June 27, 2012. PGCPS explained that the next monthly spend down meeting for all SIG grants will be held October 22, 2012.

*Amounts changed to reflect an amendment.