Baltimore City Public Schools

Title I 1003g School Improvement Grant II

2nd Quarterly Report

SY2011-12

The contents of this report align with the quarterly reporting metrics approved in the 1003 (G) application Baltimore City Schools submitted to the Maryland State Department of Education.

Executive Summary

Data from the first and second quarters of the 2011-2012 school year (SY2011-12) show that implementation of the 1003(g) School Improvement Grant (SIG) in Baltimore City Public Schools is on schedule. *

Strengths:

- City Schools continues to foster relationships with community partners in order to utilize community resources to increase outcomes in school climate and culture as well as academic performance. For example,  Augusta Fells Savage Institute of Visual Arts, in partnership with the Druid Heights Community Development Corporation has started a successful after school program. Students are provided academic enrichment and service learning opportunities. Participation in the program is high and parents of children participating in the program are attending meetings and events related to the program. The network team has also seen increased parental involvement in other school-wide activities as well as a result. It is partnerships like these that will help City Schools keep students engaged.

Opportunities for Improvement:

- Many of the principals in SIG schools are either new principals or are new to City Schools. The Executive Directors, network teams and Office of Turnaround Schools is committed to providing additional support and resources in terms of leadership skills, district initiatives, and instructional framework in order to promote a positive school culture and increase achievement.

- While Human Capital has encouraged a tighter selection process for teachers in Turnaround Schools, City Schools must continue to foster a more targeted approach to hiring in order to ensure that high quality, experienced leaders are working with our lowest performing schools.

- City Schools continually looks for ways to support SIG schools with budget management and spending according to the provisions of the grant.

*It is important to note that much of the data presented in this report is tentative and/or preliminary and as such is highly subject to change. Data will be updated to reflect any changes during subsequent quarterly reports.

Quarterly Report

- Overview

This report reviews the required information pursuant to the Baltimore City Public Schools submission of the 1003 (g) School Improvement Grant.  The report is formatted to give an overview of each section of data.

- Monitoring

- Bi-Weekly School Support Visits

All seven of Baltimore City’s 1003(G) schools have been strategically assigned to School Support Networks 15 or 16. These Networks have an additional team member assigned to support the academic needs of the schools, and the clustering of these schools into common Networks allows for additional collaboration opportunities at monthly Network meetings. Table 1* shows the number of hours, by support type, that Networks have spent supporting 1003(G) schools thus far during the first, second, and third quarters of SY2011-12. Examples of on-site support provided by School Support Networks include facilitation of in-school professional development activities, informal classroom observations, coordinating resources, and operational support. Examples of off-site support provided by School Support Networks include conducting or planning for professional development across schools, reviewing school plans, and reviewing school data for planning purposes. Examples of Central Office support provided by School Support Networks include planning for internal meetings, attending departmental meetings, and administrative support.

*Before the 2011-2012 school year, Baltimore City Public Schools made key organizational changes that better position the district office to support schools. This reorganization increases the capacity of the school support networks currently charged with supporting schools by moving many more district office employees and services to the networks, where they can work closely with schools to ensure effective support tied directly to school-specific needs.  New positions to evaluate and coach school leaders were created to improve the ability to develop and support school leaders in providing the great schools that students and communities deserve. This function becomes even more important with the passage of the new contracts with administrators, teachers and school personnel, which tie evaluation and compensation to how schools and students are performing.

During this reorganization, certain functions were transferred to the networks in order to increase transparency and accountability. One such function is the collection of data on the total turnaround school support hours by school and support type. During the transition, this data was not tracked as systems were being updated to reflect the new structure.  Data collection resumed in January of 2012 and will be reflected in subsequent quarterly reports. While previous reports reflected support from both the Central Office and the networks, forthcoming data will focus exclusively on network support and should not be directly compared to previous years’ data.

Monthly Monitoring Visits From Turnaround Project Staff

The monthly monitoring consists of several major components, including on-site visits to each of the seven 1003(G) schools, training and meetings of the Central Office SIG Monitoring Team (CST), and the feedback loop to the school leadership teams.  Figure 1 illustrates the monthly SIG monitoring process.

Figure 1. SIG Central Office Support Team Monthly Monitoring and Report Cycle

We are striving to make the SIG monitoring in Baltimore City Public Schools a dynamic process that is responsive to the implementation needs of our schools. To this end, a fundamental component of the SIG monitoring process is the continual feedback loop. Feedback from key SIG stakeholders (including school leadership teams, restart operators, SIG Monitoring Team members, and LEA leadership) is solicited at multiple points during the monthly monitoring cycle.  During the third quarter of SY2010-11, this feedback resulted in updates and revisions to monitoring tools and processes designed to improve the effectiveness of the SIG Monitoring Team and associated supports for schools. Principals were given greater flexibility in identifying focal points for school observations; the classroom observation tool used by SIG Monitoring Team members was updated to allow a more comprehensive capture of evidence related to monitoring goals; and the manner in which key trends and suggested next steps are communicated to school leadership teams was streamlined.

Table 2 shows the frequency and number of completions for each monitoring component.

Table 2. SIG Monitoring Components for 1003(G) Schools

Source: Turnaround Schools’ Programmatic Data – SY2011 – 2012 to Date

| SIG Monitoring Components | Frequency | Number completed to date for SY2011-12 |
| --- | --- | --- |
| CST Training | Monthly | 24 |
| On-Site Monitoring Visits | Monthly | 9 |
| Pre-Observation Planning |  | 9 |
| Classroom Observations |  | 9 |
| Post-Observation Debrief |  | 9 |
| Immediate Feedback to School |  | 9 |
| Follow-Up Meetings | As needed | 24 |
| Comprehensive Feedback to Schools | Monthly | 9 |
| *Due to the quarterly schedule, the majority of November visits took place in the second quarter. |

- Progress

The benchmark tests align with the City Schools Curriculum and pacing guides for the first, second, and third benchmark. Benchmark data is used to supplement the district’s understanding of student learning, to inform instruction and instructional planning, identify professional development opportunities for teachers, and gauge progress on short academic goals at specific times during a curriculum sequence. City Schools also uses benchmark data to identify struggling students and/or skills that necessitate re-teaching, particularly items that are aligned with Maryland’s Standards.  Because they have a variety of origins, benchmark and common assessments do not usually meet the rigorous criteria for reliability and validity achieved by external assessments. When done well, however, they can model the content, format, and rigor of the high-stakes external assessments and may be predictors of student performance on them. Benchmark B was taken on October 17, 2011.

Table 1.  AYP HSA Results with Targets

Source: City Schools’ Data Link

Benchmark B data for high school students is unavailable. While 2011 data is also not yet available, the following chart represents the 2010 Adequate Yearly Progress (AYP) scores for Augusta Fells Savage Institute of Visual Arts with the school’s corresponding targets not previously reported. The AYP score is defined by how many 12th graders, eligible to graduate, have passed the HSA in 12th grade or previous grades (cumulative through high school).

|  | English | Algebra I |
| --- | --- | --- |
| School | 2010 | 2010-2011 Target Score | 2010 | 2010-2011 Target Score |
| Ben Franklin | 55.6 | 36.4 | 25.7 | 28.6 |
| Frederick Douglass | 42.6 | 40.5 | 32.1 | 32.5 |

Tables  2-4.  HSA Results, Turnaround Schools 2009-2011 w/District and Turnaround Average

Source: City Schools’ Data Link

Comprehensive data represents the scores of all students who took the HSA in the given year.

HSA English Results, Turnaround Schools 2009-2011

| Grade | Pass % | District Average |  | Turnaround Schools | Frederick Douglass |  | Ben Franklin |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2009 | 2010 | 2011 | 2009 | 2010 | 2011 | 2009 | 2010 | 2011 | 2009 | 2010 | 2011 |
| Grade 9 | Pass | 25.1% | 26.8% | 24.4% | 15.6% | 17.9% | 34.1% | 10% | 11.4% | 40% | - | 42.9% | 0% |
| Grade 10 | Pass | 45.8% | 42.9% | 41.9% | 24% | 24.4% | 18.7% | 21.5% | 25.4% | 10.9% | - | - | 30.1% |
| Grade 11 | Pass | 17.9% | 17.8% | 16.3% | 12.9% | 12.5% | 11.0% | 13.5% | 12.6% | 13.5% | - | - | 19.0% |
| Grade 12 | Pass | 13.8% | 12.3% | 14.4% | 11.5% | 8.4% | 9.0% | 10% | 6.2% | 10.0% | - | - | - |
|  | HSA Math Results, Turnaround Schools 2009-2011 |  |  |  |

| Grade | Pass % | District Average |  | Turnaround Schools | Frederick Douglass | Ben Franklin |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2009 | 2010 | 2011 | 2009 | 2010 | 2011 | 2009 | 2010 | 2011 | 2009 | 2010 | 2011 |
| Grade 9 | Pass | 31.8 % | 23.2% | 26.0% | 17.7% | 10.9% | 17.7% | 8.4% | 8.2% | 7.9% | 32.9% | 17.5% | 26.2% |
| Grade 10 | Pass | 17.5% | 9.7% | 12.1% | 6.4% | 6.2% | 12.0% | 5.2% | 5.4% | 8.7% | - | 16.9% | 15.8% |
| Grade 11 | Pass | 13.2% | 10.6% | 10.0% | 6.1% | 5.3% | 8.1% | 7.2% | 5.0% | 7.1% | - | - | 19.0% |
| Grade 12 | Pass | 11.0% | 7.6% | 9.2% | 4.0% | 5.9% | 10.4% | 3.6% | 7.1% | 10.5% | - | - | - |

|  | HSA Science Results, Turnaround Schools 2009-2011 |
| --- | --- |
| Grade | Pass % | District Average |  | Turnaround Schools | Frederick Douglass | Ben Franklin |  |
|  |  | 2009 | 2010 | 2011 | 2009 | 2010 | 2011 | 2009 | 2010 | 2011 | 2009 | 2010 | 2011 |
| Grade 9 | Pass | 63.8% | 59.3% | 63.2% | 12.5% | 21.3% | 19.0% | - | 22.2% | 33.3% | - | 14.3% | 20.3% |
| Grade 10 | Pass | 38.8% | 35.1% | 29.0% | 18.2% | 25.8% | 24.0% | 21.1% | 22.0% | 17% | - | 50.8% | 38% |
| Grade 11 | Pass | 38.8% | 34.5% | 24.3% | 25.9% | 29.3% | 9.0% | 19.3% | 21.4% | 8.8% | - | - | 17.6% |
| Grade 12 | Pass | 12.5% | 12.6% | 12.3% | 8.6% | 8.4% | 8.2% | 7.3% | 5.7% | 7.3% | - | - | - |

The Turnaround Schools average for MSA English pass rate has steadily improved over the past three years in the ninth and tenth grades. The Turnaround Schools have also shown significant gains over the past three years in Algebra- some grades having doubled their pass rates from the 2010-2011 school year. While demonstrating significant improvements, compared to district averages, the three Turnaround High Schools have room for growth.

Frederick Douglass High School had a ninth grade MSA English pass rate of 40% during the 2011-2012 school year, a nearly 30% increase from the previous year. However, the rate for grades ten through twelve remain constant at approximately 10%. Similarly, MSA Math scores hover just under 10% for all grades. Ninth graders at Frederick Douglass are also demonstrating gains in science. While incremental improvement was demonstrated from 2009 to 2011, math and science continue to be targeted areas of improvement for Frederick Douglass High School.

While data for Benjamin Franklin High School at Masonville Cove is limited, slight improvements are evident in ninth grade Algebra and Science.

Table 5. Benchmark B Reading Results, Turnaround Schools SY2010-2011 and SY2011-2012

Source: City Schools’ DataLink

| Grade | Proficiency Level | District Average for All Schools- Grade Level and Test | Average for Turnaround K-8 Schools--Grade Level and Test | School |
| --- | --- | --- | --- | --- |
|  |  |  |  | Cherry Hill |
|  |  | B 10/26/10 | B 10/17/11 | Delta 2010-2011 | B 10/26/10 | B 10/17/11 | Delta | B 10/26/10 | B 10/17/11 | Delta 2010-2011 |
|  |  |  |  |  |  |  | 2010-2011 |  |  |  |
| 3 | Advanced | 12.20% | 12.45% | 0.25% | 6.85% | 14.29% | 7.44% | 5.56% | 0.00% | -5.56% |
|  | Proficient | 40.20% | 34.84% | -5.36% | 36.99% | 50.65% | 13.66% | 38.89% | 20.69% | -18.20% |
|  | Basic | 47.60% | 52.71% | 5.11% | 56.16% | 35.06% | -21.10% | 55.56% | 79.31% | 23.75% |
| 4 | Advanced | 16.40% | 13.17% | -3.23% | 10.53% | 5.48% | -5.05% | 0.00% | 6.67% | 6.67% |
|  | Proficient | 33.50% | 31.30% | -2.20% | 21.05% | 23.29% | 2.24% | 21.62% | 10.00% | -11.62% |
|  | Basic | 50.10% | 55.54% | 5.44% | 68.42% | 71.23% | 2.81% | 78.38% | 83.33% | 4.95% |
| 5 | Advanced | 13.60% | 11.90% | -1.70% | 1.64% | 6.58% | 4.94% | 8.00% | 6.25% | -1.75% |
|  | Proficient | 29.30% | 32.45% | 3.15% | 21.31% | 39.47% | 18.16% | 24.00% | 6.25% | -17.75% |
|  | Basic | 57.10% | 55.65% | -1.45% | 63.93% | 53.95% | -9.98% | 68.00% | 87.50% | 19.50% |
| 6 | Advanced | 11.70% | 9.13% | -2.57% | 2.02% | 0.48% | -1.54% | 4.17% | 0.00% | -4.17% |
|  | Proficient | 29.00% | 24.44% | -4.56% | 20.71% | 23.67% | 2.96% | 25.00% | 12.50% | -12.50% |
|  | Basic | 59.30% | 66.43% | 7.13% | 77.27% | 75.85% | -1.42% | 70.83% | 87.50% | 16.67% |
| 7 | Advanced | 12.70% | 7.39% | -5.31% | 4.17% | 2.26% | -1.91% | 4.76% | 3.23% | -1.53% |
|  | Proficient | 34.60% | 32.15% | -2.45% | 17.86% | 28.81% | 10.95% | 52.38% | 19.35% | -33.03% |
|  | Basic | 52.80% | 60.46% | 7.66% | 77.97% | 68.93% | -9.04% | 42.86% | 77.42% | 34.56% |
| 8 | Advanced | 10.90% | 0.00% | -10.90% | 4.46% | 2.99% | -1.47% | 0.00% | 0.00% | 0.00% |
|  | Proficient | 36.20% | 35.35% | -0.85% | 24.20% | 26.35% | 2.15% | 50.00% | 0.00% | -50.00% |
|  | Basic | 52.90% | 64.65% | 11.75% | 71.34% | 70.66% | -0.68% | 50.00% | 100.00% | 50.00% |

The data points provided suggest that Cherry Hill Elementary School’s performance has declined from SY2010-2011 to SY2011-2012. However, it is important to note that these data points are skewed by the small number of students who take the test. Cherry Hill did see gains in the number of fourth graders scoring advanced. The network team and executive director expects positive movement for Cherry Hill elementary on Benchmark C to be reported next quarter.

Table 6. Benchmark B Math Results, Turnaround Schools SY2010-2011 and SY2011-2012

Source: City Schools’ DataLink

| Grade | Proficiency Level | District Average for All Schools- Grade Level and Test | Average for Turnaround K-8 Schools--Grade Level and Test | School |
| --- | --- | --- | --- | --- |
|  |  |  |  | Cherry Hill |
|  |  | B 10/26/10 | B 10/17/11 | Delta 2010-2011 | B 10/26/10 | B 10/17/11 | Delta | B 10/26/10 | B 10/17/11 | Delta 2010-2011 |
|  |  |  |  |  |  |  | 2010-2011 |  |  |  |
| 3 | Advanced | 21.70% | 23.11% | 1.41% | 9.10% | 27.71% | 18.61% | 14.71% | 7.41% | -7.30% |
|  | Proficient | 38.40% | 33.48% | -4.92% | 36.40% | 42.50% | 6.10% | 17.65% | 37.04% | 19.39% |
|  | Basic | 39.90% | 43.41% | 3.51% | 54.50% | 29.79% | -24.71% | 67.65% | 55.56% | -12.09% |
| 4 | Advanced | 28.60% | 14.16% | -14.44% | 15.75% | 16.53% | 0.78% | 7.89% | 3.57% | -4.32% |
|  | Proficient | 34.80% | 37.93% | 3.13% | 36.15% | 36.43% | 0.28% | 31.58% | 10.71% | -20.87% |
|  | Basic | 36.70% | 47.91% | 11.21% | 48.05% | 47.05% | -1.00% | 60.53% | 85.71% | 25.18% |
| 5 | Advanced | 17.30% | 10.78% | -6.52% | 5.80% | 10.98% | 5.18% | 8.33% | 6.90% | -1.43% |
|  | Proficient | 25.70% | 26.51% | 0.81% | 22.40% | 15.36% | -7.04% | 29.14% | 31.03% | 1.89% |
|  | Basic | 57.10% | 62.71% | 5.61% | 71.80% | 29.73% | -42.07% | 62.50% | 62.07% | -0.43% |
| 6 | Advanced | 12.80% | 11.50% | -1.30% | 4.70% | 9.76% | 5.06% | 0.00% | 4.55% | 4.55% |
|  | Proficient | 26.40% | 19.73% | -6.67% | 19.20% | 56.69% | 37.49% | 24.00% | 4.55% | -19.45% |
|  | Basic | 60.70% | 68.77% | 8.07% | 76.05% | 34.58% | -41.47% | 76.00% | 90.90% | 14.90% |
| 7 | Advanced | 9.40% | 7.44% | -1.96% | 1.40% | 6.55% | 5.15% | 0.00% | 0.00% | 0.00% |
|  | Proficient | 24.20% | 21.32% | -2.88% | 9.65% | 20.37% | 10.72% | 0.00% | 0.00% | 0.00% |
|  | Basic | 66.40% | 71.24% | 4.84% | 88.95% | 72.01% | -16.94% | 100.00% | 100.00% | 0.00% |
| 8 | Advanced | 11.80% | 7.04% | -4.76% | 0.80% | 3.01% | 2.21% | 0.00% | 0.00% | 0.00% |
|  | Proficient | 27.40% | 23.29% | -4.11% | 18.45% | 19.93% | 1.48% | 23.52% | 0.00% | -23.52% |
|  | Basic | 60.80% | 69.67% | 8.87% | 80.80% | 77.12% | -3.68% | 76.47% | 100.00% | 23.53% |

The data points provided suggest that Cherry Hill Elementary School’s performance has declined from SY2010-2011 to SY2011-2012. However, it is important to note that these data points are skewed by the small number of students who take the test. Cherry Hill Elementary School did experience gains in the number of students moving from basic to proficient in several grades.

The network team and executive director expects positive movement for Cherry Hill elementary on Benchmark C to be reported next quarter.

- Frequency of Teachers and Administrators Accessing Electronic Data Display System

The Electronic Data Display System, or Teacher Student Support System (TSS), is Baltimore City Public Schools’ Blackboard site and is the warehouse for information and collaboration amongst teachers, students, and other staff throughout Baltimore City Schools. All curriculum documents and resources, all links to educational databases and resources for implementation of state curriculum, and portals to other City Schools’ data systems are linked through TSS. Table 6 includes the number of teachers and administrators who have logged into the system thus far for SY2011-12, the average number of logins by administrators and teachers, and the percentage of teachers from each school who have logged in.

Data shows a decrease in log-ins from Quarter 1 to Quarter 2 and has been flagged for follow up.

Table 7. Number and Average of Teacher and Administrator Logins to TSS System for 1st,2nd, 3rd, and 4th Quarters

Source: City Schools’ Teacher Support System

|  | Cherry Hill | Ben Franklin | Frederick Douglass |
| --- | --- | --- | --- |
| Note: Quarter 1 Dates are 8/30/11 – 11/4/11; Quarter 2 Dates are 1/5/11 – 1/20/12 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |
| Number of Logins by Administrator(s) | 36 | 11 |  |  | 175 | 40 |  |  | 65 | 18 |  |  |
| Number of Administrators Logging in | 4 | 3 |  |  | 8 | 6 |  |  | 10 | 6 |  |  |
| Average Number of Logins by Administrator(s) | 9 | 3.7 |  |  | 21.9 | 6.7 |  |  | 6.5 | 3 |  |  |
| Number of Logins by Teachers and other Staff | 907 | 420 |  |  | 275 | 85 |  |  | 898 | 337 |  |  |
| Number of Teachers and other Staff in School Logging in | 24 | 23 |  |  | 22 | 14 |  |  | 54 | 43 |  |  |
| Percent of Teachers in School Logging in* | 44% | 42% |  |  | 52% | 33% |  |  | 48% | 38% |  |  |
| Average Number of Logins by Teachers | 37.8 | 18.3 |  |  | 12.5 | 6.1 |  |  | 16.6 | 7.8 |  |  |

*Derived from the number of teachers and other staff logging in divided by the number of staff at the school with “Teacher” in job title as of 11/24/10. Staff other than those with “Teacher” in the job title may be logging in, so this percentage may represent a higher rate of teacher logins than what is actually occurring.

- Attendance

Source: City Schools’ Student Management System (SMS)

| Year | 2009 | 2010 |  | 2011-12 1st Quarter | 2011-12 2nd Quarter | 2011-12 Targets |
| --- | --- | --- | --- | --- | --- | --- |
| School | % | % |  | % | % | % |
| Cherry Hill | 93.50 | 93.36 |  | 93.09 | 91.02 | 92.4 |
| Ben Franklin | 86.90 | 83.04 |  | 76.25 | 72.99 | 84.6 |
| Frederick Douglass | 74.9 | 75.29 |  | 72.85 | 69.90 | 74.8 |

With assistance from the network teams, Turnaround Schools are putting an increased emphasis on attendance. For example, the Network School Support Liaison has begun to meet weekly with a large attendance team at Frederick Douglass High School. The team has tiered students green, yellow or red based on the students’ attendance team. Individual team members have been assigned to a group of students and are responsible for tracking attendance and initiating follow up course of action. This strategic approach to the problem has not only helped to address the attendance issue at Frederick Douglass, but has also inspired a more deliberate process for addressing other areas of concern such as graduation rates. While the rate for the second quarter is lower than the first, the attendance rate for the month of January had increased significantly from the previous months with this system in place.

- SST Minutes and Documents

Table 8. Students referred to SST By School and Reason in 2011-12 School Year

Source: City Schools’ Student Management System (SMS)

| Year | Reason | Number of Students Q1* | Number of Students Q2** | Number of Students Q3*** | Number of Students Q4**** |
| --- | --- | --- | --- | --- | --- |
| School |  |  |  |  |  |
| Cherry Hill H | Attendance | 0 | 2 |  |  |
|  | Behavior | 0 | 3 |  |  |
|  | Academic | 0 | 1 |  |  |
|  | No Parent Consent | 0 |  |  |  |
| Ben Franklin | Attendance | 6 | 11 |  |  |
|  | Behavior | 3 | 11 |  |  |
|  | Academic | 1 | 13 |  |  |
|  | Health | 1 | 1 |  |  |
| Frederick Douglass | Attendance | 0 | 2 |  |  |
|  | Behavior | 0 |  |  |  |
|  | Academic | 0 |  |  |  |
|  | No Parent Consent | 1 |  |  |  |
| As of 11/7/11; **As of 1/21/12; *** As of 3/30/12; **** As of 6/30/12 |

- Suspensions

Table 9 shows the number of suspensions for each 1003(G) school for the first and second quarters of SY2011-2012 and the number of suspensions for the corresponding quarters of SY2010-11; figure 2 shows the information in a graphical format. The number of suspensions from Quarter 2 has decreased from this same period in SY2010-2011. Suspensions for SIG II schools have decreased from the same quarter in SY2010-2011 as well as from the previous quarter in SY2011-2012.

Table 9. Number of Suspensions by School for School Year 2010-11 as Compared to 1st, 2nd, and 3rd, 4th Quarters of School Year 2011-12

Source: City Schools’ Student Management System (SMS)

| Year | 2010-11 1st Quarter* | 2011-12 1st Quarter* | Change from 2010-2011 and 2011-12 1st Quarter |  | 2010-11 2nd Quarter** | 2011-12 2nd Quarter** | Change from 2010-11and 2011-12 2nd Quarter |  | 2010-11 3rd Quarter | 2011-12 3rd Quarter*** | Change from 2010-11and 2011-12 3rd Quarter |  | 2010-11 4th Quarter**** | 2011-2012 4th Quarter | Change from 2010-11 and 2011-12 4th Quarter**** | Change from 2009-10 and 2010-11 4th Quarter |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| School |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Cherry Hill | 12 | 23 | +11 |  | 27 | 17 | -10 |  |  |  |  |  |  |  |  |  |
| Ben Franklin | 9 | 25 | +16 |  | 17 | 17 | 0 |  |  |  |  |  |  |  |  |  |
| Frederick Douglass | 18 | 31 | +13 |  | 45 | 29 | -16 |  |  |  |  |  |  |  |  |  |
| * as of 11/7/11; **as of 1/21/12; ***as of 3/30/12, ****as of 6/30/12 |

Figure 2. Number of Suspensions by School for School Year 2010-11 as Compared to 1st,2nd, and 3rd, and 4th Quarters of School Year 2011-2012

# Text boxes

*SIG Monitoring Team Membership includes representatives from the following Departments and Offices within Baltimore City Public Schools:

- Chief Academic Office

- Student Support Services

- Office of Teaching and Learning

- Office of Special Education

- School Support Networks

- Office of Federal Programs/Title I

- Chief of Staff Office

- Turnaround Schools

- Office of New Initiatives

- Office of Human Capital

- Office of Assessment and Accountability