Title I School Improvement Grant (SIG II), section 1003(g) MSDE Priority SIG II Monitoring Teams’ Second Onsite Visit Feedback for Baltimore City Public Schools (BCPSS), Benjamin Franklin @ Masonville Cove High School, Frederick Douglass High School, and Cherry Hill Elementary Middle School MSDE Onsite Monitoring Dates: February 2013

Title I School Improvement Grant (SIG II):  The School Improvement Grant (SIG II) Program, authorized under section 1003(g) of Title I of the Elementary and Secondary Act of 1965, provides funding through state educational agencies (SEAs) to local educational agencies (LEAs) with the lowest-achieving schools. These schools have the greatest need for the funds and have demonstrated the strongest commitment to use the funds to raise the achievement of students.  The United States Department of Education (USDE) views the large infusion of Federal funds into the SIG II program through the American Recovery and Reinvestment Act of 2009 (ARRA) as a historic opportunity to address one of the most intractable challenges for America’s education system: turning around or closing down our nation’s persistently lowest-achieving schools.  USDE approved Maryland’s Flexibility Plan in May 2012 which included Maryland’s SIG II schools as Priority Schools.

# Purpose of the Priority SIG II Monitoring Teams’ Second Onsite Visit: As approved by USED, MSDE, through Priority SIG II Monitoring Teams will conduct three onsite monitoring visits annually in each LEA that receives a school improvement grant to ensure the LEA is implementing its intervention model fully and effectively in Maryland’s Tier I and Tier II schools. The purpose of the Priority SIG II Teams second onsite visit is to review documentation that substantiates the LEA’s implementation, both programmatic and fiscal, of its SIG II Grant, as approved by MSDE.  Once all documentation provided by the LEA has been reviewed, Priority SIG II Monitoring Teams will determine a level of implementation for each section/component/strategy/action that consists of being MET, PARTIALLY MET, or NOT MET.  For areas that are MET in this feedback, MSDE will continue to monitor sustainability of the level of implementation.  Based on the Priority SIG II Teams’ Onsite Visit Feedback, MSDE expects the LEA to review and analyze the feedback and make adjustments to its approved SIG II application through the system’s internal controls and submission of programmatic and fiscal amendments to MSDE.

| Table Organization of Priority SIG II Teams’ Second Onsite Visit Feedback |
| --- |
| Table 1 | LEA Commitments and Capacity |
| Table 2 | Levels of Implementation At -a -Glance for Priority SIG II Schools |
| Table 3 | Section 2: Benjamin Franklin @ Masonville Cove High School, Tier II |
| Table 4 | Section 2: Frederick Douglass High School, Tier II |
| Table 5 | Section 2: Cherry Hill Elementary Middle School, Tier I |
| Table 6 | Priority SIG II School Budget for Benjamin Franklin @ Masonville Cove High School |
| Table 7 | Priority SIG II School Budget for Frederick Douglass High School |
| Table 8 | Priority SIG II School Budget for Cherry Hill Elementary/Middle School |
| Table 9 | Section 5: Priority SIG II LEA Budget |
| Table 10 | Section 5: Priority SIG II Consolidated Budget for Schools |

| TABLE 1: LEA Commitments and Capacity by Baltimore City Public School System MSDE SIG II Monitoring Team Members: Gail Clark Dickson Monitoring Date: March 5, 2013 |
| --- |
| Central Support Presented Evidence: SANE documentation of monthly Central Support Team meetings, inclusive of representatives from the Turnaround Office, Networks, Title I, and Chief Academic Officer representative | Level of Implementation: MET |
| How often will the LEA 1003(g) Central Support Team meet? Presented Evidence: The Central Support Team meets monthly; Occasionally the team meets individually with network reps SANE documentation of meetings from 9/2012 – 2/2013 | Level of Implementation: MET |
| How often will they report on their work and the work on Tier I, II and III schools to the Superintendent? Presented Evidence: Network Executive Directors and Facilitators have ongoing quarterly check-ins with the Superintendent A sample memo was presented as evidence which was addressed to Dr. Alonso reflecting SIG/Turnaround Schools’ Quarterly report dated, 10/9/2012 | Level of Implementation: MET |
| How often will they report on their work and the work on Tier I, II and III schools to the Board of Education? Presented Evidence: Quarterly reports are provided to the Board of Commissioners Evidence of a quarterly update to the Teaching and Learning Committee/Office of Chief Academic Officer about the Turnaround Initiative dated 10/9/2012 | Level of Implementation: MET |
| Has the LEA 1003(g) central support team met prior to the submission of the grant application to review the individual school descriptions and to discuss how it will coordinate and manage the support, monitoring and assessment outlined in those plans? ______ YES ______NO Presented Evidence: | Level of Implementation: N/A |
| What role has or will the LEA 1003(g) central support team play in the creation of annual goals for student achievement and annual review/assessment of progress based on these goals described in sections 2 and 3 of this proposal? Presented Evidence: Evidence of School Performance Plan with identified Annual Measurable Objectives (AMOs) for Priority SIG II Schools Additional documentation on goal planning: SAN documentation of Turnaround Office & Network Support Official Budget Meeting (2/27/13) at Ben Franklin; SANE documentation of the Aspiring Principals Institute with Frederick Douglass High School (FDHS) & Cherry Hill Elementary/ Middle School representatives in attendance SAN documentation for staff development on Teach like a Champion on 12/12/12 with FDHS & Benjamin Franklin High School (BFHS) representatives in attendance Sign in sheets of ongoing Network support for Priority SIG II with evidence of Learning Walks and Instructional Framework Monitoring | Level of Implementation: MET |
| What steps will the LEA take to ensure that the school improvement funds are utilized (1) in a timely way and (2) effectively and efficiently to support the required components of the selected intervention? Specifically, what assurances will the LEA make that schools and LEA support teams have access to these funds, even during annual rollover processes? How will the LEA support principals’ timely and effective use of these funds? Presented Evidence: Monthly reports regarding spend downs in collaboration with the Business Manager Evidence of ongoing Budget/Fiscal monitoring with Priority SIG II Schools Evidence of a grants meeting with Turnaround Office & Grant Administration Staff for SIG schools on 6/4/2012 Ongoing Grant Managers Team Meeting documentation with yearly calendar; Sample documentation include the 9/19/2012 meeting Ongoing monthly operators/principal meetings with the Turnaround Office reflected in SAN documentations from 7/2012 – 2/2013 | Level of Implementation: MET |
| Within this proposal, the LEA identified actions taken or in the planning to support individual Tier I and Tier II schools’ implementation of the selected interventions. Looking across the commitments made for the schools, and considering as well the strategies selected by the LEA for identified Tier III schools, what additional actions will the LEA take to ensure that the selected interventions are implemented as designed and to make the other changes such as: (1) realignment of other resources; (2) removal of expectations that might run counter to the approach outlined in the selected intervention; (3) timely modification of practices and policies (those anticipated ahead of time and those that will emerge during implementation); and (4) engaging in reflective and sustained, collaborative conversation and planning to ensure that improvement efforts can be sustained once this funding ends? Presented Evidence: Evidence of Ongoing Support: Realignment of resources (an additional human capital person was hired); Continued work with the Breakthrough center; Support services from MSDE; Mentoring opportunities; Monthly principal/operators’ meetings; Aspiring Leadership Program; Monthly Teach Like Champions staff development; Attendance at the Harvard Leadership Institute; Targeted PD from learning walks and feedback to teachers with follow-up drive the instructional framework; Collaboration in planning with teachers; SIG walks by Networks; Staff data talks; and Continued shift in thinking about Special Education, more collaboration about good instruction | Level of Implementation: MET |
| What are the major challenges to full and effective implementation of all components of the SIG grant that the LEA 1003 (g) central support team has identified and how will the team address these challenges in the early phases of the work? Presented Evidence: Challenges: Hiring the right staff for Turnaround Schools At the forefront of the CAO; Need to identify needs early to address staffing issues Improving accountability measures for external providers Modifying policies and procedures to address accountability and renewal; aligning systems tools with State’s tools for monitoring Exploring Network structuring Internal discussion regarding identifying Priority SIG schools to a specific Network Networks are working as a team in strategizing with schools teams Continued conversations about the amendment process | Level of Implementation: MET |

| TABLE 2: Levels of Implementation At-a-Glance on the Requirements for the Turnaround Intervention Model in BCPSS’ Tier II Priority SIG II Schools | Benjamin Franklin @ Masonville Cove High School Requirement Level of Implementation M-Met PM-Partially Met NM-Not Met 2012 | Benjamin Franklin @ Masonville Cove High School Requirement Level of Implementation M-Met PM-Partially Met NM-Not Met 2013 | Frederick Douglass High School Requirement Level of Implementation M-Met PM-Partially Met NM-Not Met 2012 | Frederick Douglass High School Requirement Level of Implementation M-Met PM-Partially Met NM-Not Met 2013 |
| --- | --- | --- | --- | --- |
| Replace the principal and grant the principal sufficient operational flexibility | PM | M | M | M |
| Screen all existing staff and rehire no more than 50 percent; and select new staff | PM | M | PM | PM |
| Implement such strategies as financial incentives, increased opportunities for promotion and career growth | M | M | M | PM |
| Provide staff with ongoing, high-quality, job-embedded professional development that is aligned with the school’s comprehensive instructional program | M | PM | PM | M |
| Adopt a new governance structure | M | M | M | M |
| Use data to identify and implement an instructional program that is research-based and “vertically aligned” | M | PM | M | PM |
| Promote the continuous use of student data (such as from formative, interim, and summative assessments) to inform and differentiate instruction | PM | M | PM | M |
| Establish schedules and implement strategies that provide increased learning time | PM | M | PM | M |
| Provide appropriate social-emotional and community-oriented services and supports for students | PM | M | PM | M |
| Learning to Work focus with implementation of a 4+1 schedule | M | M | N/A | N/A |
| Environmental Sciences CTE programming | M | M | N/A | N/A |
| Recruit, screen, and select external providers to ensure quality | M | M | N/A | N/A |

| COMP. # | TABLE 2: Levels of Implementation At-a-Glance on the Requirements for the Restart Intervention Model in BCPSS’ Priority SIG II Schools | Cherry Hill Elementary/Middle School Requirement Level of Implementation M-Met PM-Partially Met NM-Not Met 2012 | Cherry Hill Elementary/Middle School Requirement Level of Implementation M-Met PM-Partially Met NM-Not Met 2013 |
| --- | --- | --- | --- |
| 1 | Student Profile | PM | M |
| 2 | Staff Profile | PM | M |
| 3 | Student Achievement | M | M |
| 4 | Rigorous Curriculum | NM | PM |
| 5 | Instructional Program | PM | M |
| 6 | Assessments | PM | M |
| 7 | School Climate & Culture | PM | M |
| 8 | Student, Family and Community Support | PM | PM |
| 9 | Professional Development | PM | M |
| 10 | Organizational Structure and Resources | M | M |
| 11 | Comprehensive and Effective Planning | PM | M |
| 12 | Effective Leadership | M | M |

| TABLE 3: Benjamin Franklin @ Masonville Cove High School, Tier II LEA: Baltimore City Public Schools MSDE Priority SIG II Monitoring Team: John Grymes, Renee Williams and Glen Lee Monitoring Dates: February 25 – 26, 2013 |
| --- |
| Overall Level of Implementation: Partially Met |
| Comp # | Description | Requirement Level of Implementation | Insufficient Evidence by Component and Action Item |
| 1 | Replace the principal and grant the principal sufficient operational flexibility (including in staffing, calendars/time, and budgeting) to implement fully a comprehensive approach in order to substantially improve student achievement outcomes and increase high school graduation rates | Met |  |
| 2 | Use locally adopted competencies to measure the effectiveness of staff who can work within the turnaround environment to meet the needs of students (A) Screen all existing staff and rehire no more than 50 percent; and (B) Select new staff | Met |  |
| 3 | Implement such strategies as financial incentives, increased opportunities for promotion and career growth, and more flexible work conditions that are designed to recruit, place, and retain staff with the skills necessary to meet the needs of the students in the turnaround school | Met |  |
| 4 | Provide staff with ongoing, high-quality, job-embedded professional development that is aligned with the school’s comprehensive instructional program and designed with school staff to ensure that they are equipped to facilitate effective teaching and learning and have the capacity to successfully implement school reform strategies | Partially Met | 4c. No proof that the Towson University Course was offered. (Note: Principal reported funds for this course were eliminated when year-two SIG funds were reduced. No evidence of a budget amendment). |
| 5 | Adopt a new governance structure, which may include, but is not limited to, requiring the school to report to a new “turnaround office” in the LEA or SEA, hire a “turnaround leader” who reports directly to the Superintendent or Chief Academic Officer, or enter into a multi-year contract with the LEA or SEA to obtain added flexibility in exchange for greater accountability | Met |  |
| 6 | Use data to identify and implement an instructional program that is research-based and “vertically aligned” from one grade to the next as well as aligned with State academic standards | Partially Met | 6d. No proof that the Towson University Course was offered. (Note: Principal reported funds for this course were eliminated when year-two SIG funds were reduced. No evidence of a budget amendment). |
| 7 | Promote the continuous use of student data (such as from formative, interim, and summative assessments) to inform and differentiate instruction in order to meet the academic needs of individual students | Met |  |
| 8 | Establish schedules and implement strategies that provide increased learning time | Met |  |
| 9 | Provide appropriate social-emotional and community-oriented services and supports for students | Met |  |
| 10 | Learning to Work focus with implementation of a 4+1 schedule | Met |  |
| 11 | Environmental Sciences CTE programming | Met |  |
| 12 | Recruit, screen, and select external providers to ensure quality | Met |  |

| TABLE 4: Frederick Douglass High School, Tier II LEA: Baltimore City Public Schools MSDE Priority SIG II Monitoring Team: John Grymes, Mary Cross and Kristi Peters Monitoring Dates: February 7 – 8, 2013 |
| --- |
| Overall Level of Implementation: Partially Met |
| Comp # | Description | Requirement Level of Implementation | Insufficient Evidence by Component and Action Item |
| 1 | Replace the principal and grant the principal sufficient operational flexibility (including in staffing, calendars/time, and budgeting) to implement fully a comprehensive approach in order to substantially improve student achievement outcomes and increase high school graduation rates | Met |  |
| 2 | Use locally adopted competencies to measure the effectiveness of staff who can work within the turnaround environment to meet the needs of students (A) Screen all existing staff and rehire no more than 50 percent; and (B) Select new staff | Partially Met | 2a. The school-based multi-tier recruitment selection model for certified teachers applying to Baltimore City Public Schools was not provided. |
| 3 | Implement such strategies as financial incentives, increased opportunities for promotion and career growth, and more flexible work conditions that are designed to recruit, place, and retain staff with the skills necessary to meet the needs of the students in the turnaround school | Partially Met | 3a. No documentation to verify staff payments for working extended hours. 3b. The draft MOU in the file has not been executed. The MOU has been signed by the Baltimore Teachers Union (BTU). The Turnaround Office reported the MOU is awaiting the Superintendent’s signature. |
| 4 | Provide staff with ongoing, high-quality, job-embedded professional development that is aligned with the school’s comprehensive instructional program and designed with school staff to ensure that they are equipped to facilitate effective teaching and learning and have the capacity to successfully implement school reform strategies | Met |  |
| 5 | Adopt a new governance structure, which may include, but is not limited to, requiring the school to report to a new “turnaround office” in the LEA or SEA, hire a “turnaround leader” who reports directly to the Superintendent or Chief Academic Officer, or enter into a multi-year contract with the LEA or SEA to obtain added flexibility in exchange for greater accountability | Met |  |
| 6 | Use data to identify and implement an instructional program that is research-based and “vertically aligned” from one grade to the next as well as aligned with State academic standards | Partially Met | 6h. No evidence that the law program is aligned with the BCCC law program. This is a new partnership with BCCC. FDHS is currently negotiating an articulation agreement with the community college. |
| 7 | Promote the continuous use of student data (such as from formative, interim, and summative assessments) to inform and differentiate instruction in order to meet the academic needs of individual students | Met |  |
| 8 | Establish schedules and implement strategies that provide increased learning time | Met |  |
| 9 | Provide appropriate social-emotional and community-oriented services and supports for students | Met |  |

| TABLE 5: Cherry Hill Elementary Middle School, Tier I LEA: Baltimore City Public Schools MSDE SIG II Monitoring Team: Lynn Muller, Michelle Goady and Sally Dorman Monitoring Dates: February 13 - 14, 2013 |
| --- |
| Overall Level of Implementation: Partially Met |
| Comp # | Description | Requirement Level of Implementation | Insufficient Evidence by Component and Action Item |
| 1 | Student Profile | Met |  |
| 2 | Staff Profile | Met |  |
| 3 | Student Achievement | Met |  |
| 4 | Rigorous Curriculum | Partially Met | 4a.Elements of planning such as lesson plans and unit plans are present; however, there is no documentation of the back mapping based on student data in the Understanding By Design framework. |
| 5 | Instructional Program | Met |  |
| 6 | Assessments | Met |  |
| 7 | School Climate & Culture | Met |  |
| 8 | Student, Family and Community Support | Partially Met | 8d.Insufficient evidence of marketing door to door and in the community (businesses, day care, boys clubs, etc). No Spanish translations. |
| 9 | Professional Development | Met |  |
| 10 | Organizational Structure and Resources | Met |  |
| 11 | Comprehensive and Effective Planning | Met |  |
| 12 | Effective Leadership | Met |  |

| TABLE 6 Priority SIG II Year 2 School Budget for Benjamin Franklin High School , Tier II |
| --- |
| MSDE Fiscal Reviewer: Geri Taylor Lawrence Monitoring Date: March 5, 2013 |
| Total SIG II Year 2 Allocation: $ 1,081,999 | School Budget Spent: $ 334,821 | Percent of School Budget Spent: 31% | Spend Down Data as of: February 28, 2013 |
| Salaries & Wages | Contractual Services | Supplies & Materials | Other |
| Budgeted: $ 569,554 | Budgeted: $ 215,168 | Budgeted: $ 31,430 | PD/Conference Budgeted: $ 23,240 |
| Encumbered: $ 0 | Encumbered: $ 113,799 | Encumbered: $ 776.00 | PD/Conference Encumbered: $0 |
| Spent (amount): $ 234,273 Spent (%): 41 % | Spent (amount): $ 0 Spent (%): 0 % | Spent (amount): $ 8,202 Spent (%): 26 % | PD /Conference Spent (amount): $ 0 ( 0%) |
| How much of the school budget, based on the LEA’s approved application, has been expended to date (amount and %)? BCPSS provided documentation that showed Benjamin Franklin has spent $ 334,821. This amount is 31 % of their approved SIG II year 2 budget. An additional amount of $ 114,575 has been encumbered. Expended amounts for fixed charges are included in the total spent. |
| Is school spending consistent with budget timeline? If not, what steps are being taken to expend the funds as planned? BCPSS explained that spending is not consistent with the budget timeline. Turnaround Office staff will continue to work with the school to expend funds. |
| What action steps or planned activities have not taken place that would impact the budget? BCPSS indicated all planned activities have taken place but the school is a little slow ordering materials. There is a slight delay with the submission of the invoices by the vendor. |
| Has a budget amendment been submitted? If yes, what budget changes were requested for this school? BCPSS indicated that no budget amendment is expected to be submitted. |
| How often are school expenditures monitored by the LEA? Who monitors? BCPSS provided documentation that showed that monitoring was conducted on Nov. 9, Dec. 6, 2012; Jan. 9, Jan. 31, and Feb. 28, 2013. BCPSS explained that expenditures are monitored by the principal and school based business manager on a weekly basis. The Turnaround Business Manager meets with the principal and school based business manager to review spending, encumbrances and barriers to spending. |

| TABLE 7 Priority SIG II Year 2 School Budget Frederick Douglass High School , Tier II |
| --- |
| MSDE Fiscal Reviewer: Geri Taylor Lawrence Monitoring Date: March 5, 2013 |
| Total SIG II Year 2 Allocation: $ 1,508,281 | School Budget Spent: $ 842,484 | Percent of School Budget Spent: 56 % | Spend Down Data as of: February 28, 2013 |
| Salaries & Wages | Contractual Services | Supplies & Materials | Other |
| Budgeted: $811,330 | Budgeted: $ 405,600 | Budgeted: $62,596 | Budgeted: N/A |
| Encumbered: $ 0 | Encumbered: $ 123,233 | Encumbered: $ 22,018 | Encumbered: N/A |
| Spent (amount): $ 473,797 Spent (%): 58 % | Spent (amount): $ 231,304 Spent (%): 57 % | Spent (amount): $ 35,960 Spent (%): 58 % | Spent: N/A |
| How much of the school budget, based on the LEA’s approved application, has been expended to date (amount and %)? BCPSS provided documentation that showed Frederick Douglass has spent $ 842,484. This amount is 56 % of their approved SIG II year 2 budget. An additional amount of $ 145,753 has been encumbered. Expended amounts for fixed charges are included in the total spent. |
| Is school spending consistent with budget timeline? If not, what steps are being taken to expend the funds as planned? BCPSS indicated that Frederick Douglass is consistent with the budget timeline. |
| What action steps or planned activities have not taken place that would impact the budget? BCPSS indicated that stipends for extended day will be transferred from general funds to the grant at the end of the school year. Additionally, the principal bonus will be posted to the grant at the end of the school year if the school targets are met. |
| Has a budget amendment been submitted? If yes, what budget changes were requested for this school? BCPSS indicated that no budget amendment is expected to be submitted. |
| How often are school expenditures monitored by the LEA? Who monitors? BCPSS provided documentation that showed that monitoring was conducted on Nov. 15, Nov. 27, Dec. 6, 2012; Feb. 7, and Feb. 25, 2013. BCPSS explained that the Expenditures are monitored by the principal and school based business manager on a weekly basis. The Turnaround Business Manager meets with school based business manager monthly to review spending, encumbrances, and barriers to spending. |

| TABLE 8 Priority SIG II Year 2 School Budget for Cherry Hill Elem/Middle School, Tier I |
| --- |
| MSDE Fiscal Reviewer: Geri Taylor Lawrence Monitoring Date: March 5, 2013 |
| Total SIGII Year 2 Allocation: $ 1,128,425 | School Budget Spent: $ 184,799 | Percent of School Budget Spent: 16 % | Spend Down Data as of: February 28, 2013 |
| Salaries & Wages | Contractual Services | Supplies & Materials | Other |
| Budgeted: $ 486,435 | Budgeted: $ 399,823 | Budgeted: $ 136,007 | Budgeted : N/A |
| Encumbered: $ 0 | Encumbered: $ 366,336 | Encumbered: $ 4,145 | Encumbered: N/A |
| Spent (amount): $ 115,042 Spent (%): 24 % | Spent (amount): $ 26,495 Spent (%): 7 % | Spent (amount): $ 8,487 Spent (%): 6% | Spent (amount): N/A Spent (%): N/A |
| How much of the school budget, based on the LEA’s approved application, has been expended to date (amount and %)? BCPSS provided documentation that showed Cherry Hill has spent $ 184,799. This amount is 16 % of their approved SIG II year 2 budget. An additional amount of $ 370,481 has been encumbered. Expended amounts for fixed charges are included in the total spent. |
| Is school spending consistent with budget timeline? If not, what steps are being taken to expend the funds as planned? BCPSS explained that spending for Cherry Hill is not consistent with budget timeline. The school has been spending funds from their year 1 allocation. The Turnaround Office staff will continue to work with the schools to expend funds. |
| What action steps or planned activities have not taken place that would impact the budget? BCPSS indicated that stipends for extended day will be transferred from general funds to the grant at the end of the school year. Additionally, the principal bonus will be posted to the grant at the end of the school year if the school targets are met. |
| Has a budget amendment been submitted? If yes, what budget changes were requested for this school? BCPSS indicated that no budget amendment is expected to be submitted. |
| How often are school expenditures monitored by the LEA? Who monitors? BCPSS provided documentation that showed monitoring was conducted on Nov. 9, 2012, Jan. 4, Jan. 30, Feb. 7, and Feb. 26, 2013. BCPSS explained that expenditures are monitored by the principal, operator and business manager on a monthly basis. The Turnaround Business Manager meets with the Operator and business manager monthly to review spending, encumbrances, and barriers to spending. |

| TABLE 9 Section 5: SIG II Year 2 LEA Budget LEA: Baltimore City Public Schools |
| --- |
| MSDE Fiscal Reviewer: Geri Taylor Lawrence Monitoring Date: March 5, 2013 |
| Total SIG II Year 2 Allocation: $332,402 | LEA Budget Spent: $ 1,704 | Percent of LEA Budget Spent: 1% | Spend Down Data as of: February 28, 2013 |
| Salaries & Wages | Contractual Services | Supplies & Materials | Other |
| Budgeted: $ 213,240 | Budgeted: $ 50,000 | Budgeted: $ 17,000 | Budgeted: Travel: $5,017 Technology: $2,493 |
| Encumbered: $ 0 | Encumbered: $ 0 | Encumbered: $ 1,584 | Encumbered: Travel: $ 0 Technology: $ 1,075 |
| Spent (amount): $ 0 Spent (%): 0 % | Spent (amount): $ 0 Spent (%): 0 % | Spent (amount): $ 1,704 Spent (%): 10 % | Spent Travel (amount): $ 0 (0 %) Spent Technology (amount) $ (0 %) |
| How much of the LEA SIG 1003(g) Title I Part A, budget has been expended to date (amount and %)? BCPSS provided documentation that showed the LEA has spent $ 1,704. This amount is 1% of their approved SIG II year 2 budget. An additional amount of $ 2,659 has been encumbered. Expended amounts for fixed charges are included in the total spent. |
| Is the LEA spending consistent with budget timeline? If not, what steps are being taken to expend the funds as planned? BCPSS indicated that the LEA spending is not consistent with budget timeline. BCPSS explained that there is an internal error (salary charges were posted to an invalid account). Staff from Grants Administration, Human Capital and the Turnaround Office will meet to reconcile and correct the error; this correction will put LEA spending on target. |
| What action steps or planned activities have not taken place that would impact the LEA budget? BCPSS explained the contract amount of $50, 000 for New Leaders New Schools will be moved to salaries and wages. |
| Has a budget amendment been submitted? If yes, what budget changes were requested for the LEA? BCPSS indicated that no budget amendment is expected to be submitted. |
| How often are LEA expenditures monitored? Who monitors? BCPSS indicated that district that district financial analyst met with Turnaround Office staff on Dec. 4, Dec. 17, 2012; Jan. 6, Jan. 8, February 5, 2013 to plan, discuss, and revise the district SIG I budget. |

| TABLE 10 Section 5: SIG II Year 2 Consolidated Budget LEA: Baltimore City Public Schools |
| --- |
| MSDE Fiscal Reviewer: Geri Taylor Lawrence Monitoring Date: March 5, 2013 |
| SIG II 1003(g) Title I, Part A |
| Total Allocation Amount Spent Percent Spent Amount Encumbered Spend Down Data as of : | $ 4,051,108 |
|  | $1,363,808 |
|  | 34% |
|  | $633,467 |
|  | February 28, 2013 |