# Title I School Improvement Grant (SIG), section 1003(g)

# SIG Monitoring Team’s First Onsite Visit Feedback

School: Booker T. Washington Middle School LEA: Baltimore City Public School System (BCPSS) Principal: Dr. Euna McGruder LEA Turnaround Director: Beth Nolan LEA Central Support Team Lead: Tasha Franklin Johnson SIG Team’s School Visit: September 24, 2010

Title I School Improvement Grant (SIG):  The School Improvement Grant (SIG) Program, authorized under section 1003(g) of Title I of the Elementary and Secondary Act of 1965, provides funding through State educational agencies (SEAs) to local educational agencies (LEAs) with the lowest-achieving schools that have the greatest need for the funds and demonstrate the strongest commitment to use the funds to raise significantly the achievement of students.  The United States Department of Education (USED) views the large infusion of Federal funds into the SIG program through the American Recovery and Reinvestment Act of 2009 (ARRA) as a historic opportunity to address one of the most intractable challenges for America’s education system: turning around or closing down our Nation’s persistently lowest-achieving schools.  Maryland’s approved application reflects Secretary Duncan’s determination to ensure that SIG funds are used to implement one of four rigorous school intervention models—turnaround, restart, transformation, and school closure.  Through a rigorous technical review process, MSDE approved Prince George’s County Public Schools’ application (PGCPS) on July 1, 2010 and Baltimore City Public School System’s application (BCPSS) on August 27, 2010.  Both school systems were granted approval to charge to their grants beginning July 1, 2010.

Maryland State Department of Education’s (MSDE) Monitoring of LEA Approved SIG Application:  As approved by USED, MSDE will monitor each LEA that receives a school improvement grant to ensure that it is implementing its intervention model fully and effectively in Maryland’s Tier I and Tier II schools.  Both PGCPS and BCPSS must submit to MSDE a quarterly summary report of the LEA monitoring/oversight that has been completed and the progress the Tier I or Tier II schools have made towards achieving their goals. In addition, MSDE will perform onsite visits to these same schools.  The primary function of the onsite visits is to review and analyze all facets of a school’s implementation of the identified approved intervention model and collaborate with leadership, staff, and other stakeholders pertinent to goal attainment.  MSDE’s School Improvement Grant Monitoring Teams (SIG Teams) will conduct three onsite monitoring visits annually (Introductory/Start Up One Day Visit; Interim Midyear Two Day Visit; and End of Year One Day Visit) with the school leadership team and district level team composed of staff responsible for the technical assistance, administrative support, and monitoring.

# SIG Monitoring Team’s First Onsite Visit Purpose:

The Introductory Start-up Onsite Visit is the first opportunity for the SIG Monitoring Team to discuss BCPSS’ approved SIG Plan for Booker T. Washington Middle School with school and district staff to ensure that all school system stakeholders are familiar with and understand the approved SIG Plan.  In addition, BCPSS was required to present an update on the system’s progress in the implementation of its approved plan for Booker T. Washington Middle School.   During this update, LEA and School Staff shared what has been implemented; what has been partially implemented; and what has not been implemented at this time. BCPSS also discussed potential changes it needs to make in the school’s approved plan for the first year of SIG.   BCPSS staff was asked to provide a guided tour of the building for the SIG Team.

# BCPSS SIG Background:

- In Maryland’s approved SIG application, the Maryland State Department of Education (MSDE) identified five Tier I schools and seven Tier II schools in the BCPSS.

- During the 2008-2009 school year, BCPSS launched Expanding Great Options Initiative to create more and better school options for all students over time.  The City Schools began to link school performance and parent choice to facility improvement and new school creation strategies.  With federal stimulus dollars under the American Recovery and Reinvestment Act of 2009 (ARRA) combined with Title I School Improvement Grant, under section 1003(g), BCPSS was presented new opportunities for transforming its persistently lowest achieving schools and advancing its Expanding Great Options goals more broadly and strategically.

- On August 27, 2010, MSDE approved BCPSS’ SIG Application.  At that time, MSDE gave approval for BCPSS to begin charging to its SIG on July 1, 2010.

- In its approved SIG application, BCPSS made the decision to serve all five of its Tier I schools and only two out of the seven Tier II schools.

- BCPSS made the decision not to serve Cherry Hill Elementary/Middle School, Francis M. Wood Alternative High School, Frederick Douglass High School, Institute of Business and Entrepreneurship High School, and Masonville Cove Academy.   In its approved SIG application, BCPSS provided the reasons it lacked the capacity to serve these schools.

- BCPSS made the decision to implement a specific intervention model for the following Tier I and Tier II schools:

| School | Tier I or Tier II | Intervention Model |
| --- | --- | --- |
| Calverton Elementary/Middle School | Tier I | Restart Intervention Model |
| Commodore John Rodgers Elementary/Middle School | Tier II | Restart Intervention Model |
| Baltimore IT Academy (formerly Chinquapin Middle School) | Tier I | Restart Intervention Model |
| Garrison Middle School | Tier I | Restart Intervention Model |
| William C. March Middle School | Tier I | Restart Intervention Model |
| Augusta Fells Savage Institute of Visual Arts HS | Tier II | Turnaround Intervention Model |
| Booker T. Washington Middle School | Tier I | Turnaround Intervention Model |

- BCPSS will receive $25,183,804.00 over a three year grant period for its seven Tier I and Tier II SIG schools.

- Based on its approved SIG Plan, BCPSS, in its LEA SIG budget, will receive $1,999,343.00, in the first year; $2,049,995.00, in the second year; and $1,838,605.00, in the third year.  The total SIG amount for the LEA over the three years is $5,887,943.00.

- Based on its approved SIG Plan, Booker T. Washington Middle School will receive $928,355.00, in the first year; $1,002,144.00, in the second year; and $1,002,144.00, in the third year.   The 3 year SIG grant totals $2,932,644 for Booker T. Washington Middle School.

- Based upon evidence reviewed from the SIG Monitoring Team’s three onsite visits, MSDE will determine the LEA’s capacity to ensure goal attainment, and subsequently, renewal of the School Improvement Grant funds each of the three years for the school district and school.

- In its approved SIG application, BCPSS identified 16 individuals as members of its 1003(g) Central Support Team (CST).  BCPSS did not identify a lead for the CST.  In terms of reporting and communications, MSDE identified Tasha Franklin Johnson, Office of Federal Programs/Title I Director, as the CST lead.

- In its documentation provided at the SIG Teams’ First Onsite Visits, BCPSS provided a list of 21 individuals as active members of its Turnaround Central Office Support Team with the following goal:

All school based issues are resolved within or a plan is developed to get to resolution within 48 hours.

- In addition, BCPSS’ School Support Networks provide a streamlined model for problem-solving, communication and central office collaboration and support to schools.

- Beth Nolan, SIG Turnaround Director, was appointed on September 14, 2010 and began working on September 25, 2010.

- Dr. Euna McGruder, Principal at Booker T. Washington Middle School, was appointed on June 22, 2010 and began working on July 3, 2010.

# The following individuals participated in the SIG Team’s Visit on September 23, 2010:

- SIG MSDE Monitoring Team Leader:         Valerie Ashton-Thomas

- SIG MSDE Monitoring Team Members:     Walt Sallee,  Bob Glascock,  Annette Harris, Gary Hedges

- SIG  MSDE Monitoring Leads:                    Tina McKnight

- BCPSS Turnaround Director:	      	   Beth Nolan

- Principal:      	           	  		   Euna McGruder

- BCPSS Attendees:                                     Felipe O. Jackson, Roger Shaw, Koren Stukes, Paul Grant, Scott Johnson,

Kimberly Worthington, Roann Tsakalas, Landa McLaurin, Kim Huffman,

Amy Rosenkrans, Kim Ferguson, Dawn Dowling, Debbie Thomas

SIG Monitoring Team’s First Onsite Visit Feedback for Booker T. Washington Middle School:

- TABLE  I:   Based on its first monitoring onsite visit, the SIG Monitoring Team determined overarching issues on BCPSS’ Approved SIG Plan.   BCPSS must submit required responses to MSDE by the identified timeline.

Special Note: All required responses submitted to MSDE on or before December 15, 2010 must be submitted at the same time.

- TABLE  2:   MSDE required each SIG Monitoring Team to ask the LEA and school specific questions related to its SIG approved plan. This table reflects what BCPSS shared verbally with the SIG Monitoring Team.  The SIG Monitoring Team compiled information that was shared by the LEA and school in this table.  This information will be reviewed and used by the SIG Monitoring Team during its second onsite visit.

- TABLE  3:   MSDE developed a SIG Monitoring Tool based on the LEA’s approved plan for a specific school.  This tool was used by the SIG Monitoring Team to determine the school system’s implementation of the approved plan.  The SIG Monitoring Team compiled information that was shared by the LEA and school in this table.  This information will be reviewed and used by the SIG Monitoring Team during its second onsite visit.

# TABLE  1

| SIG Monitoring Team First Onsite Visit’s Overarching Issues on BCPSS’ Approved SIG Plan for Booker T. Washington Middle School |
| --- |
| Issues | Required Response from BCPSS | Timeline |
| Staffing In its approved SIG plan, BCPSS states, The Office of Human Capital (OHC) and the Office of the Chief Academic Officer will assist the newly selected principal with development of staffing model and the budgeting process as needed and in accordance with established guidelines. There are some concerns about the staffing at Booker T. Washington. There are only three returning classroom teachers: 6th grade (1 out of 6 teachers); 7th grade (1 out of 4 teachers); and 8th grade (1 out of 4 teachers) grades. Six core teachers are Teach for America teachers. There are three long term substitute teachers, with two long term substitutes in 8th grade. That is 50% of the 8th grade teachers. The SIG plan includes hiring an additional administrator or teacher leader. There have been some barriers in filling this essential position. The principal would like to add a part-time business manager to manage the SIG funds. | Provide the written process to ensure there is a staffing priority for Booker T. Washington. In the process, address the needs relative to long term substitute teachers, Teach for America teachers, and first year teachers. Provide documentation for the plan in filling the additional administrator or teacher leader position at Booker T. Washington. | On or before December 15, 2010 |
| Programmatic & Fiscal Monitoring BCPSS’ SIG application was approved August 27, 2010, and MSDE gave approval for BCPSS to begin charging to this grant as of July 1, 2010. The SIG Team understands there are some activities and strategies, for many reasons, that may or may not be implemented as written in the approved grant. The SIG Monitoring Team recommends that BCPSS review the budgets for both the LEA and Booker T. Washington. It is important that there is not a large carryover for the first year. BCPSS needs to submit programmatic and fiscal amendments to MSDE as soon as possible. For example, the school reported that there are only 60 minutes of extended learning time four days a week planned. However, the grant reflects 90 minutes. Because of this change in the approved SIG grant, BCPSS must submit a programmatic amendment to MSDE. | Submit grant budget/program amendments for the extended day changes and the unfilled (to date) administrative position. Special Notes: BCPSS must receive prior written approval from the MSDE Program Monitor before implementing any programmatic changes. BCPSS must receive prior written approval from the MSDE Program Monitor for any budgetary realignment of $1,000 or 15% of total object, program or category of expenditure (whichever is greater). Rationale for these budgetary changes must be clear. | On or before December 15, 2010 |

Table 2

| Overarching Questions for the District Central Support Team and the School Staff | SIG Monitoring Team Consensus Feedback on Overarching Questions from the 1st Onsite Visit at Booker T. Washington Middle School |
| --- | --- |
| How have the LEA and the school ensured that all school stakeholders have been informed about the SIG approved plan? What documentation is available for the SIG monitoring team to review that shows evidence of these activities? What future activities are planned to inform all stakeholders as the plan is being implemented? | There were Board presentations to the public on the intervention model selection for the school. Multiple presentations were made to all stakeholders. Documentation of the meetings was provided. The Back to School Night was scheduled for Sept. 28 and the SIG intervention model for Booker T. Washington was planned as an agenda item. Two other community events have been held. The principal conducts community visits. Fine arts showcase events will occur in fall and spring. |
| 2. Describe the plans for the LEA to provide a rapid response to address immediate needs of the school. | Evidence is provided in document binder provided to SIG monitoring team. Includes rapid response plan, central office Turnaround Project Management Team, and School Support Network. Baltimore City Schools Rapid Response Team has a written process for responding to SIG school needs immediately. The goal of the team is that all school based issues are resolved or a plan is developed to get to resolution within 48 hours. This process is in its initial stages of implementation. School staffing is an issue that should be addressed by the rapid response team. Currently, there are 5 long-term substitutes, and a vacant assistant principal position. School Support Network provided strong support in planning for the opening of school. The mission of the School Support Network it to provide and coordinate timely and effective support services in partnership with city schools. |
| 3. Describe some visible improvements (quick wins) early in the school turnaround process. | The BCPSS made some capital improvements at the school. The school’s main lobby was renovated over the summer. The new lobby configuration allows for each grade level to take a different route to their classroom once they enter the building, minimizing previous traffic flow problems. The building was clean with had improved lighting, and the environment was conducive to learning. The school leadership team provides quick response in addressing staff needs. There is deliberate use of scheduling, space, and explicit structures to minimize conflict and maximize efficiency during the school day. There is some evidence of alignment of instruction with State Curriculum. |
| 4. Describe any changes as of today that address culture and climate issues that impact teaching and learning. | Classroom environments were conducive to teaching and learning (e.g. word walls, expectations, student work, objectives, schedules, use of audio/visual aids, etc.). There was a high level of student engagement of students in the classrooms. |
| 5. What are the LEA’s and school’s plans to ensure that there will be a consistent focus on improving instruction? | There is a focus on addressing “deltas” from professional development sessions and the use of real-time data. Professional development is job-embedded. Staff expectations are high. Curriculum workshops are held the first Saturday of every month which follow the scope and sequence. Follow-up sessions are held on the following Wednesday. These workshops are conducted by the Academic Deans and school administration. |
| 6. Explain how the Central Support Team (CST) supported the school to date. What documentation is available for the SIG Monitoring Team to review to show evidence of these activities? Describe the future schedule for ongoing onsite support by the CST to the school. | Baltimore City Schools provided substantial evidence in a document binder to address this question. Baltimore City Schools has a two prong approach for supporting SIG schools: School Support Network and the School Support Monitoring team. The School Support Monitoring team is scheduled in SIG schools for half a day each month. School Support Networks assisted the school in completing the school readiness checklist to ensure readiness for the start of the school year. Baltimore City Schools identified the members of the Monitoring Teams for the Turnaround Schools and their calendar of support days for the school year. Plans are to meet three times each month: once onsite; once for planning; and once to follow up on the action plan. The power point used for training the Monitoring Team on their roles within the Turnaround School Initiative was provided in the document notebook. A School Support log is being developed to document all support provided to the school and to align the support to the strategies and activities in the SIG grant. |
| 7. Discuss the early lessons learned in implementing the Turnaround Intervention Model through School Improvement Grant. | There is a need to take a closer look at recruitment strategies for new hires for the school. Greater priority should be given for teacher hiring for the upcoming year. |
| 8. Describe the process for monitoring the “spend down” of the SIG funds. Who will be responsible for the monitoring? How frequently? | A spending plan was developed by the school. Monthly spending reports from the BCPSS grants administration office will be sent to the school. The principal will have access to these reports. The principal would like to hire a business manager to assist with grant management. |

Table 3

| Turnaro Turnaround Reqiore Requirement Model | LEA Design and Implementation of the Intervention Model (include alignment of additional resources) | Timeline for Implementation | Name and Position of Responsible Person(s) | SIG Team Consensus Comments (must indicate any documentation you reviewed during the 1st SIG Onsite Monitoring visit) |
| --- | --- | --- | --- | --- |
| 1. Replace the principal and grant the principal sufficient operational flexibility (including in staffing, calendars/time, and budgeting) to implement fully a comprehensive approach in order to substantially improve student achievement outcomes and increase high school graduation rates | Needs Assessment #2 – A new principal and new teaching staff will lead Booker T. Washington into a new era. A rigorous principal selection process has been designed and implemented to ensure we attract and retain “qualified and effective school leaders with a 3 year proven track record in turning around low performing schools yielding double digit results.” A thorough screening process to secure a body of evidence to support the turnaround leader track record. In part, the turnaround leader must exemplify characteristics of a distinguished principal that will ensure our students’ academic success. The Office of Human Capital (OHC) and the Office of the Chief Academic Officer will assist the newly selected principal with development of staffing model and the budgeting process as needed and in accordance with established guidelines. The Office of Teaching and Learning has a New Teacher Support Coordinator whose primary responsibility is to provide support for new teachers. The first layer of support is a mentor for each teacher who does not have tenure. This mentor will be an experienced teacher at the school who will meet at least once a week to provide school-based support for teachers. The mentor will meet with the New Teacher Support Coordinator at least quarterly in order to increase coaching skills. (from Needs Assessment Section 11-Comprehensive and Effective Planning) New Leaders for New Schools will provide a resident principal NLNS will provide support for the leadership team thru professional development and coaching (from School Budget Narrative) Hire additional administrator or teacher leader | April, 2010 | Office of Human Capital, Office of the Chief Academic Officer | Principal appears to be a good match for the school. She came on board on July 3, 2010 and was the result of a nationwide search for a school leader. Assistant principal (or teacher leader – as defined in the budget narrative) position is unfilled at this time and there is concern surrounding the selection process for such a critical position. This will be a SIG funded position. |
| 2. Use locally adopted competencies to measure the effectiveness of staff who can work within the turnaround environment to meet the needs of students (A) Screen all existing staff and rehire no more than 50 percent; and (B) Select new staff | Needs Assessment #12 - School leaders will be required to do daily classroom visits to all classrooms to monitor daily instruction and will log the class visits and teacher feedback about the instruction. Harvard’s Richard Elmore model of Instructional Rounds will be used to support teachers. The leadership team from Booker T with central office leaders will spend the week of July 5 at Harvard’s Leadership Institute to develop strategies to monitor and provide feedback to teachers to improve daily instruction to increases student achievement. At the end of the institute, a written plan will be developed. This plan will be monitored by the Executive Director of Secondary Schools for implementation and accountability. The CAO who will support the school leadership team by providing additional professional development and support throughout the year to increase their effectiveness in doing the “Instructional Rounds.” The CAO’s leadership team will participate in an “Instructional Round” at least once a month. OHC will provide school leadership with early opportunity to review and contact all veteran teachers who have indicated an interest in seeking a new school assignment through the voluntary transfer process or are specifically being considered for a turnaround school. OHC will assist school leadership in accessing new teacher candidates in shortage subject areas who are certified and highly qualified. | April, 2010, ongoing | Office of Human Capital, Executive Director of Secondary Schools, Office of the Chief Academic Officer | Leadership team has completed the summer training at Harvard. There is concern regarding the Office of Human Capital support in the teacher selection process for Booker T. Washington. All but 3 staff members were hired by central office prior to the arrival of the principal. There are 5 first year teachers on the staff and they plan with teacher leaders. There is only one returning teacher from the previous year at each grade level, 6-8th grade. All the special education teachers are new to the school. There are currently 5 long-term substitutes on staff. Classroom visits are being done daily and feedback is provided weekly. Formalized instructional rounds have not yet been implemented. This will occur beginning in October. The principal appears to have limited operational flexibility. |
| 3. Implement such strategies as financial incentives, increased opportunities for promotion and career growth, and more flexible work conditions that are designed to recruit, place, and retain staff with the skills necessary to meet the needs of the students in the turnaround school | Needs Assessment # 2 - Turnaround school teachers will have access to innovative compensation options that could result in up to $7000 of additional compensation above their salaries depending on the school’s reform package and student achievement outcomes. These financial incentives may come in the form of a salary increase for extended instructional hours, compensation for professional development during the summer, or performance bonuses earned by improving student achievement school-wide. Targets for student growth and achievement will be set for the school each school year. Teachers and school staff will be eligible to share in performance bonuses made available to each school when the school’s targets are met. The school will potentially get $500 per student plus 10% for performance bonuses and will work in collaboration with Office of Human Capital to distribute funds to employees. (All incentives are contingent upon availability of funding) To support increased staff retention, in particular teacher retention and satisfaction, turnaround school teachers will have access to innovative compensation options that could result in up to $7,000 of additional compensation above their salaries depending on the school’s reform package and student achievement outcomes. These financial incentives may come in the form of a salary increase for extended instructional hours, compensation for professional development during the summer, or performance bonuses earned by improving student achievement school-wide. Teachers will be afforded two weeks of planning time during the summer in the first year. In subsequent years, schools may choose to continue summer planning activities. Teachers will be compensated for participation in planning time during the summer. (from School Budget Narrative) Principal Pay Differential Principal Vacation Buyout (end of year) | April, 2010 | Office of Human Capital | School based decisions were made for compensation of teachers. Differentiated compensation system is being implemented, weighted for performance in reading, mathematics, and attendance. Additional compensation will be given to returning teachers (2011-2012) if the school meets academic targets set for 2010-2011. The two week of summer planning and professional development was held. New teachers attended training at Booker T. Washington but missed system-wide new teacher orientation. Principal was eligible for and received full pay differential and buy-out options. |
| 4. Provide staff with ongoing, high-quality, job-embedded professional development that is aligned with the school’s comprehensive instructional program and designed with school staff to ensure that they are equipped to facilitate effective teaching and learning and have the capacity to successfully implement school reform strategies. | Needs Assessment #9 – The school will increase after-school job-embedded professional development and/or collaborative planning. To prepare for the opening of school, ongoing professional development t on the Common Core Standards, the instructional Academic Priorities (Rigor, Intervention, and Engagement) as well as providing scale to the instructional quality will commence. School leaders will be required to do daily classroom visits to all classrooms to monitor daily instruction and will log the class visits and teacher feedback about the instruction. Harvard’s Richard Elmore model of Instructional Rounds will be used to support teachers. The part of the leadership team from Booker T. Washington along with central office leaders will spend the week of July 5 at Harvard’s Leadership Institute on Closing the Achievement Gap to develop strategies to monitor and provide feedback to teachers to improve daily instruction to increases student achievement. At the end of the institute, a written plan will be developed to map out the year long professional development opportunities. This plan will be monitored by the Executive Director of Secondary Schools and the Director of Turnaround Initiatives for implementation and accountability. The CAO who will support the school leadership team by providing additional professional development and support throughout the year to increase their effectiveness in doing the “Instructional Rounds”. The CAO’s leadership team will participate in an “Instructional Round” at least once a month. During the summer of 2010 the school will begin to frame their work with the Skillful Teacher practices outlined by Jon Saphier in his Research for Better Teaching (RBT) work. The staff will work with a consultant from RBT who will introduce the framework during the August training and continue the work throughout the school year. The RBT consultant will provide insight around implementation as the year progresses. Also, during the course of the school year New Leaders for New Schools will work to support the specific development of the leadership team. Their work with the team will begin with a diagnostic of school team operations and then move into the work of supporting the team to move student achievement. | July 2010, Ongoing | Office of Human Capital and Office of the Chief Academic Officer, Executive Director of Secondary Schools, Director of Turnaround | Two weeks of professional development was completed during the summer with a focus on rigor, intervention, and engagement. The summer professional development appeared to be well designed, organized and focused, and topics were relevant for teachers and students. Future professional development activities will be designed to address identified needs throughout the year. There was evidence of instructional norms (e.g. outcomes, objectives, student work, schedules, student self-assessments, etc.) There is no early release for PD. All PD is job-embedded and occurs weekly by content and grade level. An overview by a consultant was provided on Skillful Teaching practices based on Research for Better Teaching. Plans have been made to have the consultant return later in the year and next summer to provided professional development. This is on hold until the contract with NLNS is executed. |
| 5. Adopt a new governance structure, which may include, but is not limited to, requiring the school to report to a new “turnaround office” in the LEA or SEA, hire a “turnaround leader” who reports directly to the Superintendent or Chief Academic Officer, or enter into a multi-year contract with the LEA or SEA to obtain added flexibility in exchange for greater accountability. | Needs Assessment #12 - The school will report all activities to the Director of Turnarounds. This individual will work closely with the school-based leadership team to support and evaluate the implementation of the turnaround model. The Director will conduct periodic reviews to ensure that the curriculum is being implemented with fidelity, is having the intended impact on student achievement, and is modified if ineffective. ( Section 4.B LEA Capacity/Budget) Hire a Turnaround School Coordinator Hire a Coordinator of Turnaround School Accountability Contracted services with New Leaders for New Schools to provide intense support for leadership team (from Needs Assessment Section 11-Next Steps) BCS Support Network 11 is assigned to support Turnaround Schools (5 staff members) Weekly support from the Network lead 2 network liaisons will be at the school at least one x per week for academic support | July 2010-2013 | Sonja Brookins Santelises, Laura Weeldreyer, Director of School Turnaround TBD | Director of Turnaround Schools has been hired. Coordinator of Turnaround School Accountability has not been hired yet. This person will provide data and budget support. The school will develop a School Performance Plan(SPP) which will replace the school improvement plan. Its components will include: SIG grant (replaces core component); Title I schoolwide components; schoolafety, family/community engagement New Leaders for New Schools contract has not yet been executed. The funds were not currently available. Network 11 support for the school is occurring on a weekly basis. The principal reports that the Network support has been very helpful. |
| 6. Use data to identify and implement an instructional program that is research-based and “vertically aligned” from one grade to the next as well as aligned with State academic standards | Needs Assessment # 3, 6 City Schools has created a city curriculum that is aligned vertically and matches the State academic standards. Individual content and unit tests have been aligned with the curriculum. Data from these assessments are scanned into a database management system to identify individual student needs. This phase of this system will be available to all teachers on August 23, 2010. This system replaces our current OARS system which houses the benchmark results. School Net, a data warehouse and testing system, has been purchased for all City Schools. The first phase of this system will be available to all teachers on August 23, 2010. This system replaces our current OARS system which houses the benchmark results. School Net will also connect all the silos in City Schools that hold data (from attendance, to enrollment, to MSA and HSA data) This system is not merely a system to collect benchmark data but teachers will be able to create tests using an ETS item bank that is aligned to the Maryland State Standards and this data will be collected and compared with other data. But the amazing part of this system, when a teacher analyses the data and determines that a student needs a particular skill or concept, School Net will also be connected to resources for the student and teacher that will help the teacher remediate the skills. (This is during phase 2). (from School Budget Narrative) Hire an Education Associate position to implement Fine Arts instructional program | June 2010-2013 | Sonja Brookins Santelises, Director of School Turnaround TBD Matt Van Itallie, Achievement and Accountability | The BCPSS School Net system provides a means for the school to score and analyze benchmark data for reading and math. The first benchmarks have been completed and scanned into the School Net system. The school anticipates data now should be accessible since the new system is reported to be operational for middle schools. ETS provided the alignment between BCPSS benchmark assessments and Maryland State standards. The principal has two Education Associate positions (language arts and math) that are “fair-funded” (school level budget). Education Associates will work with central office staff to coordinate school curriculum with the fine arts program. |
| 7. Promote the continuous use of student data (such as from formative, interim, and summative assessments) to inform and differentiate instruction in order to meet the academic needs of individual students | Needs Assessment # 3,6 - School based staff will use City Schools quarterly benchmark assessments that are aligned to the Maryland State Curriculum, to inform their work. The benchmarks will serve as formative assessments for how to move forward within HSA tested areas. Under the director of the Chief Academic Officer, the executive directors for Teaching and Learning and Student Support Networks will meet with school based leadership staff to monitor progress of students in reading and math. Based on this need analysis, the corresponding offices will provide support to school leadership and to the teachers to analyze and interpret the student data, as well as provide other strategies for teachers to use to help students master these skills. (This is during phase 2.) (from Needs Assessment Section 6-Assessments) Teachers must use formative, interim and summative assessments consistently. Leadership must be sure that teachers know how to access benchmark data Data will be collected weekly School leaders will attend teacher planning sessions weekly and track school level data monthly CAO leadership team will attend these meetings at least monthly | July 2010-2013 | School –Based Administrators TBD, Director of Turnarounds Linda Eberhart, Executive Director of Teaching and Learning Sonja Brookins-Santelises, Chief Academic Officer | There are 80 minutes of common planning time every day for teachers. The teachers were provided training on School Net. |
| 8. Establish schedules and implement strategies that provide increased learning time | Needs Assessments #5- The school day will be extended for an additional 90 minutes each day for all students. The school day will start at 8 a.m. and will end at 4:15 p.m. instead of 2:45 p.m. which is the normal day by the union contract. Teachers will be remunerated to support their time in extended day. During the extended school day block students will have the opportunity to engage in additional art classes as well as remediation if necessary. Four Art Teachers will be funded through general fair student funding dollars to ensure the implementation of a rich art curriculum during the block and throughout the school day. An intervention or enrichment period is planned for all students each day. The KIPP model will be used that begins the day with an intervention/enrichment period where all teachers will be assigned a small group of students to support additional reading and math instruction. Students’ needs are assessed on a weekly basis during a focused discussion at the grade level team collaborative planning time. A data matrix that is completed during the planning time will be used to track the skills that students need to master during the intervention period. Each student will receive a regular literacy and math class for 60 minutes each day that addresses grade level needs in these areas. In addition to the regular literacy class sixth grade students will also receive an interdisciplinary class of Reading through Theatre daily. This class will apply literacy skills through an art integration approach by interpreting the text through theatre. City Schools general funds $250,000) will be used to install a black box theatre so that students will have the most up-to-date facilities for this class. During the summer of 2010, Booker T. Washington teachers will work cooperatively to develop the curriculum and assessment for this course. This curriculum and the $5,000 stipends will be paid by The Office of Teaching and Learning, and it will be reviewed to ensure that it is aligned to Maryland State Standards. Additional time will be provided to students who are basic in math during Saturday School classes for 3 hours twice a month from September through May. This funding for year one will be supported by the Title 1 ARRA Comprehensive Extended Learning Grant. This will provide an additional 60 hours of instruction throughout the year. In additional to the highly qualified math teachers from Booker T Washington additional tutors will be provided by Morgan State. (from Needs Assessment Section 3-Student Achievement) Students will receive 2 periods of literacy instruction; one will be the basic English course; second block will be reading intervention such as Read 180, Reading Apprenticeship, and Corrective Reading will be in place second semester Similar plan for mathematics; a variety of interventions will be in place second semester 8th grade students who scored below 300 on MSA will take an algebra readiness course as well as the HSA algebra data analysis course. | July 2010-2013 | School –Based Administrators TBD, Director of Turnarounds Linda Eberhart, Executive Director of Teaching and Learning Sonja Brookins-Santelises, Chief Academic Officer | There are 60 minutes of extended learning time four days a week; however the grant reflects 90 minutes. This will need to be amended. The extended day will include all 6th, 7th, and 8th graders. The focus of the 6th grade extended day will be the Arts while 7th and 8th grade extended day will have a reteach and advisory focus. 99% of the 7th and 8th graders are attending Booker T. Washington because they were former students, not because of the Arts. Plans are being made to contract with outside vendors to provide Extended Learning Opportunities (ELO) rather than teachers (e.g. University Instructors). Principal is investigating possible opportunities for morning math. . There has been professional development around the fine arts area (e.g. dance, photography, choral music, band, theater). While math interventions have begun, reading interventions have not yet been implemented. The reading interventions has not been selected for the school |
| 9. Provide appropriate social-emotional and community-oriented services and supports for students | Needs Assessment #7, 8 - Additional personnel will be hired to provide a safe environment for all students. A community outreach liaison will be funded through the SIG grant. This person will be support centrally by the Office of Communications and Family Partnerships. The role of the outreach liaison will be to work with and support families to create a safe climate at Booker T. Washington. A behavioral specialist will also be hired through general funding. This person will work with students who need to find alternative methods to resolve conflict. The behavioral specialist will provide students training to become Peer Conflict mediators. The City Schools Network 11 Student Support member will work with the staff each week to implement strategies to continue to improve the climate of the school and lower the suspension rate. The suspension rate will be tracked on at least a monthly basis by the Executive Director of the Office of Student Support. Monthly feedback will be given to the school leadership team about their progress in this area as well as suggestions to continue to decrease the rate. There will be three hall monitors who will be strategically assigned in the building to support the movement of students during class period changes and when students are in classes. (from Needs Assessment Section 7-School Culture and Climate) A new entrance for students will be built adjacent to the main office to improve security The University of Maryland at Baltimore will set up a clinic at the school that will include mental health services, dental services, and entire wrap around services that will be needed for a Community School. These services will be available to students during the day but also to the families and community during the evening and on the weekend. The dean of the School of Social Work at UMAB is coordinating this project through the Office of Families and Partnerships in City Schools. It will be modeled after the successful Harlem Children Zone in NYC. These services will be provided free. City Schools just has to provide the space at the school as well access for these services in the evening and on the weekends. All staff will be trained in PBIS during the two week August school-based summer professional development session. During this time teachers will also develop common standards and procedures that will be implemented for the 2010-2011 school year. The Office of Student Support will provide this training and support. Staff will train on the PBIS, and leadership will ensure the effective implementation by supporting teachers and making available rewards for the students – a store, field trips, etc. The Family School Council’s subcommittee on parent involvement will establish and implement a strategic plan to ensure communication to families which will include Back to School nights, a regular communication system, bulletin boards in the school, etc. Leadership will be reaching out to the community, particularly the arts community, to create youth leadership opportunities for students. (from Executive Summary) Leadership will develop Mission and Vision with input from stakeholders | July 2010-2013, ongoing | School-Based Administrators Jonathan Brice, Executive Director of Student Support Services Michael Sarbanes, Executive Director – Partnerships, Communications, & Community Engagement | Community School Coordinator has been hired. Behavior specialist has been hired (Dean of Culture and Climate). The specialist has held 72 parent conferences to date. Hall monitors are in place. The students travel in the hallways lined up in ABC order. There is a school police officer on staff. New entrance is in place. The school is clean, freshly painted, and the learning environment is inviting and conducive. Student work was posted, some with feedback provided to students using Post-It notes. There are 1.5 social workers, full time psychologist, and nurse (RN). The leadership team has participated in community walks with students. Family school council school committee is scheduled. University of Maryland School of Social Work interns are in the building on Tuesdays, Wednesdays, and Thursdays. There are three interns. The staff has only been given an overview of PBIS. It is not operational currently. The principal’s vision is for the school and the school community to reclaim its positive past history and culture. Cab Calloway once attended Booker T. Washington. The school had strong community support and pride. She plans to achieve this through academic rigor, resilience and relationships. The principal uses data to move global understanding. Every staff member is given articles to read each week. |

| Permissible Strategies for the Implementation of the Turnaround Model. LEA may implement any of the required and permissible under the transformation model or design a new school model (e.g. themed, dual language academy) |
| --- |
| Strategy | Timeline | Person(s) Responsible | SIG Monitoring Comments (must indicate any documentation you reviewed during the 1st SIG Onsite Monitoring Visit) |
| Establish performing arts instructional program & increase academic rigor (Needs Assessments 4,5) | Sept. 2009-Sept.2013 | School -Based Director of the Arts Director of Turnaround Schools Linda Eberhart, Director of Teaching and Learning Sonja Brookins-Santelises, Chief Academic Officer | This has been initiated and will be ongoing. |
| Strong community involvement & interested partners identified (Needs Assessment #8) | Sept. 2009-Sept.2013 | School -Based Director of the Arts Director of Turnaround Schools Linda Eberhart, Director of Teaching and Learning Sonja Brookins-Santelises, Chief Academic Officer Michael Sarbanes, Executive Director – Partnerships, Communications, & Community Engagement | This has been initiated and will be ongoing. |
| Adjustment to schedule to ensure Arts Integration throughout the curriculum. (Needs Assessment 5) | Sept. 2009-Sept.2013 | Amy Rosenkrans, Director of Humanities | This has been initiated and will be ongoing. |
| Other Actions the LEA will take to implement the Turnaround Model |
| Strategy | Timeline | Person(s) Responsible |  |
| Recruit, screen, and select external providers to ensure quality (Needs Assessment 10) Recruit, screen, and select external providers to ensure quality of instruction for the arts. (Needs Assessment 10) | July 2010- July 2013 | Office of Human Capital and Office of Academics | This has been initiated and will be ongoing. |
| Ensure that additional funding is secure so that the theme- Arts- is implemented to fidelity (Needs Assessment 10) | May 2010 | Amy Rosenkrans, Director of Humanities | This has been initiated and will be ongoing. |