# Title I School Improvement Grant (SIG), section 1003(g)

# SIG Monitoring Team’s First Onsite Visit Feedback

School: Commodore John Rodgers Elementary/Middle School LEA: Baltimore City Public School System (BCPSS) Principal: Marc Martin LEA Turnaround Director: Beth Nolan LEA Central Support Team Lead: Tasha Franklin Johnson SIG Team’s School Visit: September 29, 2010

Title I School Improvement Grant (SIG):  The School Improvement Grant (SIG) Program, authorized under section 1003(g) of Title I of the Elementary and Secondary Act of 1965, provides funding through State educational agencies (SEAs) to local educational agencies (LEAs) with the lowest-achieving schools that have the greatest need for the funds and demonstrate the strongest commitment to use the funds to raise significantly the achievement of students.  The United States Department of Education (USED) views the large infusion of Federal funds into the SIG program through the American Recovery and Reinvestment Act of 2009 (ARRA) as a historic opportunity to address one of the most intractable challenges for America’s education system: turning around or closing down our Nation’s persistently lowest-achieving schools.  Maryland’s approved application reflects Secretary Duncan’s determination to ensure that SIG funds are used to implement one of four rigorous school intervention models—turnaround, restart, transformation, and school closure.  Through a rigorous technical review process, MSDE approved Prince George’s County Public Schools’ application (PGCPS) on July 1, 2010 and Baltimore City Public School System’s application (BCPSS) on August 27, 2010.  Both school systems were granted approval to charge to their grants beginning July 1, 2010.

Maryland State Department of Education’s (MSDE) Monitoring of LEA Approved SIG Application:  As approved by USED, MSDE will monitor each LEA that receives a school improvement grant to ensure that it is implementing its intervention model fully and effectively in Maryland’s Tier I and Tier II schools.  Both PGCPS and BCPSS must submit to MSDE a quarterly summary report of the LEA monitoring/oversight that has been completed and the progress the Tier I or Tier II schools have made towards achieving their goals. In addition, MSDE will perform onsite visits to these same schools.  The primary function of the onsite visits is to review and analyze all facets of a school’s implementation of the identified approved intervention model and collaborate with leadership, staff, and other stakeholders pertinent to goal attainment.  MSDE’s School Improvement Grant Monitoring Teams (SIG Teams) will conduct three onsite monitoring visits annually (Introductory/Start Up One Day Visit; Interim Midyear Two Day Visit; and End of Year One Day Visit) with the school leadership team and district level team composed of staff responsible for the technical assistance, administrative support, and monitoring.

# SIG Monitoring Team’s First Onsite Visit Purpose:

The Introductory Start-up Onsite Visit is the first opportunity for the SIG Monitoring Team to discuss BCPSS’ approved SIG Plan for Commodore John Rodgers Elementary/Middle School with school and district staff to ensure that all school system stakeholders are familiar with and understand the approved SIG Plan.  In addition, BCPSS was required to present an update on the system’s progress in the implementation of its approved plan for Commodore John Rodgers Elementary/Middle School.  During this update, LEA and School Staff shared what has been implemented; what has been partially implemented; and what has not been implemented at this time. BCPSS also discussed potential changes it needs to make in the school’s approved plan for the first year of SIG.   BCPSS staff was asked to provide a guided tour of the building for the SIG Team.

# BCPSS SIG Background:

- In Maryland’s approved SIG application, the Maryland State Department of Education (MSDE) identified five Tier I schools and seven Tier II schools in the BCPSS.

- During the 2008-2009 school year, BCPSS launched Expanding Great Options Initiative to create more and better school options for all students over time.  The City Schools began to link school performance and parent choice to facility improvement and new school creation strategies.  With federal stimulus dollars under the American Recovery and Reinvestment Act of 2009 (ARRA) combined with Title I School Improvement Grant, under section 1003(g), BCPSS was presented new opportunities for transforming its persistently lowest achieving schools and advancing its Expanding Great Options goals more broadly and strategically.

- On August 27, 2010, MSDE approved BCPSS’ SIG Application.  At that time, MSDE gave approval for BCPSS to begin charging to its SIG on July 1, 2010.

- In its approved SIG application, BCPSS made the decision to serve all five of its Tier I schools and only two out of the seven Tier II schools.

- BCPSS made the decision not to serve Cherry Hill Elementary/Middle School, Francis M. Wood Alternative High School, Frederick Douglass High School, Institute of Business and Entrepreneurship High School, and Masonville Cove Academy.   In its approved SIG application, BCPSS provided the reasons it lacked the capacity to serve these schools.

- BCPSS made the decision to implement a specific intervention model for the following Tier I and Tier II schools:

| School | Tier I or Tier II | Intervention Model |
| --- | --- | --- |
| Calverton Elementary/Middle School | Tier I | Restart Intervention Model |
| Commodore John Rodgers Elementary/Middle School | Tier II | Restart Intervention Model |
| Baltimore IT Academy (formerly Chinquapin Middle School) | Tier I | Restart Intervention Model |
| Garrison Middle School | Tier I | Restart Intervention Model |
| William C. March Middle School | Tier I | Restart Intervention Model |
| Augusta Fells Savage Institute of Visual Arts HS | Tier II | Turnaround Intervention Model |
| Booker T. Washington Middle School | Tier I | Turnaround Intervention Model |

- BCPSS will receive $25,183,804.00 over a three year grant period for its seven Tier I and Tier II SIG schools.

- Based on its approved SIG Plan, BCPSS, in its LEA SIG budget, will receive $1,999,343.00, in the first year; $2,049,995.00, in the second year; and $1,838,605.00, in the third year.  The total SIG amount for the LEA over the three years is $5,887,943.00.

- Based on its approved SIG Plan, Commodore John Rodgers Elementary/Middle School will receive $1,027,065.00, in the first year; $558,722.00, in the second year; and $558,722.00, in the third year.   The 3 year SIG grant totals $2,144,509 for Commodore John Rodgers Elementary/Middle School.

- Based upon evidence reviewed from the SIG Monitoring Team’s three onsite visits, MSDE will determine the LEA’s capacity to ensure goal attainment, and subsequently, renewal of the School Improvement Grant funds each of the three years for the school district and school.

- In its approved SIG application, BCPSS identified 16 individuals as members of its 1003(g) Central Support Team (CST).  BCPSS did not identify a lead for the CST.  In terms of reporting and communications, MSDE identified Tasha Franklin Johnson, Office of Federal Programs/Title I Director, as the CST lead.

- In its documentation provided at the SIG Teams’ First Onsite Visits, BCPSS provided a list of 21 individuals as active members of its Turnaround Central Office Support Team with the following goal:

All school based issues are resolved within or a plan is developed to get to resolution within 48 hours.

- In addition, BCPSS’ School Support Networks provide a streamlined model for problem-solving, communication and central office collaboration and support to schools.

- Beth Nolan, SIG Turnaround Director, was appointed on September 14, 2010 and began working on September 25, 2010.

- Marc Martin, Principal at Commodore John Rodgers Elementary/Middle School, was appointed on May 25, 2010 and began working on July 1, 2010.

# The following individuals participated in the SIG Team’s Visit on October 5, 2010:

- SIG MSDE Monitoring Team Leader:                     Hilda Ortiz

- SIG MSDE Monitoring Team Members:                 Scottie Griffin, Ann Glazer, Donna Olszewski, Mary Cross

- SIG  MSDE Monitoring Lead:                                 Tina McKnight

- BCPSS Turnaround Director:	      	               Beth Nolan

- Living Classrooms Foundation (Restart Partner):  Scott  W. Raymond (V.P., Education)

- Principal:      	           	  		              Marc Martin

- BCPSS Attendees:                                                 Jamila Sams, Tara Barnes, Krystal Henry, Roann Tsakalas, Jacquile

Muldrow, Toni M. Worthington, Nakeia Oliver, Irma E. Johnson,

Janise Lane, Pamela Moore, Malcum Dates, Jill Basye-Featherston

SIG Monitoring Team’s First Onsite Visit Feedback for Commodore John Rodgers Elementary/Middle School:

- TABLE  I:   Based on its first monitoring onsite visit, the SIG Monitoring Team determined overarching issues on BCPSS’ Approved SIG Plan.   BCPSS must submit required responses to MSDE by the identified timeline.

Special Note: All required responses submitted to MSDE on or before December 15, 2010 must be submitted at the same time.

- TABLE  2:   MSDE required each SIG Monitoring Team to ask the LEA and school specific questions related to its SIG approved plan. This table reflects what BCPSS shared verbally with the SIG Monitoring Team.  The SIG Monitoring Team compiled information that was shared by the LEA and school in this table.  This information will be reviewed and used by the SIG Monitoring Team during its second onsite visit.

- TABLE  3:   MSDE developed a SIG Monitoring Tool based on the LEA’s approved plan for a specific school.  This tool was used by the SIG Monitoring Team to determine the school system’s implementation of the approved plan.  The SIG Monitoring Team compiled information that was shared by the LEA and school in this table.  This information will be reviewed and used by the SIG Monitoring Team during its second onsite visit.

Commodore John Rodgers Elementary/Middle School-Restart Model Restart Partner- Living Classrooms Foundation (LCF) (From the Baltimore City’s SIG Executive Summary) Commodore John Rodgers is partnered with the Living Classrooms Foundation (LCF), which operates The Crossroads School, a successful charter middle school in the same community. Commodore John Rogers will have a new principal this year and teachers were asked to reapply for their jobs. Under the leadership of LCF, this school has been identified as a site for National Board Certification by the Maryland State Department of Education and teachers will receive a tremendous amount of coaching, mentoring and professional development. The school will have an extended day in SY 2010-11. Other hallmarks of the school will include the following: technology will be infused into the classroom; a Dean of Students will be responsible for extensive community outreach; and students will begin to develop portfolios which are presented to the community three times per year.

# TABLE  1

| SIG Monitoring Team First Onsite Visit’s Overarching Issues on BCPSS’ Approved SIG Plan for Commodore John Rodgers Elementary/Middle School |
| --- |
| Issues | Required Response from BCPSS | Timeline |
| 1. Programmatic & Fiscal Monitoring BCPSS’ SIG application was approved August 27, 2010, and MSDE gave approval for BCPSS to begin charging to this grant as of July 1, 2010. The SIG Team understands there are some activities and strategies, for many reasons, that may or may not be implemented as written in the approved grant. Commodore John Rogers Elementary/Middle School had a projected enrollment of 220 students for 2010-2011, however the current enrollment is greater than 450 students. With more than doubling of the expected enrollment, the school has some immediate staffing and instructional material needs. One 4th grade class has 36 students. These unanticipated needs may prompt amendments to the SIG grant. The SIG Monitoring Team recommends that BCPSS review the plans and budgets for both the LEA and Commodore John Rodgers. BCPSS needs to submit programmatic and fiscal amendments to MSDE as soon as possible. | Submit grant budget/program amendments as soon as possible to MSDE for review and approval for Commodore John Rodgers Elementary/ Middle School. Special Notes: BCPSS must receive prior written approval from the MSDE Program Monitor before implementing any programmatic changes. BCPSS must receive prior written approval from the MSDE Program Monitor for any budgetary realignment of $1,000 or 15% of total object, program or category of expenditure (whichever is greater). Rationale for these budgetary changes must be clear. | On or before December 15, 2010 |

Table 2

| Overarching Questions for the District Central Support Team and the School Staff | SIG Monitoring Team Consensus Feedback On Overarching Questions from the 1st Onsite Visit at Commodore John Rodgers Elementary/Middle School |
| --- | --- |
| How have the LEA and the school ensured that all school stakeholders have been informed about the SIG approved plan for the school? What documentation is available for the SIG monitoring team to review that shows evidence of these activities? What future activities are planned to inform all stakeholders as the plan is being implemented? | The Operator (Living Classrooms) had extensive outreach into the community. Parents were invited to experience a similar program at Crossroads School. Multiple presentations were given during school board meetings and school site meetings during the selection process for the Operator of the school. The document binder included the May 3, 2010 letter sent to inform Commodore John Rodgers Parents about the selected Turnaround Operator for the school. |
| Describe the plans for the LEA to provide a rapid response to address immediate needs of the school. | School Support Network team is currently being trained. BCPSS provided a binder with documentation for their structured process for responding rapidly to immediate needs of its SIG schools. BCPSS Rapid Response Team has a written process for responding to SIG school needs immediately. The goal of the team is that all SIG school based issues are resolved within or plan is developed to get to resolution within 48 hours. This process is in its initial stages of implementation. BCPSS report that there is district-wide awareness of SIG schools with special “tagging” of SIG Schools to help ensure 48 hour response or plan of action to address issues. All support for SIG schools will be logged in a School Support Log. The School Support Log correlates issues and responses to the grant strategies and activities. SIG Schools are given a higher priority by BCPSS through their School Support Network initiative. |
| Describe some visible improvements (quick wins) early in the school turnaround process. | Enrollment increases Facilities improvement Staffing increases Climate improvement Emphasis on use of technology Buy-in from parents Safety measures for prek/k pickup. Parents sign these students out daily. |
| Describe any changes as of today that address culture and climate issues that impact teaching and learning. | The school uses an online system for tracking behavior infractions which parents can access. The school established Five Promises that were posted throughout the school to help remind students and staff of behavior expectations. There is an established system for demerits and detentions as a consequence for inappropriate behaviors. A collaborative re-entry process after suspensions was established to include all involved individual (parents and students). |
| What are the LEA’s and school’s plans to ensure that there will be a consistent focus on improving instruction? | Once the analysis of student achievement data is completed (MSA, diagnostic testing, etc.), school will then initiate the multiple strategies identified to address instructional and learning needs. Focus on student needs, meaningful instruction, and more learning time. There is a focus on use of data to inform next steps. Teacher collaboration and collegial classroom visits are in place to support shared accountability. Planned monthly meetings by the LEA’s SIG monitoring team and ongoing School Support Network support have a focus on improving instruction. |
| Explain how the Central Support Team (CST) supported the school to date. What documentation is available for the SIG Monitoring Team to review to show evidence of these activities? Describe the future schedule for ongoing onsite support by the CST to the school. | BCPSS provided substantial evidence in a document binder to address this question. The members of the Turnaround Central Office Support Team were listed. BCPSS has a two prong approach for supporting SIG schools: School Support Network and the School Support Monitoring team. The School Support Monitoring team is scheduled in SIG schools for half a day each month. School Support Networks assisted the school in completing the school readiness checklist to ensure readiness for the start of the school year. BCPSS identified the members of the cross functional Monitoring Teams for the SIG Schools and their calendar of support days for the school year. Plans are to meet three times each month: once onsite; once for planning; and once to follow up on the action plan. The power point developed for training the School Support Monitoring Team on their roles within the Turnaround School Initiative was provided in the document notebook. There is a form for the Monitoring Team’s onsite school monitoring visits. BCPSS trained school staff on Title I SANE documentation process. |
| Discuss the early lessons learned in implementing the Restart Intervention Model through School Improvement Grant. | Transition is huge –more time was needed for planning. New leadership had lack of history and had to build trust with the community. Changing the climate was difficult. Greater enrollment than anticipated (caused challenges in school opening). The lack of usable test data is barrier to effective instruction that address student needs. |
| Describe the process for monitoring the “spend down” of the SIG funds. Who will be responsible for the monitoring? How frequently? | This will be a collaborative process between the school and the LEA. A spending plan was developed by the school. Monthly spending reports from the BCPSS grants administration office will be sent to the school. The principal will have access to these reports. |
| Describe how the LEA has monitored the Restart Partner for this school up to this date. What documentation is available of the monitoring? What is the process for ongoing monitoring in the future? | The LEA holds monthly meetings with schools. The document binder included the Operators Meeting Schedule for SIG Schools for 2010-2011. Living Classroom Foundation will meet monthly at the BCPSS Central Office for technical assistance. A sample agenda was provided. Performance goals for the school were provided. |

Table 3

| Data point (from Needs Analysis) | School Needs Assessment | Strategy to address: Note: See the school plan document for the “Persons responsible” and “Estimated date of each completion” for each strategy.) | Documentation that can be used as evidence of Successful Completion | SIG Monitoring Team Consensus Feedback (must identify all documentation reviewed during the 1st SIG Onsite Monitoring visit) |
| --- | --- | --- | --- | --- |
| Student Profile | Increase enrollment overall but specifically in the middle school Improve attendance Reduce suspensions and expulsions | To meaningfully increase enrollment from year to year, the school will first need to improve student achievement, school culture and climate, and safety for all students and staff. We will need to communicate strategies and progress to the community using actual student achievement data and conduct active outreach by way of the Community Associations, and families who might consider re-enrolling in Commodore John Rogers (CJR). Living classrooms also intends to contact “Waitlisted” families to enroll in CJR at the middle school level As a part of the outreach to all families, Living Classrooms will articulate a commitment of an attendance goal of (95%). Any students who are below 95% will have home visits; students who do not meeting adequate attendance rates will be placed on an intervention plan to include detention time. Students who are meeting or exceeding attendance benchmarks will be recognized and rewarded. Living Classrooms intends to implement PBIS school-wide and set with parents and students firm expectations regarding respect and student behavior. CJR staff will implement Super Star Referral certificates for students who demonstrate excellent behavior and model this throughout the year. Early intervention will occur for students who don’t meet expectations. Interventions will include but not be limited to phone conferences with parents and weekly detention. | Increase enrollment by 10% Annual attendance data and On course attendance tracking though out the school year Suspension and expulsion rates | The expected enrollment was 220 students, but the school has a current enrollment of 460 students. Staff conducted strategic recruitment School planning and implementation impacted by higher numbers than expected. Shared attendance policy with every family at the time of enrollment. Social worker helped to address attendance issues with specific families. Summer workshops addressed attendance policies. Staff uses online attendance record keeping which parents can access. Every incident has been documented. There have been 12 suspensions to date. There were a total of 138 suspensions all of last year. After suspensions, a suspension conference with parents and students are held to reconcile the situation (re-entry process) The school has already had their first PBIS party. |
| Staff Profile | Hire 27 new staff PD for new teachers | Recruit system-wide All teachers (especially those with less than 5 years experience) will be provided with Professional Development (PD) and coaching – see all strategies and practices listed in the PD section. A fulltime Dean of Students will dedicate part of her day to mentoring these teachers with less than five years of experience. All teachers will complete a professional development survey and have access to aching and other professional development opportunities. This school has been identified as a National Board Certification School by MSDE. A full time Dean of Students will dedicate part of her day to mentoring teachers with less than five years experience. These teachers will have coaching, informal observation, video of their classroom teaching for self reflection, observing peer classroom teaching, and feedback from learning walks (weekly). All teachers will fill out a professional development (PD) survey so the PD plan will reflect the self identified needs of staff. Some PD will be given one on one and some PD will be school-wide or in small groups. All teachers will have access to the coaching and the other PD listed above for teachers with less than five years of experience. (from the Next Steps in the Needs Assessment) | 22 teachers have been hired to date. PD and program implementation plans, weekly PD records, PD survey | 1. Principal interviewed approximately 300 candidates for 22 positions. All core teachers are highly qualified. There are 12 teachers involved with the National Board Certified program. Living classrooms observed all former teachers and only offered employment to 5 out of 60 teachers. Due to increases in enrollment, additional staff needs to be hired. (such as the intermediate class with 36 students and primary class with 30 students). 2. Teachers completed a survey to determine their strengths and professional development needs. Professional development will be based on identified needs and will be prioritized. Teachers received a week of professional development prior to system wide staff reporting back to school. The schedule is designed to allow for PD each Wednesday beginning at 1:00 p.m. (for 2 hours). |
| Student Achievement | Culture of high expectations Student investment and engagement in achievement Providing timely, accurate, and specific feedback Frequent assessment of student progress with opportunities for improvement Additional time on task Skill-building One-on-One Intervention/Support Parent involvement in school work Low attendance Address multiple skill levels Confirm learning | Teachers will plan collaboratively to outline their scope of work for their grade level and content area by balancing City Curriculum documents, National Standards, State Standards (Common Core and the Maryland State Curriculum) Student portfolios will be maintained. Teachers will share specific achievement goals for each grade level at the start of the school year. Students will select work for portfolios that demonstrate learning outcomes and track progress towards mastery. The Operator will provide additional out of school time experiences to support increased student achievement. Living Classrooms will develop a Strategy board for exchanging best practices and to provide immediate feedback. Teachers will score student work collaboratively and provide student feedback in order to norm expectations for accuracy. The testing program will include the following: Diagnostic testing Benchmark testing Concept Assessments Unit Assessments Performance Assessments The Revision system will reflect the following: Students will have multiple opportunities to re-test in order to build mastery Extended Day Schedule Homework will be targeted with a focus on building mastery of skills already learned Small group instruction Regular parent contact such as phone calls, conferences, and letters home in “parent friendly” language and Spanish Small group instruction Regular parent contact such as phone calls, conferences, and letters home in “parent friendly” language and Spanish Increase daily attendance Differentiated instruction Daily assessments | 1-2: Scope of work for each grade level/content area Student portfolios Student-led conferences Presentations of Learning Photo gallery on line of methods for immediate feedback Process of analyzing teacher feedback of student work during collaborative team meetings documented through video and posted on a SharePoint site Test score analysis Rescored assessments Documentation of student growth on assessments Part of instructional day tracked by Oncourse Teachers’ Schedules Call logs completed by teachers and maintained by Marc Martin Increased student attendance 92.5% (2009 - 90.2%) Lesson Plans/Classroom Observations Weekly data analysis | Teachers plan their scope of work for their grade level that addresses state curriculum (curriculum mapping and team planning). Students keep artifacts of their work to be placed in portfolios. To learn how to conduct presentations of learning, staff from Crossroads School was invited to model student led presentation of their learning. Students’ work is connected to the school’s learning targets. Strategy boards were evident in the collaboration room. Work on developing projects for the performance assessments has begun as well as unit assessments. Teachers will use weekly assessments and daily exit tickets to ensure that standards are being met. The staff is in the progress on their reading diagnostic testing of all students. Students have begun using revision binders. Display board outside of the classroom indicated a student task for revisiting their work in revisions binders. The extended school day is 7:30 to 3:00 M,T,Th.F. An after school program for middle school math has begun. Forty students are participating. The school’s schedule indicates an acceleration period that is used for providing academic intervention and for accelerating instruction for students performing above grade level. Parents are required to attend student led conferences. If parents are unable to attend, the staff visits parents. Professional development will be provided at the appropriate time based on priority need from the teacher survey. |
| Rigorous Curriculum | Development of performance learning experiences that cross disciplines and are grounded in meaningful real world applications in order to engage students. Improve reading skills and MSA scores Meet daily learning objectives in reading Curriculum and instruction alignment Meet daily learning objectives in math | Performance Learning Curricular Design Develop structured design process to assist teams of teachers in creation of performance learning experiences. Vertical planning opportunities for grade level teams to build and expand on the learning experiences from grade levels above and below. Living Classrooms will implement Success For All Reading Edge program Living Classrooms will use the Open Court curriculum All instruction will be aligned with the Maryland State Curriculum. Living Classrooms will continue to use MathWorks curriculum The operator will ensure that the curricula are aligned with state standards and City Schools curricular mapping. All textbooks and other resources will be aligned with these curricula. Planning of the curricula will engage teachers and leadership by content and grade levels. PD will be provided to strategize with teachers how to differentiate their lesson plans based on student needs (i.e. small group instruction) and identify rigor. Living Classrooms will engage in Collaborative Analysis of Curricular Resources for Rigor using the following approach: THE WHAT: Develop protocol that analyzes rigor of curriculum scope by cross analyzing curricular documents with Common Core and National Standards. THE HOW: Use protocol to match current content specific research with how we are requiring students to demonstrate their knowledge – emphasis on higher level and critical thinking opportunities. Video analysis of teaching to determine a common expectation of rigor and a common language to explain it. Development of performance learning experiences that cross disciplines and are grounded in meaningful real world applications in order to engage students. | Performance learning experiences Cross-grade level collaboration Improved scores on formative reading assessments Daily assessments Lesson plans and posted daily learning objectives in classrooms Daily assessments | Staff meets one Wednesday a month for vertically planning discussions and to allow for expansions of learning experiences. They also meet one Wednesday a month to discuss project based experiences. One project is planned for each grade level which has integrated application. Not implementing Success For All. Other alternatives are being considered. Teacher met during the summer to begin their curriculum alignment and planning. They created curriculum maps to guide their work. The video taping of lessons have been started to support lesson study. |
| Instructional Program | Alignment of instruction with curricular scope and sequence Use of timely and frequent data points to inform instruction Integration of Technology in Instruction Investing in high levels of student engagement More rigor in math/ reading with research-based instruction curricula Improve use of technology Data analysis to inform/differentiate instruction Master Schedule | The operator is experienced in school operation and is familiar with City Schools’ curricular maps. They will use MathWorks and partner with Success for All for daily reading block using Reading Edge and Open Court for language arts. The school has 24 Smart Boards, documentation cameras, and a student response system to support the infusion of technology into the curriculum. Teachers will receive PD on how to infuse this technology into their lesson planning to meet the needs of varied learning styles of students. The Living Classrooms will use a Pacing Board to implement the following: Tracking of progress along curricular sequence for every grade level/content area on board in Teacher Collaboration Center Vertical planning opportunities for grade level teams to build and expand on the learning experiences from grade levels above and below. Living Classrooms will use City Schools’ Data Warehouse to: Train all teachers on how to access the district data warehouse Train all teachers on how to create assessments connected to data warehouse Train on how to utilize information to revise instructional plan for both pacing and instructional strategies Living Classrooms will train on using a SMART Board: Training for all teachers on how to use SMART Board, and student response clickers technology Training for all teachers on how to create flipcharts to support instruction using the SMART technology and storage of these resources on teacher collaboration SharePoint site. The following strategy will be used via Student Led Conferences and Presentations of Learning. The Living Classrooms will use the City Math Curriculum and partner with Success For All for daily reading block using Reading Edge. Technology integration will be an integral component of implementing the curriculum: 24 SMART Boards, documentation cameras, student response system. The Living Classroom will utilize benchmark data to monitor student progress. Living Classrooms will increase class time in core subjects | Pacing board Training schedule for data warehouse PD schedule for using data to transform instruction 3.SMART Boards installed SMART Training schedule SMART folder on SharePoint Site Lesson Plans that exemplify SMART integration 4.Presentations of Learning by all students 5.Student-led conferences by all students Daily instruction schedule; Observation and lesson plans Data Records Daily instruction schedule | During the summer teachers created curriculum maps and pacing board. Teachers are using Smart Boards. The use of technology was evident in all observed classrooms. This will take place throughout the school year when teachers meet for collaborative planning. Teachers were observed using effective use of Smart Boards in the classroom. This was modeled for staff of Crossroads Charter School. School day from 7:30 to 3:00 with 2 hour blocks of instruction, Literacy/Humanities and Math, and an Acceleration math block. |
| Assessments | Informative Data | Living Classroom will use multiple data sources to guide instructional decisions. These data will include benchmarks, high stakes testing (Stanford, MSA, Dibels, and teacher created assessments). Universal design will be used to meet the varied learning styles of students. Teachers will be trained to access benchmark data and how to analyze that data. They will give daily assessments (quizzes, exit tickets) and tests in order to have timely data to assess the effectiveness of their instruction and what they need to re-teach. If 70% of the students fail the quiz or exit ticket then the skill will be re-taught to the whole class. If not, then specific students will be provided more strategic intensive intervention (small groups, pull-out when necessary) to be re-taught the skill. Teachers will collaboratively plan twice a month – one time will be a vertical planning meeting and the other will be a grade level meeting. Student assessment data will be analyzed and teachers will strategize how to adjust their instruction to better meet the needs of their students. | Quarterly Data results | Data will be reviewed with a focus on student outcome. |
| School Climate & Culture | Improve Culture and Climate | The operator will continue to use the PBIS discipline plan and add a demerit program- both to be used school wide and with fidelity. The demerit program is web based and families will have access to the program. The Dean of Students will be the primary communicator with families regarding student behavior. The Dean will work with families and students to ensure that students get back on track. Students can earn points in 5 areas – attendance, behavior, homework completion, academic performance, and community service. These points are used at the school store and to purchase a monthly school trip. Five Promises – much of the school climate will be derived from this structure that is so successful at Crossroads, another City School. The Five Promises include: Commitment to Quality, Perseverance, Honor and Integrity, Contribution, and No Excuses. These Five Promises are a pledge that the students, parents, and staff strive to live up to throughout the year | Climate Surveys, suspension rates, and Oncourse tracking system Observation of classrooms and community meetings. There should be visible and explicit usage and reinforcement of the Five Promises in all classrooms and structures at CJR | Culture and Climate improved and evident during tours and visits. The school identified this area as one of the visible “quick wins”. Parents and students have made a positive adjustment to the change (ie: learning expectations, processes) The Five Promises strategy is infused throughout the school and is connected to all school activities. Parents are involved with this program. All staff have cohort of approximately 10 students for advisory/morning meeting where they review goal setting and life skills. Community meetings are held weekly for intermediate and middle school students. |
|  | Improve Culture and Climate | The School Leadership Program is a program that establishes the culture of achievement and behavior. Named the Leaders Go Places (LGP), this program assesses students in areas of attendance, homework completion, testing, behavior, and service learning. It sets four levels of achievement that the students are challenged to meet throughout the school year: Bronze, Silver, Gold, and Platinum. This has been a program that has been highly successful at a similar City Schools (Crossroads) because it challenges students to meet levels of excellence in all of the aforementioned categories, and it informs and challenges parents to be informed as well. As students meet benchmarks, they are recognized and rewarded. | Oncourse Data results and tracking which should begin in the Fall of 2010 | The staff uses a merit system which can result in detention (for middle school) which is tracked online. Parents have access to this program. |
|  | Increase Parental and Community Involvement | Home Visits and Frequent Communication with parents are required. CJR staff will dramatically increase parental involvement by conducting home visits with all parents/guardians to begin to develop relationships and expectations. Those expectations will include parental commitment to their student’s progress and Student Led Conferences/ Presentations of Learning that occur throughout the year. Additional support and communication will occur by phone calls home and written reports on student progress. Additionally, a community development team will be meeting with community associations such as Butchers Hill and Johns Hopkins in helping to inform them on the progress of the CJR turnaround. During the summer of 2010, there will be several meet and greet opportunities for parents and the community at the school. | Parental Home Visit documentation/Family and Community Data Collection | The first Wednesday of every month staff makes home contact with families. |
|  | Improve appearance of building and control classroom temperatures/climate Reduce suspensions Improve school image with community Improve school image with community | Currently, LCF is working with Larry Flynn on the implementation of over $1 million in renovations via a non-SIG source to the interior and exterior of CJR. Improvements include: painting of the entire interior, retiling of floors, bathroom repairs, and a total overhaul of the HVAC heating and cooling system. All strategies listed above - also see student profile The Living Classrooms will reduce suspensions and improve achievement - also see student profile The Living Classrooms will increase service learning in neighboring communities. Staff will meet with Butchers Hill and East Baltimore Community Association to determine service learning projects that will enhance local neighborhoods, improve relationships between CJR and the community, and serve students with meaningful, engaging projects. | Visual observation/ documentation Reduce suspensions by 10% in the first year of contract Community feedback Service learning records and Community feedback | They have strategically configured the appearance of the building through painting, floor and ceiling tile replacement, furniture updates, removal and replacement of walls, office lobby reconfigured, air conditioning system upgraded, etc. |
| Student, Family & Community Support | Compile accurate family contact info. Between 35-50% of students’ contact information is incorrect/incomplete . Communicate student academic strategies and progress to families | Living Classrooms will work with City Schools, the City of Baltimore records and local families and communities to identify where our students are living and if they have current phone numbers that we can use to contact them. CJR staff will work with families to develop learning objectives for each student. Regular progress reports will be sent home as well as using phone calls and school visits to inform families regarding progress. Families will be expected to participate in Student Led Conferences and Presentations of Learning throughout the year. Also, parents will participate each trimester in the presentation of their student’s portfolio. The portfolio presentation has been successful at the operator’s other school. (from the Next Steps in the Needs Assessment) | Accurate student records Parent communication logs | The school is striving to maintain emergency contact information for each student. (35 -50% had incorrect contact information). Constant online upgrading of contact information whenever parents visit school.) |
|  | Increase parent involvement Increase Community involvement | Throughout the summer, the school will host summer community gatherings (i.e. barbeques, community association meetings with Butcher’s Hill and Johns Hopkins) twice per month. Through the operator’s volunteer coordinator, Legg Mason personnel have volunteered to help move materials into and around the school to help the school prepare for opening day. The leadership has advertised open office hours to families through flyers sent to homes and for families that do not attend the planned office hours, home visits will be scheduled. (From the Next Steps in the Needs Assessment) CJR will increase parent involvement by hosting regular family-friendly events throughout the year to engage families and students in entertaining and informative sessions about the life of the school. CJR will contact families to request their involvement in the Parent Advisory Council. Currently, the PTO is a weak organization with very few members. We will be working with City Schools to create structures that will bring CJR into compliance with the Family and Community Engagement Policy. CJR will increase community involvement by regular meetings/outreach to the Butcher’s Hill, Johns Hopkins, and other Communities. The school will create a newsletter, which will be distributed to local communities. The school will also actively recruit for volunteer opportunities connected with CJR. | Sign-in sheets at events and parent/community meetings. Meeting agendas, newsletters, and increased volunteerism | Approximately 60% attended summer orientation events and Back to School night had 250 families in attendance. At Back to School night parents could access resources to become volunteers. Parents and students signed commitment forms following orientation sessions. Spanish interpreters were in attendance to facilitate. Fifty families were represented at the first PTO meeting. Nineteen volunteer surveys were turned in. Existing community partnerships will be continued. Space is designated in the building for Butcher’s Hill to encourage community participation. |
| Professional Development | Development of a clear purpose for PD linked to research, student data, and teacher data Development of differentiated PD experiences for each staff member Accountability for professional development implementation Development of common shared language for professional development Shared decision making around Professional Development with teacher input Professional Development Experiences tailored to adult-learning styles Integration of opportunities for follow-up and application Increase professional learning opportunities Improve modeling Improve Data Collection Improve instructional strategies derived from data | 1. Living Classrooms will focus on Goal setting informed by the triangulation of three data points: teacher data, student data, and current research to develop clear goals for professional development experiences that are on-going, connected, and job-embedded. 2. Living Classrooms will focus on Long-term plan for professional development experiences that are focused around developed goals and prioritized by greatest needs . Living Classrooms will create a Professional Development Portfolio –In electronic format, each staff member will identify their own goals in addition to adopting school wide or team wide goals. Sub-goals for each large goal will be outlined and sequenced. PD experiences will be loaded after each occurrence with a rating, reflection, and brief action plan for implementation. Follow up includes space to upload into the electronic portfolio artifacts that evidence the connection between the goals, PD experiences and classroom. 3.Living Classrooms will utilize a variety of accountability measures such as: Action research generated by teachers linked to each professional development experience outlining information learned, next steps for application of the strategy in the classroom, and analysis of implementation. Includes sample of student work to exemplify the implementation Instructional Rounds by all staff focused on implementation of strategies from PD and analysis of effectiveness of implementation, recommendations for next steps for developing skill sets for follow up PD Student Data a variety of student data points, including benchmark data, standardized test data, student work samples, qualitative teacher and student data will be collected and analyzed to determine effectiveness of specific PD. 4.Living Classrooms will engage in Book study groups – selection of professional books aligned with school-wide goals for PD, creation of protocols for interactions in groups, clearly set outcomes, school-wide sharing during PD of main tenants learned from research books to guide school-wide discussion on next steps for possible implementation of ideas learned. Student Work Sample Analysis –by looking at student work, teachers define a commonly shared language and set the parameters for common definitions for what the language introduced in their professional development experiences. 5.Living Classrooms will focus on Teacher Growth Self Assessments – on-going self assessments of teachers’ growth in each competency area in order to guide professional development experiences provided Stake-holder Committee of teachers responsible for outlining PD experiences throughout the school year. Living Classrooms will develop a Professional Development planning template that will frame all professional development activities to ensure they are relevant to school-wide goals, practical in the implementation of strategies immediately, and hands-on in delivery. All PD experiences will mirror expectations for teaching students -taking into account learning styles of participants, attached meaning to real-world experiences, checks for understanding, support, etc. Living Classrooms will focus on On-going PD experiences linked together – experiences will be both sequential as they are prioritized and build from one another, and cyclical in that they will be revisited to build deeper understandings and allow feedback from implementation to guide and shape next steps of the work and define new needs. Action research generated by teachers will be linked to each professional development experience outlining information learned, next steps for application of the strategy in the classroom, and analysis of implementation. Includes sample of student work to exemplify the implementation. Living Classrooms will engage in Differentiated Professional Development Opportunities – Mix of whole group, small group, targeted professional development through workshops, lesson study, book studies, action research, cross-visitation Living Classrooms will use videos of class instruction and Staff Observations Living Classrooms will provide PD on use the benchmarks. Living Classrooms will focus on weekly data analysis informing and improving classroom instruction and differentiation. On August 16th the entire school staff will report and begin PD until school opens and there will be one full week of PD the first week of July. The topics for PD include – data analysis, curriculum mapping, interdisciplinary project planning, school-wide implementation of the discipline plan, learn how to asses student portfolios (students will present their portfolio every trimester and receive a grade, and their parent/guardian must be present), team building and teacher observation protocols.(from the Next Steps in the Needs Assessment) | Professional development goals with supporting relationship to data Long-term scope and sequence of professional development experiences for the entire year Professional Development Electronic Portfolios Teacher action research documents Instructional Rounds Summaries of trends and recommendations of next steps Impact on student achievement through data collection Book study group presentations and subsequent staff recommendations for next steps Collaborative meetings around student work 5.Teacher self assessment survey results PD Committee minutes 6.PD planning template Collection of PD plans for entire year 7.PD long-term plan Teacher Action Research 8.Sign-in sheets and PD plans 9.Videos and notes from observations 10.Regular data collection 11.Data collection records | The school started their delivery of professional development in the summer. The agenda for the professional development was provided. The principal shared that the priority for professional development will be centered on learning to use student data to inform instruction. They will be using benchmark data as well as formative and summative data to review achievement results. Teachers will be expected to participate in collegial classroom visits. Teacher surveys will be revisited four times during the year to assess progress and identify further needs. The long term PD plan was not available. A comprehensive professional development plan will be requested. Documentation was provided on the summer professional development sessions. The focus was curriculum mapping and collaborative team building. |
| Organizational Structure and Resources | Increase teacher collaboration and access to resources | To increase teacher Collaboration, Living Classrooms will utilize a Teacher Collaboration Center that will provide: Professional collaboration space that promotes collegiality and access to both resources of all kinds including human resources Teachers’ personal desks are housed in this center along with their own professional resources Curricular guides, professional books, educational magazines/articles Copiers, poster makers, laminators and a variety of teacher tools Strategy boards: platform to highlight successful strategies linked to goals Cross visitation scheduling board: platform to organize weekly cross visitation between teachers SharePoint Site – electronic platform designed for Grade level/content area teachers to post unit plans daily lesson plans for access and collaboration by others | Existence of Teacher Collaboration Center in School SharePoint Site | The Principal has developed a collaboration center where teachers are expected to meet to plan, share and analyze student data, interact, and support colleagues. |
| Organizational Structure and Resources | Increase Effectiveness of Collaborative Planning time with CFIP: Classroom Focused Improvement Process Extend time on task Develop more public private partnerships | Templates and action plans for collaborative meetings Individual portfolio links Data collection documents for all students. CFIP Strategy – Develop common planning time with grade-level teams or vertical teams who share common assessments one hour/ week Utilize developed CFIP norms and templates to guide meeting discussions Develop questions to answer in data dialogue Notice trends and patterns in students strengths and needs Determine instructional practices that could have contributed to weaknesses and create action plan to address Identified students who excelled and need assistance and develop intervention strategies Identify 1-2 areas of improvement in instruction to implement The Living Classroom will extend the learning day schedule by 10% Partnership with the East Baltimore Mental Health Partnership through Johns Hopkins to provide fulltime mental health counseling to students that include wrap around services Morgan State has been asked to provide tutoring at the school but it has not been finalized. Additionally, the Baltimore City Teacher Leader initiative will be utilized to provide models of exemplary teaching. (From the Next Steps in the Needs Assessment) | CFIP templates used to progress and document the movement of the strategy Master schedule Memorandum of Understanding, SANE | Schedules were provided indicating the new configurations (students attend school from 7:30-3:30 daily). The partnership with John Hopkins has been continued. |
| Organizational Structure and Resources | Improve teacher development through deep reflection processes Teacher Leader Initiative High-Concentration Cluster | Recognized National Board Certified Teacher Development Site – Under MSDE’s guidance a Baltimore NBCT (Dean of Instruction) will coach and mentor 30% of total teaching staff through the NBC process on site Support process will pull from successes of PG County model and other national models that have increased the number of NBCT Baltimore City Teacher Leader Program– 10% of the City’s Teacher Leader force will work as classroom teachers .5 of the school day, providing “Master Teacher” developmental support to other teaching staff. These teachers are successful as evidenced by standardized test data and exemplary model classroom video submissions approved by the Office of Teaching and Learning. Teacher Leaders are tasked with supporting the district during the other .5 of their day with the exception of one half day per week which will be solely focused on supporting teachers and interventions with students on site. | MSDE recognized National Board Certified Teachers – increasing total city’s NBCT population by 25% Data Collection from Teacher Leader impact conducted by Office of Teaching and Learning | The school has hired two National Board Certified teachers and has identified another ten teachers to begin the certification process. |
| Comprehensive and Effective Planning | Assess students Planned interventions Improve attendance Increase safety Increase Overall Parent/Community Satisfaction with CJR Improve reading achievement Improve math achievement Increase special ed. students’ hours in regular classroom settings | All CJR students will have comprehensive, diagnostic testing that occurs in the Fall. This testing will help to identify skill deficiencies that need to be improved upon before students are able to perform grade level work Comprehensive, diagnostic testing will result in education plans for each child. These will be helpful when small group interventions are taking place and will assist with differentiated instruction. Parent/Community support and regular parent communication – see attendance strategies under student profile section School-wide discipline program PBIS Improve achievement, safety, parent involvement and communication – see previous sections Improved instruction and time on task- see student achievement section Improved instruction and time on task - see student achievement section Accelerate learning and improve behavior so students can spend more time in regular classrooms - see student achievement section | Data results Data results Increased attendance to 92.5% for 2010-11 Increase in Climate Survey results for 2010-11 Increase in Climate Survey results for 2010-11 Growth of 1.5 years in reading assessments Growth of 1.5 years in math assessments Spec. Ed. Data records | The school continues to train teachers to administer diagnostic testing to all students (DRA). The school’s schedule includes an acceleration period to provide additional academic support as needed. Principal stated that middle school discipline continues to be a challenge. |
| Effective Leadership | Increase accountability Extended time on task to lengthen instruction | The administrators will monitor collaborative planning sessions in order to learn about student performance and how teachers are adjusting their lesson planning/instruction accordingly. Also, there will be a Collaborative Center in the school where data will be posted and updated every two weeks. Leadership will analyze the data and use the information to inform their learning walks. All formative assessment info will be shared with teachers, leadership, and the Living Classrooms (LCF). This will allow LCF to work with the Principal and Dean of Instruction to hold the school accountable for student achievement, attendance, homework completion, and other important measures that will lead to improved outcomes. LCF will work with City Schools and other funding partners to make available extended learning hours throughout the year. LCF will also explore Saturday learning opportunities as well as summer school options. | Assessment data analysis: daily quizzes and formative assessments Master schedule |  |
|  | Improve oversight of school budget | Monthly meetings with Principal and Operator will be held to review financial records and assess financial needs/concerns. | Budget records | Living Classrooms meets monthly with the principal and oversees the budget. |
|  | Assessment of school leadership | Principal observation and assessment between LCF and City Schools | Principal Evaluation documents | Executive Director who evaluates the principal attended the MSDE SIG First Onsite Monitoring visit of Commodore John Rogers Elementary/Middle School. |
|  | Creation of the Dean of Instruction position | Living Classrooms will hire and develop this individual. All of the SIG schools must undertake the important work of developing new school missions, visions, and shared values. (from the Executive Summary) | Data results | Dean of Instruction is in place. The principal shared the new vision and mission for the school, including their shared beliefs. |