## Table 1
Table 1 | MSDE Questions | Issue Description | Owner | Date Due | Status | Comment
Sect 4.b | How often will they report on their work and the work on Tier I,11, and III schools to Superintendent | Need sign in sheets and notes for CAO November 29 and December 19 2011 meetings with superintendent | Dr. Duane Arbogast/Acting Deputy Superintendent | Ongoing | In Progress | Meetings with Superintendent are confidential; however, we were able to obtain emails verifying meetings took place.
Sect 4.c | How often will they report on their work and the work on Tier I,11, and III schools to Board of Education | Need sign in sheets and agenda for meeting dated Jan 20, 2012 meetings on SIG presentation to system's cabinet members | E. Ryans and Myra G. | Ongoing | In Progress | Compliance Specialist will ensure that all future meetings are documented with a sing-in sheet and an agenda.
Sect 4.f | What steps will the LEA take to ensure that the school improvement funds are utilized (1) in a timely way and (2) effectively and efficiently to support the required components of the selected intervention? Specifically, what assurances will the LEA make that schools and LEA support teams have access to these funds, even during annual rollover processes? How will the LEA support principals’ timely and effective use of these funds? | MSDE believes as of this time of the year the funding percentages should be higher | E. Ryans | Ongoing | In Progress | The original 1003g yearly budget developed at the inception of the grant, did not meet the needs of the schools. Due to the extensive amount of amendments processed over the past 2 years, a 100 day planning process was developed to allow for timelier spend down of funds and reduce the needs of future amendents. The Turnaround Office Compliance Specialist worked closely with each school to develop a budget. During the process, the compliance specialist collaborated with the assigned budget specialist to ensure all line items and explanations were consistent with the spirit of the grant and met appropriate guidelines. [Programmatic amendments were created, when appropriate.]
OTHER ACTION STEPS:
1. To monitor the spend-down of the grant, monthly SIG Budget meetings will occur facilitated by the district’s Chief Financial Officer.
2. Danielle Curtis, Cynthia Moore, and Myra G will collaborate to provide monthly statements to each school and the turnaround office to advise of remaining balances.
3. The Chief Financial Officer (CFO) has reorganized his division to provide an additional layer of support for all grants within the district. The CFO has aligned budget analysts and accountants into one unit that will report to the Director of Finance and Treasury Operations. This is the first step to increase the division’s ability to support grant program managers to strategically plan and spend grant dollars within the specified time-frame.
4. The 1003g SIG application has been revised and updated to more accurately reflect current initiatives in the schools.
5. Each school will identify a dedicated Accountability Portfolio Manager who will be responsible for maintaining school-based documentation as it relates to the SIG requirements. The compliance specialist with provide ongoing technical assistance to each school’s accountability portfolio manager to ensure that all S.A.N.E. documentation is collected on a regular basis.

## TABLE 3-6
Req. # | Comp.# | Name of School | Issue Description | Findings | What needs to be done | By whom | By when | Status (Not Started, In Progress, Complete) | Comments
1a. | 1 | Benjamin Stoddert MS | Replace the principal & grant the principal sufficient operational flexibility (including staffing, calendars/time, and budgeting) to implement fully a comprehensive approach in order to substantially improve student achievement outcomes and increase high school graduation rates | Documentation for principal screening was not provided, as outlined in the plan | Documentation must be maintained for principal screening, as outlined in the plan. | Myra G | Complete | Complete | Documentation for initial prinipal screening (Summer 2010) has been obtained from HR and is now available for MSDE.
1b. | 1 | Benjamin Stoddert MS | Replace the principal & grant the principal sufficient operational flexibility (including staffing, calendars/time, and budgeting) to implement fully a comprehensive approach in order to substantially improve student achievement outcomes and increase high school graduation rates | New principals visited Harlem Children Zone, but the sign-in sheets was not provided. | Sign-in sheets must be maintained for new principals who visit the Harlem Children Zone. | E. Ryans | Ongoing | In Progress | Do not have - can provide travel information as evidence of attendance; future travel will be set up in ERO, participants will register, and a sign-in sheet will be sent with the team
3b. | 3 | Benjamin Stoddert MS | Implement such strategies as financial incentives, increased opportunities for promotion and career growth, and more flexible work conditions that are designed to recruit, place, and retain staff with the skills necessary to meet the needs of the students in the turnaround school | Instructional Lead Teachers (ILTS) are still in the bargaining unit. Union will not agree for them to receive incentive stipends. | This language was prematurely inserted into the 1003g grant application. PGCPS has finally reached an agreement with PGCEA; ILT's are part of PGCEA so they will receive the same incentive stiped as teachers. | E. Ryans | by December 31, 2012 | In Progress | After further discussions with PGCEA, an agreement on teacher incentives has been reached; "offer letters" have been signed by all PGCEA employees; ILT's are part of PGCEA so they will receive the same incentive stiped as teachers
3e. | 3 | Benjamin Stoddert MS | Implement such strategies as financial incentives, increased opportunities for promotion and career growth, and more flexible work conditions that are designed to recruit, place, and retain staff with the skills necessary to meet the needs of the students in the turnaround school | No sign-in sheets for November 28th meeting for the Aspiring Principals Institute conducted by MSDE. | Provide sign-in sheets for November 28th meeting. | Myra G | Received August 23, 2012 | Complete | Requested and received from Paul Dunford and Tom DeHart
3f. | 3 | Benjamin Stoddert MS | Implement such strategies as financial incentives, increased opportunities for promotion and career growth, and more flexible work conditions that are designed to recruit, place, and retain staff with the skills necessary to meet the needs of the students in the turnaround school | There were no opening for outside teachers due to reduction in force of teachers. | Hiring of staff was significantly impacted by the Reduction in Force (RIF) that occurred in PGCPS last year (2011-2012). As a result of the negotiated agreement as it applies to RIF, schools were not afforded the luxury of a comprehensive screening process for the hiring/removal of staff. | E. Ryans | Ongoing | In Progress | Staffing continues to be an ongoing process. A much-improved relationship with Human Resources along with the assignment of a Staffing Specialist (Tiffany Bascomb) has resulted in a shift from a “placement” mentality to one of collaboration with schools. In most cases, principals were able to negotiate for “best fit” candidates, when openings were available.
4a. | 4 | Benjamin Stoddert MS | Provide staff with on-going, high-quality, job-embedded professional development that is aligned with the school's comprehensive instructional program and designed with school staff to ensure that they are equipped to facilitate effective teaching and learning and have the capacity to successfully implement school reform strategies | No evidence of sign-in and agendas for: - Research for Better Teaching training in the building; - In-School Support/Coaching for Teachers and/or Teacher Teams (10 days on-site per school); - Leadership Development/Leadership Seminars to improve Teaching and Learning (8 days on-site per school); and - Observation, Program Development and Leadership Support Days (8 days for leadership work per school; 4 days for program coordination/support for whole groups sessions) | Instructional Resource Teacher's (IRT) mid-year progress report must show that mentoring services were provided by newly created positions. This should include the types of descriptions and mentoring. | TA Instructional Specialists, Myra G | Ongoing | In Progress | The compliance specialist will provide ongoing technical assistance to the accountability portfolio manager to ensure proper documentation is maintained.
4a. | 4 | Benjamin Stoddert MS | Provide staff with on-going, high-quality, job-embedded professional development that is aligned with the school's comprehensive instructional program and designed with school staff to ensure that they are equipped to facilitate effective teaching and learning and have the capacity to successfully implement school reform strategies | Sign-in sheets for St. Michael's retreat were not provided. | Sign-in sheets must be maintained for any future retreats. | Myra G | Ongoing | Complete | Leadership Retreat occurred June 25-27, 2012; sign-in sheets are available; future conferences will be set up in ERO, participants will register, and a sign-in sheet will be sent with the team
5c. | 5 | Benjamin Stoddert MS | Adopt a new governance structure, which may include, but is not limited to, requiring the school to report to a new "turnaround office" in the LEA or SEA, hire a "turnaround leader" who reports directly to the Superintendent or Chief Academic Officer, or enter into a multi-year contract with the LEA or SEA to obtain added flexibility in exchange for greater accountability | Funds were not spent to create Parent Involvement Room in the SIG I School. | To create a Parent Involvement Room in the SIG I School using the budgeted funds. | Year 2, Amendment #4 was submitted and approved removing this language from the grant | Complete | Complete | Year 2, Amendment #4 was submitted and approved removing this language from the grant
5e. | 5 | Benjamin Stoddert MS | Adopt a new governance structure, which may include, but is not limited to, requiring the school to report to a new "turnaround office" in the LEA or SEA, hire a "turnaround leader" who reports directly to the Superintendent or Chief Academic Officer, or enter into a multi-year contract with the LEA or SEA to obtain added flexibility in exchange for greater accountability | Co-observation is not taking place as written. Amendment is pending. | To co-observate according to the written plan. This action is pending approval. | An amendment was submitted removing this langauge from the grant | Complete | Complete | An amendment was submitted removing this langauge from the grant (Year 2, Amendment #4)
5h. | 5 | Benjamin Stoddert MS | Adopt a new governance structure, which may include, but is not limited to, requiring the school to report to a new "turnaround office" in the LEA or SEA, hire a "turnaround leader" who reports directly to the Superintendent or Chief Academic Officer, or enter into a multi-year contract with the LEA or SEA to obtain added flexibility in exchange for greater accountability | Sign-in sheet and notes missing from Harlem Visit. | Sign-in sheet(s) and notes must be maintained for future Harlem Visit(s). | E. Ryans | See comments. | In Progress | Do not have - can provide travel information as evidence of attendance; future travel will be set up in ERO, participants will register, and a sign-in sheets will be sent with the team to meetings.
6d. | 6 | Benjamin Stoddert MS | Use data to identify and implement an instructional program that is research-based and "vertically aligned" from one grade to the next as well as aligned with State academic standards | There is no evidence that the district is providing training and evaluation of success for Key Elements to Mathematics Success (KEMS) and Key Elements to Algebra Success (KEAS) for 2011-2012. | Trainings held in the large conference rooms such as AVID, the participants would initial and date on their participation list (s). The SANE documents for AVID Team Meeting(s) in school is maintained. | Myra G | Complete | Complete | Summer 2012 - participants registered in ERO and sign-in sheets were sent with school teams
6i. | 6 | Benjamin Stoddert MS | Use data to identify and implement an instructional program that is research-based and "vertically aligned" from one grade to the next as well as aligned with State academic standards | Student selection criteria for STEM classes were not provided, just a hand written note listing the criteria was provided (MSA math scores, math/science grades, teacher recommendations, honor designation). | The student selection criteria for STEM classes must be maintained. | Myra G | Ongoing | In Progress
6j & m. | 6 | Benjamin Stoddert MS | Use data to identify and implement an instructional program that is research-based and "vertically aligned" from one grade to the next as well as aligned with State academic standards | Invoices and inventory control sheet were not provided. | Invoices and inventory control sheet(s) must be maintained. | C. Moore and Myra G | By December 31, 2012 | In Progress | Inventory of SIG-purchased equipment, etc has been added as a document needed in the Accountability Portfolios for schools
6k-l. | 6 | Benjamin Stoddert MS | Use data to identify and implement an instructional program that is research-based and "vertically aligned" from one grade to the next as well as aligned with State academic standards | Funds for Media Center and Interactive Learning Lab for students were reallocated to summer leadership retreat at St. Michael's. Funds were already spent in summer 2011. Amendment is pending. | Prior approval is needed before funds are spent on unbudgeted expenses. This request is pending approval. | Myra G | Complete | Complete | This activity was included in SIG I, Year 1 Amendment #7
7d-e. | 7 | Benjamin Stoddert MS | Promote the continuous use of student data (such as from formative, interim, and summative assessments) to inform and differentiate instruction in order to meet the academic needs of individual students | There is no ESOL program in the building (no ESOL teachers); however, school staff shared that there are 4 ELL students, all have BASIC Score outcomes. Following the on-site visit, the Turnaround Office reported that there are no ESOL students in the school. They are being served at a regional center. | There must be some ESOL students enrolled in the school instead of the regional center. | Principal and PGCPS ESOL department | Ongoing | In Progress | ESOL teacher assignment is a PGCPS decision and is based on student enrollment.
8d. | 8 | Benjamin Stoddert MS | Establish schedules and implement strategies that provide increased learning time | Parent Forum during August Academy did not take place. | Parent Forum(s) must take place. | Myra G | Complete | Complete | This year's August Academy (2012) included a parent event
8e. | 8 | Benjamin Stoddert MS | Establish schedules and implement strategies that provide increased learning time | School day not extended due to Union issues. | While the original intent of the 1003g grant was to extend the school day by 60 minutes; collective bargaining (union) issues prevented this from occurring as planned; however, each turnaround school offered an ELO program to students. | E. Ryans | Complete | Complete | For 2012-2013, PGCPS extended the school day for all middle schools by 40 minutes
9a. | 9 | Benjamin Stoddert MS | Provide appropriate social-emotional and community -oriented services and supports for students | No evidence showing parent meetings. | Parent meetings must be documented. | Myra G | Ongoing | In Progress | Compliance Specialist is providing ongoing technical assistance to school and MAEC staff
9c. | 9 | Benjamin Stoddert MS | Provide appropriate social-emotional and community -oriented services and supports for students | No evidence of implementation of PBIS with fidelity during the school year. | PBIS implementation during the school year must be documented. | Myra G | Ongoing | In Progress
9e. | 9 | Benjamin Stoddert MS | Provide appropriate social-emotional and community -oriented services and supports for students | No evidence of funds spent for Parent Engagement area. | Funds spent for Parent Engagement must be documented. | Myra G | Complete | Complete | Year 2, Amendment #4 was submitted and approved removing this language from the grant.
9e. | 9 | Benjamin Stoddert MS | Provide appropriate social-emotional and community -oriented services and supports for students | No SANE documents for parent meetings except for Back to School Night. | Parent Meetings items (S.A.N.E = sign-in sheets, agendas, notes, and evaluations) must be maintained. | Myra G | Ongoing | In Progress | Compliance Specialist is providing ongoing technical assistance to school and MAEC staff
9l. | 9 | Benjamin Stoddert MS | Provide appropriate social-emotional and community -oriented services and supports for students | Student Advocate positions' "employment letter" was provided. However, the documents were only for part-time employment with 15 hours/week 9 (dated, Nov. 21, 2011) instead of the full-time positions as indicated in the plan. | All Student Advocate positions' (full-time and part-time) "employment letter/documents" must be maintained as indicated in the plan. | N/A | Complete | Complete | This feedback is an error. The employment letter cited indicated full-time (MSDE team misread the letter).
1a.III-V | 1 | Drew Freeman MS | Replace the principal & grant the principal sufficient operational flexibility, including staffing, calendars/time, and budgeting to implement fully a comprehensive approach in order to substantially improve student achievement outcomes and increase high school graduation rates. | No documentation related to interview, selection, final review, and nominees for Superintendent. | Human Capital needs to provide report on the # of applicants, etc. | Myra G | Complete | Complete
1b.II | 1 | Drew Freeman MS | Replace the principal & grant the principal sufficient operational flexibility, including staffing, calendars/time, and budgeting to implement fully a comprehensive approach in order to substantially improve student achievement outcomes and increase high | No documentation of collaborative planning sessions with the new Turnaround Director and MSDE leadership office to finalize the LEA proposal. | Provide documentation. | E. Ryans | Ongoing | In Progress | Turnaround Director was hired after LEA proposal was approved. Once on board, however, the turnaround director has worked with the SIG I principals to modify and amend the SIG plan to meet the needs of the schools. This has evolved into an extensive 100-day planning process allowing principals to individualize their SIG plan to include budget allocation requests.
1b.II | 1 | Drew Freeman MS | Replace the principal & grant the principal sufficient operational flexibility, including staffing, calendars/time, and budgeting to implement fully a comprehensive approach in order to substantially improve student achievement outcomes and increase high school graduation rates. | Program grant amendment request noted because negotiations failed to get three year commitment for teaching at turnaround schools but has not been received. | Provide amendment request. | E. Ryans | Complete | Complete | Year 2, Amendment #2 removed this language from the grant
2a.II | 2 | Drew Freeman MS | Use locally adopted competencies to measure the effectiveness of staff who can work within the turnaround environment to meet the needs of students A) Screen all existing staff and rehire no more than 50 percent; and B) Select new staff. | No evidence of screening according to local measures due to Reduction in Force (RIF). Selection process could not be determined. | Provide evidence of screening according to local measures due to RIF, as well as provide evidence of selection process. | E. Ryans | Ongoing | In Progress | Hiring of staff was significantly impacted by the Reduction in Force (RIF) that occurred in PGCPS last year (2011-2012). As a result of the negotiated agreement as it applies to RIF, schools were not afforded the luxury of a comprehensive screening process for the hiring/removal of staff. Request has been made to HR for documentaiton from summer 2012 hiring efforts.
2a.III | 2 | Drew Freeman MS | Use locally adopted competencies to measure the effectiveness of staff who can work within the turnaround environment to meet the needs of students A) Screen all existing staff and rehire no more than 50 percent; and B) Select new staff. | No evidence of including screening measures related to increasing student achievement in interviews, rubrics, etc.. | Determine selection process. | E. Ryans | By October 1, 2012 | In Progress | Hiring of staff was significantly impacted by the Reduction in Force (RIF) that occurred in PGCPS last year (2011-2012). As a result of the negotiated agreement as it applies to RIF, schools were not afforded the luxury of a comprehensive screening process for the hiring/removal of staff. Request has been made to HR for documentaiton from summer 2012 hiring efforts.
2a.III | 2 | Drew Freeman MS | Use locally adopted competencies to measure the effectiveness of staff who can work within the turnaround environment to meet the needs of students A) Screen all existing staff and rehire no more than 50 percent; and B) Select new staff. | Due to RIF, selection process could not be implemented. | Determine selection process. | E. Ryans | Ongoing | In Progress | Hiring of staff was significantly impacted by the Reduction in Force (RIF) that occurred in PGCPS last year (2011-2012). As a result of the negotiated agreement as it applies to RIF, schools were not afforded the luxury of a comprehensive screening process for the hiring/removal of staff. Request has been made to HR for documentaiton from summer 2012 hiring efforts.
3b. | 3 | Drew Freeman MS | Implement such strategies as financial incentives, increased opportunities for promotion and career growth, and more flexible work conditions that are designed to recruit, place, and retain staff with the skills necessary to meet the needs of the students in the turnaround school. | Annual incentives for Instructional Lead Teachers (ILT's) could not be negotiated and was never submitted for approval so a grant amendment is needed to remove this item | submit amendment to provide annual incentives for ILTs. | E. Ryans | by December 31, 2012 | In Progress | After further discussions with PGCEA, an agreement on teacher incentives has been reached; "offer letters" have been signed by all PGCEA employees; ILT's are part of PGCEA so they will receive the same incentive stiped as teachers
3c. | 3 | Drew Freeman MS | Implement such strategies as financial incentives, increased opportunities for promotion and career growth, and more flexible work conditions that are designed to recruit, place, and retain staff with the skills necessary to meet the needs of the students in the turnaround school. | Non-financial incentives for teachers have not been negotiated as of yet; therefore, implementation has not occurred. | Provide process for addressing non-financial incentives for teachers to be negotiated. | E. Ryans | Ongoing | Complete | The PGCEA "offer letter" addresses the non-financial incentives, i.e. paid PD, paid registration to conferences, etc.
4a.II-IV | 4 | Drew Freeman MS | Provide staff with ongoing, high quality, job-embedded professional development that is aligned with the school's comprehensive instructional program and designed with school staff to ensure that they are equipped to facilitate effective teaching and learning and have the capacity to successfully implement school reform strategies. | No S.A.N.E documents (sign-in sheets, agendas, notes, and evaluations) to make the distinction between coaching meetings, leadership development, and support days. | Provide documentation to discern between coaching meetings, leadership development, and support days. | Myra G | Ongoing | In Progress | The compliance specialist will provide ongoing technical assistance to the accountability portfolio manager to ensure proprer documentation is maintained.
5e.V | 5 | Drew Freeman MS | Adopt a new governance structure, which may include, but is not limited to, requiring the school to report to a new "turnaround office" in the LEA or SEA, hire a "turnaround leader" who reports directly to the Superintendent or Chief Academic Officer, or enter into a multi-year contact with the LEA or SEA to obtain added flexibility in exchange for greater accountability | No documentation of Turnaround Director in attendance at school leadership team meeting. | Provide evidence of Turnaround Director's attendance at school leadership team meeting. | E. Ryans | Ongoing | In Progress | An amendment has been submitted and is pending approval revising the language of this item.
5i. | 5 | Drew Freeman MS | Adopt a new governance structure, which may include, but is not limited to, requiring the school to report to a new "turnaround office" in the LEA or SEA, hire a "turnaround leader" who reports directly to the Superintendent or Chief Academic Officer, or | No documentation of collaboration in the topic areas of student, family, and community support. | Provide documentation of the collaboration in these topic areas..Additionally, an amendment is needed as these activities are being addressed by the MAEC partnership. | Mid-Atlantic | Complete | Complete | Mid-Atlantic is our contracted parent engagement partner; they were added via an amendment in year 2
5i. | 5 | Drew Freeman MS | Adopt a new governance structure, which may include, but is not limited to, requiring the school to report to a new "turnaround office" in the LEA or SEA, hire a "turnaround leader" who reports directly to the Superintendent or Chief Academic Officer, or | An amendment is needed as these activities are being addressed by the MAEC. | Provide process to produce amendment to address this issue. | E. Ryans | Complete | Complete | Mid-Atlantic is our contracted parent engagement partner; they were added via an amendment in year 2
6j. | 6 | Drew Freeman MS | Use data to identify and implement an instructional program that is researched-based and "vertically aligned" from one grade to the next as well as aligned with State academic standards. | AV carts with locking cabinet, math manipulative, and multi-media game show were not ordered. | Provide process to place orders. | C. Moore and Myra G | by December 31, 2012 | In Progress | Inventory of SIG-purchased equipment, etc has been added as a document needed in the Accountability Portfolios for schools
6k. | 6 | Drew Freeman MS | Use data to identify and implement an instructional program that is researched-based and "vertically aligned" from one grade to the next as well as aligned with State academic standards. | Classroom library upgrades have not been ordered. | Provide process for ordering library upgrades. | C. Moore | By October 31, 2012 | In Progress
8d. | 8 | Drew Freeman MS | Establish schedules and implement strategies that provide increased learning time. | No documentation of diagnostic assessment component of August Academy. | Provide documentation of diagnostic assessment component of August Academy. | Principal | Ongoing | In Progress | Students matriculate with assessment information from the elementary school; school primarily addresses climate and culture during the August Academy
3b | 3 | G. James Gholson MS | Implement such strategies as financial incentives, increased opportunities for promotion and career growth, and more flexible work conditions that are designed to recruit, place, and retain staff with the skills necessary to meet the needs of the students in the turnaround school | No agreement with union and PGCPS regarding stipends for staff (amendment pending). | MSDE suggests PGCPS explore creative incentives with extended year via summer school. | E. Ryans | Ongoing | In Progress | After further discussions with PGCEA, an agreement on teacher incentives has been reached; "offer letters" have been signed by all PGCEA employees; ILT's are part of PGCEA so they will receive the same incentive stiped as teachers
4a | 4 | G. James Gholson MS | Implement such strategies as financial incentives, increased opportunities for promotion and career growth, and more flexible work conditions that are designed to recruit, place, and retain staff with the skills necessary to meet the needs of the students in the turnaround school | No evidence of Research for Better Teaching’s April meeting. (Agenda and attendee list were not provided.) | The missing evidence is available but was in the LEA binder; the school did not have its own copy. | E. Ryans and Myra G. | Ongoing | In Progress | The compliance specialist will provide ongoing technical assistance to the accountability portfolio manager to ensure proprer documentation is maintained.
6d | 6 | G. James Gholson MS | Use data to identify and implement an instructional program that is research-based and “vertically aligned” from one grade to the next as well as aligned with State academic standards | Amendment pending for Algebra goal. | It was determined that the original Algebra goal of 100% was unrealistic (especially since PGCPS' goal is only 75%). An amendment was submitted and approved removing this language from the grant. | E. Ryans | Complete | Complete | Year 2, Amendment #3 was submitted and approved
6i | 6 | G. James Gholson MS | Use data to identify and implement an instructional program that is research-based and “vertically aligned” from one grade to the next as well as aligned with State academic standards | No evidence of the teacher 2-week professional development for Project Lead the Way. | Teacher was unable to produce the official training certificate; however, attendance was verified through UMBC. | Principal | Ongoing | In Progress | Teacher was unable to produce the official training certificate; however, attendance was verified through UMBC.
6j | 6 | G. James Gholson MS | Use data to identify and implement an instructional program that is research-based and “vertically aligned” from one grade to the next as well as aligned with State academic standards | No evidence of technology embedded instruction for students. | For 2012-2013, each school will be required to complete and submit a Technology Plan as evidence of technology embedded instruction | Myra G | by October 31, 2012 | In Progress | Each school will be required to complete and submit a Technology Plan as evidence of technology embedded instruction
6k | 6 | G. James Gholson MS | Use data to identify and implement an instructional program that is research-based and “vertically aligned” from one grade to the next as well as aligned with State academic standards | No evidence of use of classroom library books. | Each school will be required to complete and submit a Technology Plan; evidence of classroom library use will be a line item. | Myra G | by October 31, 2012 | In Progress | Each school will be required to complete and submit a Technology Plan; evidence of classroom library use will be a line item.
8a | 8 | G. James Gholson MS | Establish schedules and implement strategies that provide increased learning time | No evidence of extended day by 60 minutes | While the original intent of the 1003g grant was to extend the school day by 60 minutes; collective bargaining (union) issues prevented this from occurring as planned; however, each turnaround school offered an ELO program to students. | N/A | Complete | Complete | For 2012-2013, PGCPS extended the school day for all middle schools by 40 minutes
8e | 8 | G. James Gholson MS | Establish schedules and implement strategies that provide increased learning time | No documentation of extended instructional time | The compliance specialist will provide ongoing technical assistance to the ELO coordinator to ensure proprer documentation is maintained. | Myra G | Ongoing | In Progress | The compliance specialist will provide ongoing technical assistance to the ELO coordinator to ensure proprer documentation is maintained.
9j | 9 | G. James Gholson MS | Provide appropriate social-emotional and community-oriented services and supports for students | No documentation for the position of the second student advocate position | Working with HR to ensure all positions are filled | E. Ryans and Myra G. | By October 1, 2012 | In Progress | 1003g-funded positions will be verified once the final position printout is available for HR; any inaccuracies will be addressed at that time
1b | 1 | Thurgood Marshall MS | Replace the principal and grant the principal sufficient operational flexibility (including in staffing, calendars/time, and budgeting) to implement fully a comprehensive approach in order to substantially improve student achievement outcomes and increase high school graduation rates | Need sign in sheets from Harlem Children Zone conference or some evidence of participation. | Sign-in sheets needed or other verification of participation. Contact to Harlem Children Zone for any check-in log/documentation of attendance | E. Ryans | Ongoing | In Progress | Do not have - can provide travel information as evidence of attendance; future travel will be set up in ERO, participants will register, and a sign-in sheet will be sent with the team
4c | 4 | Thurgood Marshall MS | Provide staff with ongoing, high-quality, job-embedded professional development that is aligned with the school’s comprehensive instructional program and designed with school staff to ensure that they are equipped to facilitate effective teaching and learning and have the capacity to successfully implement school reform strategies | Professional Development (PD) not held due to late assignment of the principal. | Plan & provide PD, provide sign-in sheets, agenda | Myra G | By September 15, 2012 | In Progress | Copies of all sign-in sheets (Turnaround Summer Symposium - 2011) can be provided; School has conducted extensive PD (summer 2012) and documentation is available
4d | 4 | Thurgood Marshall MS | Provide staff with ongoing, high-quality, job-embedded professional development that is aligned with the school’s comprehensive instructional program and designed with school staff to ensure that they are equipped to facilitate effective teaching and learning and have the capacity to successfully implement school reform strategies | Funds were diverted from school and classroom library up-grades. Summer workshops were not held. | Provide justification for funds, request approval for moving. Plan workshops to occur during current school year. | Myra G | By October 1, 2012 | In Progress | Summer 2012 - many workshops were held and more are scheduled; ERO documentaiotn is available
5c | 5 | Thurgood Marshall MS | Adopt a new governance structure, which may include, but is not limited to, requiring the school to report to a new “turnaround office” in the LEA or SEA, hire a “turnaround leader” who reports directly to the Superintendent or Chief Academic Officer, or enter into a multi-year contract with the LEA or SEA to obtain added flexibility in exchange for greater accountability | No documentation of school inventory shared. | Documentation of school inventory | C. Moore and Myra G | by December 31, 2012 | In Progress | Inventory of SIG-purchased equipment, etc has been added as a document needed in the Accountability Portfolios for schools
5e | 5 | Thurgood Marshall MS | Adopt a new governance structure, which may include, but is not limited to, requiring the school to report to a new “turnaround office” in the LEA or SEA, hire a “turnaround leader” who reports directly to the Superintendent or Chief Academic Officer, or enter into a multi-year contract with the LEA or SEA to obtain added flexibility in exchange for greater accountability | Co-observation was not taking place as written. Amendment is pending. | Amendment was submitted removing this langauge from the grant | E. Ryans and Myra G. | Pending approval | Complete | An amendment was submitted (and is pending approval) removing this langauge from the grant
5e | 5 | Thurgood Marshall MS | Adopt a new governance structure, which may include, but is not limited to, requiring the school to report to a new “turnaround office” in the LEA or SEA, hire a “turnaround leader” who reports directly to the Superintendent or Chief Academic Officer, or enter into a multi-year contract with the LEA or SEA to obtain added flexibility in exchange for greater accountability | Missing evidence – notes & sign-in sheet for the August 11, 2011 meeting. | Provide documentation | E. Ryans | Unsure how to complete this task | Not Started | Do not have; Compliance Specialist will ensure that all meetings are documented with a sing-in sheet and an agenda
5e | 5 | Thurgood Marshall MS | Adopt a new governance structure, which may include, but is not limited to, requiring the school to report to a new “turnaround office” in the LEA or SEA, hire a “turnaround leader” who reports directly to the Superintendent or Chief Academic Officer, or enter into a multi-year contract with the LEA or SEA to obtain added flexibility in exchange for greater accountability | Provide documentation that teachers were evaluated properly and provided meaningful feedback on their work | Obtain evaluations from HR | E. Ryans | By October 1, 2012 | In Progress | Final Evaluatons will be requested from HR and placed in accountability portfolio (pending confidentiality issues)
5g | 5 | Thurgood Marshall MS | Adopt a new governance structure, which may include, but is not limited to, requiring the school to report to a new “turnaround office” in the LEA or SEA, hire a “turnaround leader” who reports directly to the Superintendent or Chief Academic Officer, or enter into a multi-year contract with the LEA or SEA to obtain added flexibility in exchange for greater accountability | The meetings do not include school team members – provide documentation of Turnaround steering committee meetings (multi-disciplinary team) that includes the members of TMMS School Team to monitor progress. | Include all required members, provide sign-in sheets and agendas | E. Ryans | Monthly beginning September 24, 2012 | In Progress | Beginning January 2012, principals began attending Turnaround Executive Committee meetings
5g | 5 | Thurgood Marshall MS | Adopt a new governance structure, which may include, but is not limited to, requiring the school to report to a new “turnaround office” in the LEA or SEA, hire a “turnaround leader” who reports directly to the Superintendent or Chief Academic Officer, or enter into a multi-year contract with the LEA or SEA to obtain added flexibility in exchange for greater accountability | Turnaround Steering Committee is now known as the Turnaround Executive Committee (TEC). TEC meets as a district-wide entity, the principal is a part of the leadership team; however, the team does not meet with schools individually. | Re-evaluate & plan how the team can meet with schools during Committee meetings | E. Ryans | on-going | In Progress | Beginning January 2012, principals began attending Turnaround Executive Committee meetings; however, meeting with each school individually is not a specific requirement of the grant.
5h | 5 | Thurgood Marshall MS | Adopt a new governance structure, which may include, but is not limited to, requiring the school to report to a new “turnaround office” in the LEA or SEA, hire a “turnaround leader” who reports directly to the Superintendent or Chief Academic Officer, or enter into a multi-year contract with the LEA or SEA to obtain added flexibility in exchange for greater accountability | Dec. 14-15, 2011 visit to the Harlem’s Children Zone - Sign-in sheet and notes were not available for the Harlem Visit. | Sign-in sheets needed or other verification of participation. Contact to Harlem Children Zone for any check-in log/documentation of attendance | E. Ryans | Ongoing | In Progress | Do not have - can provide travel information as evidence of attendance; future travel will be set up in ERO, participants will register, and a sign-in sheet will be sent with the team
5i | 5 | Thurgood Marshall MS | Adopt a new governance structure, which may include, but is not limited to, requiring the school to report to a new “turnaround office” in the LEA or SEA, hire a “turnaround leader” who reports directly to the Superintendent or Chief Academic Officer, or enter into a multi-year contract with the LEA or SEA to obtain added flexibility in exchange for greater accountability | Provide documentation that Turnaround Director is working collaboratively with the director of Cross-Divisional Initiatives to support the LEA Director during the current 2011-2012 school year. | Provide documentation | E. Ryans | By October 15, 2012 | In Progress | Documentation has been requested (Paul Dunford, MSDE)
6i | 6 | Thurgood Marshall MS | Use data to identify and implement an instructional program that is research-based and “vertically aligned” from one grade to the next as well as aligned with State academic standards | Agenda for AVID site team meetings with dates. | Provide Agendas | Myra G | Ongoing | In Progress | Compliance Specialist is providing ongoing technical assistance to school to ensure documentaiton is being maintained
6i | 6 | Thurgood Marshall MS | Use data to identify and implement an instructional program that is research-based and “vertically aligned” from one grade to the next as well as aligned with State academic standards | AVID pre-planning stages—initialed list of attendees and daily agendas needed. | Provide documentation | Myra G | Complete | Complete | AVID Conference (summer 2012) plus school conducted summer AVID planning
6j | 6 | Thurgood Marshall MS | Use data to identify and implement an instructional program that is research-based and “vertically aligned” from one grade to the next as well as aligned with State academic standards | Evidence of advertised Math position-- interview panel, dates, times, etc., but the position is still vacant | Work with HR to advertise and fill position | E. Ryans and Myra G. | Complete | Complete | Employment letter and job posting available
6l | 6 | Thurgood Marshall MS | Use data to identify and implement an instructional program that is research-based and “vertically aligned” from one grade to the next as well as aligned with State academic standards | SIG funds were to be redirected to a summer leadership retreat to St .Michaels, but due to the late assignment of the principal to the school, the retreat did not take place. | Identify a date and plan retreat | Myra G | Complete | Complete | Leadership Retreat occurred June 25-27, 2012; sign-in sheets are available
6m | 6 | Thurgood Marshall MS | Use data to identify and implement an instructional program that is research-based and “vertically aligned” from one grade to the next as well as aligned with State academic standards | Never purchased new instructional programs to be housed in the media center or classrooms. | Purchase instructional programs through Oracle, provide documentation & file Pos | E. Ryans | Complete | Complete | Funds were redirected in Amendment #9 (year 1)
6n | 6 | Thurgood Marshall MS | Use data to identify and implement an instructional program that is research-based and “vertically aligned” from one grade to the next as well as aligned with State academic standards | According to the District, the labs are purchased and in use, but no invoice or inventory control sheet was presented | Inventory all equipment & tag | C. Moore and Myra G | by December 31, 2012 | In Progress | Inventory of SIG-purchased equipment, etc has been added as a document needed in the Accountability Portfolios for schools
7e | 7 | Thurgood Marshall MS | Promote the continuous use of student data (such as from formative, interim, and summative assessments) to inform and differentiate instruction in order to meet the academic needs of individual students | Waiting on documentation from Turnaround Office for the technology upgrade | Provide documentation | N/A | Complete | Complete | Funds were redirected in Amendment #9 (year 1)
7h | 7 | Thurgood Marshall MS | Promote the continuous use of student data (such as from formative, interim, and summative assessments) to inform and differentiate instruction in order to meet the academic needs of individual students | No evidence of the ELL teacher working with core academic teachers was presented. | Provide documentation | Principal and PGCPS ESOL department | Ongoing | In Progress | Pending number of ESOL students and percentage of an ESOL teacher assigned to the school.
8a | 8 | Thurgood Marshall MS | Establish schedules and implement strategies that provide increased learning time | Documentation of purchases of instruments, etc. was not presented. | Retrieve Oracle POs Setup binder with all purchase orders | C. Moore | By October 31, 2012 | In Progress
8b | 8 | Thurgood Marshall MS | Establish schedules and implement strategies that provide increased learning time | Turnaround document indicates ELO was to begin in October but started ELO program in December. | Provide justification for late start | E. Ryans | Complete | Complete | 2012-2013 ELO will begin on October 1.
8c | 8 | Thurgood Marshall MS | Establish schedules and implement strategies that provide increased learning time | Summer Academy will be hosted this summer for TMMS. | Provide copy of documentation & materials | Myra G | Complete | Complete | August Academy was held on August 7-9
8c | 8 | Thurgood Marshall MS | Establish schedules and implement strategies that provide increased learning time | Amendment will be submitted for use of 2011 academy monies will be used for 2012 summer academy. | File Amendment request & approval | E. Ryans and Myra G. | Complete | Complete | SIG I, Year 2 Amendment #4
8d | 8 | Thurgood Marshall MS | Establish schedules and implement strategies that provide increased learning time | Lack of documentation of increased learning time for teachers. | Provide documentation | Myra G | Ongoing | In Progress | Compliance Specialist is providing ongoing technical assistance to school to ensure documentaiton is being maintained
9a | 9 | Thurgood Marshall MS | Provide appropriate social-emotional and community-oriented services and supports for students | Provide evidence the Turnaround steering committee is monitoring the social-emotional supports being provided to students and families at TMMS. | Provide documentation | Dr. Arbogast and E. Ryans | Monthly beginning September 24, 2012 | In Progress | Monthly Turnaround Executive Committee meetings will resume for the 2012-2013 school year on September 24, 2012
9b | 9 | Thurgood Marshall MS | Provide appropriate social-emotional and community-oriented services and supports for students | Provide agenda and notes for Dec. 8th PBIS meeting. | Provide documentation | Principal | Ongoing | In Progress | Do not have; Compliance Specialist will provide technical assistance to principal and leadership team concerning S.A.N.E. requirements
9b | 9 | Thurgood Marshall MS | Provide appropriate social-emotional and community-oriented services and supports for students | Provide student and parent surveys, referral data, suspension, and attendance data. | Provide documentation | Mid-Atlantic | Ongoing | In Progress
9b | 9 | Thurgood Marshall MS | Provide appropriate social-emotional and community-oriented services and supports for students | Provide documentation for funds spent on PBIS incentives. | Provide documentation | C. Moore | Ongoing | In Progress
9b | 9 | Thurgood Marshall MS | Provide appropriate social-emotional and community-oriented services and supports for students | It was reported the Turnaround Office has documents related to PBIS incentives but were not available. | Provide documentation | C. Moore | Ongoing | In Progress
9d | 9 | Thurgood Marshall MS | Provide appropriate social-emotional and community-oriented services and supports for students | Initial intent - $5000.00/school, but the budget was loaded to the District office. (The amendment will be written to reflect the misinterpretation of the original amendment.) | File Amendment request & approval | Myra G | Complete | Complete | Year 2, Amendment #4 was submitted and approved removing this language from the grant

## Table 7-10
Table #. Quest # | School | MSDE Questions | Findings | Owner | Date Due | Status (Not Started, In Progress, Complete) | Comment
7.3 | Benjamin Stoddert MS | What action steps or planned activities have not taken place that would impact budget | Funds not used for AVID Conference Travel - conference to take place in Summer 2012 | C. Moore |  | Complete
7.4 | Benjamin Stoddert MS | Has budget amendment been submitted? What changes were requested for this school? | Amendment to be submitted March 2012 - ($11K) to be realigned from supplies to equipment | Myra G |  | Complete
8.3i | Drew Freeman MS | What action steps or planned activities have not taken place that would impact budget | Vacant position for academic resource coach - position will be re-advertised | E. Ryans |  | Complete
8.3ii | Drew Freeman MS | What action steps or planned activities have not taken place that would impact budget | Funds not used for AVID Conference Travel - conference to take place in Summer 2012 | C. Moore |  | Complete
9.3i | G James Gholson MS | What action steps or planned activities have not taken place that would impact budget | Transportation for parents to come to school events $16,800 has not been spent | C. Moore and Myra G | Ongoing | In Progress | Year 2 Amendment #4 expanded scope of this category
9.3ii | G James Gholson MS | What action steps or planned activities have not taken place that would impact budget | Funds not used for AVID Conference Travel - conference to take place in Summer 2012 | C. Moore |  | Complete
10.3i | Thurgood Marshall MS | What action steps or planned activities have not taken place that would impact budget | Math Coach Position is vacant | E. Ryans |  | Complete
10.3ii | Thurgood Marshall MS | What action steps or planned activities have not taken place that would impact budget | August Academy not conducted ($57K) | C. Moore and Myra G |  | Complete | August 2012
10.3iii | Thurgood Marshall MS | What action steps or planned activities have not taken place that would impact budget | Transportation for parents to come to school events $16,800 has not been spent | C. Moore and Myra G | Ongoing | In Progress | Year 2 Amendment #4 expanded scope of this category
10.3iv | Thurgood Marshall MS | What action steps or planned activities have not taken place that would impact budget | Funds not used for AVID Conference Travel - conference to take place in Summer 2012 | C. Moore |  | Complete

## Table 11-12
Table #. Quest # | Budget | MSDE Questions | Findings | Owner | Date Due | Status (Not Started, In Progress, Complete) | Comment
11.2 | SIG 1 Year 2 LEA ARRA Budget | Is LEA spending consistent with budget timeline? | Spending not on target for most categories - Amendment to be submitted March 2012 | Myra G | December 31, 2012 | In Progress | Amendment #4 was approved by MSDE on 8/24/12. Final Spend-down will begin in mid-October 2012 (grant extension until December 31, 2012)
11.3 | SIG 1 Year 2 LEA ARRA Budget | What action steps or planned activities have not taken place that would impact budget | Concern in the category of salaries; for teacher incentives $1,541,372 - negotiations in progress with the teacher's union | E. Ryans | December 31, 2012 | In Progress | After further discussions with PGCEA, an agreement on teacher incentives has been reached; "offer letters" have been signed by all PGCEA employees; ILT's are part of PGCEA so they will receive the same incentive stiped as teachers
11.4i | SIG 1 Year 2 LEA ARRA Budget | Has budget amendment been submitted? What changes were requested for this school? | Amendment to be submitted March 2012 | Myra G | December 31, 2012 | In Progress | Amendment #4 was approved by MSDE on 8/24/12. Final Spend-down will begin in mid-October 2012 (grant extension until December 31, 2012)
11.4ii | SIG 1 Year 2 LEA ARRA Budget | Has budget amendment been submitted? What changes were requested for this school? | $170K Funds to be re-aligned | Myra G | December 31, 2012 | In Progress | Amendment #4 was approved by MSDE on 8/24/12. Final Spend-down will begin in mid-October 2012 (grant extension until December 31, 2012)
12.3 | SIG 1 LEA Budget | What action steps or planned activities have not taken place that would impact budget | Concern around funds for teacher incentives $439,126 - negotiations in progress with teachers union | E. Ryans | December 31, 2012 | In Progress | After further discussions with PGCEA, an agreement on teacher incentives has been reached; "offer letters" have been signed by all PGCEA employees; ILT's are part of PGCEA so they will receive the same incentive stiped as teachers